## TO DO - By Key Dates
Outline of Typical Tasks for Maine Building Applicants and Exhibitors- grouped into an event countdown
Key Tasks - By Timelines | J | F | M | A | M | J | J | A | S | O | N | D
240 + days before fair
Reviewed application materials | bar: J; D
Submitted application | bar: J to F
Subscribed to email updates
120+ days before fair
Reviewed Exhibitor Resources | bar: M to J
Orientation and signed terms and conditions | bar: M to J
80-90 days before fair (avg. June 1)
Reserved and scheduled in-person site visit-in person (available to 17-day renters paid in full) | bar: A to J
Reserved accommodations (e.g. hotel, vacation rental, off-site RV, etc.) | bar: A to J
Reserved off-site, and on-site storage, and amenities | bar: A to J
Submitted final logistics info and paperwork to Building Management
Submitted insurance certificates | bar: A to J
Submitted booth rental exhibit payment – Due July 1 | bar: J
60-70 days before fair
Provided final staffing headcount to Maine Building Management | bar: M to J
Made site visit (only for 17-day renters paid in full) | bar: J to J
Set up an account with the on-site bank (if needed) | bar: J to S
40-50 + days before fair
Submitted dead storage payment to ESE (if needed) | bar: J to A
Completed any paperwork required by the ESE and/or town | bar: J to A
Reserved internet | bar: J to A
Reserved phone line (if needed—some Point of Sale systems require) | bar: J to A
40+ days before fair – FOOD and BEVERAGE exhibitors completed:
Submitted required paperwork and payment to appropriate authority for the Town of W. Springfield | bar: M to J
Provided updated information and/or status to comply with local codes | bar: M to J
Allergen training (food) | bar: M to J
ServSafe training (food) | bar: M to J
TIPS (alcoholic beverage) | bar: M to J
10 Days before fair (just before Labor Day)
Reviewed suggested packing list, and have adequate supplies and prepared gear and inventory | bar: A; A to S
Stored emergency numbers and contact information for your staff | bar: A; A to S
Print a copy of important documents to have on file at site | bar: A
Scheduled event-related updates to social media and tag the Big E! fair | bar: A; A
Begin exhibiting (on site, beginning first Friday after Labor Day)
Obtained parking passes –from Maine Building Management, on site | bar: S
Admission credentials –from Maine Building Management, on site | bar: S
Reviewed the walk-through for emergency evacuation map and identified meet-up location for all staff | bar: S
FOOD and BEVERAGE temporary permits – Handed out by local officials Thursday(s) through Saturday(s) | bar: S
Readied exhibit, locate places of interest/need on grounds, in building etc. | bar: S
Exhibition is over
Removed signage, display material, supplies, remaining inventory, storage etc. – relocate to off-site storage | bar: S
Removed signage, display material, supplies, inventory, storage etc. – relocate to off-site storage | bar: S

## TO DO - By Category
Outline of Typical Tasks for Maine Building Applicants and Exhibitors- grouped into common categories
Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process
Key Tasks - By category | J | F | M | A | M | J | J | A | S | O | N | D
Paperwork, required info to Building Management
Reviewed application materials | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J; Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process D
Submitted application | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process F
Subscribed to email updates | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J; Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process N to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process D
Reviewed Exhibitor Resources | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process M to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
Orientation and signed terms and conditions | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process M to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
Submitted final logistics data to Building Management | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
Submitted insurance certificates | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process M to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
Submitted final staffing headcount to Maine Building Management | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process M to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
Requested, scheduled site visit (only for 17-day renters paid in full) | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process M to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
Made site visit (only for 17-day renters paid in full) | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
Expenses
Reserved accommodations (e.g. hotel, vacation rental, off-site RV, etc.) | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
Reserved off-site, and on-site storage, and amenities | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
Submitted booth rental exhibit payment – Due July 1 | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
Submitted dead storage payment to ESE (if needed) | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A
Reserved internet | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A
Reserved phone line (if needed—some Point of Sale systems require) | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A
Admission credentials (for not complimentary) | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process S
Licensing and training (generally to Town of W. Springfield)
Created online account (food permit application) | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
Allergen training (food) | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
ServSafe training (food) | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
TIPS (alcoholic beverage) | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A
Liquor License Commission Meeting (alcoholic beverage) | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process S
Food/beverage permits – Local officials disburse Thursday(s) - Saturday(s) | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process S
Promotion and publicity
Contact collector for email | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
Professional signage | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
Professional marketing materials - product, price list, etc. | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
Scheduled event-related updates to social media and tag the Big E! fair | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A; Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process S
Sales, labor, inventory, revenue etc.
Set up an account with the on-site bank (if needed) | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process S
Recruited staffing help | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process M to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process S
Key points and training for staff | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process S
Planned and prepared inventory | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A
Set budget and sales goals | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process J
Event Preparation
Reviewed suggested packing list - adequate supplies, gear and inventory | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A; Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process S
Stored emergency numbers and contact information for your staff | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A; Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A to Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process S
Print a copy of important documents to have on file at site | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process A
Walk through emergency evacuation map, ID gathering spot | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process S
Readied booth space, identify places of interest/need on site | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process S
Post-Event
Clean exhibit space: remove all waste, tidy, ready for off-season deep clean | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process S
Remove signage, display material, supplies, inventory, etc. (May move to off-site storage) | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process S
Admission, Credentials, Passes, Etc. (Limited Complimentary)
Obtained parking passes –from Maine Building Management (on site) | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process S
Admission credentials –from Maine Building Management (on site) | bar: Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process S

## Moving Schedule
2022 | SEPTEMBER |  | SUNDAY
CALENDAR YEAR | CALENDAR MONTH |  | FIRST DAY OF WEEK
44801 | 44802 | 44803 | 44804 | 44805 | 44806 | 44807
2022-08-28 | 2022-08-29 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03
[5 empty] | Day 1 - First Day of Fair | Day 2
KEY: |  | Group A (17-day) load In Times: 8:00AM -5:00 PM |  |  | [Group A - START
17- Day: Group A | Short Term: Group D | [ = start exhibit | ] = end exhibit | 17 Day exhibitors: Building Mgmt distributes passes noon- 3PM at ME Building | [Group B - START
Short Term: Group B | Group E |  |  |  | Bldg open to exhibitors: 8AM-9:30PM | MAINE DAY
Short Term: Group C |  | Short term PM load out/in | Short Term AM load out/in |  |  | [Group E ]
Open to exhibitors: 8AM-9:30PM
Short term PM load in @ noon
Group B |  |  |  | Group B load in noon- 5
Special event day
Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9
Open to exhibitors: 8AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Open to exhibitors: 8AM-9:30PM
Group B - END]
|  |  | Group B - END] | [Group C START
|  |  | Short term PM load out/in | Short Term AM load out/in
Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16
Open to exhibitors: 8AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Open to exhibitors: 8AM-9:30PM
|  | Group C- END] | [Group D - START
|  | Short term PM load out/in | Short Term AM load out/in |  | Harvest New England Day
Day 17 - Last Day of Fair |  | REMINDERS: | Maine Building hours of operation - Open to public 10AM-9PM
Open to exhibitors: 8AM-10:30PM | All remaining load out - Access: 6:30AM-12:00 (noon) PM | Deliveries to grounds and booth: between 8:00 and 9:15 AM Booth designee must be present at delivery. Alert management of delivery plans. Short term load in/out, unless told otherwise: LOAD IN: Evening before start date (after building closes to public), until 10:30 PM, and the morning of start date 7 to 9 AM. LOAD OUT: Evening of end date (after building closes to public), until 10:30 PM, and morning after 7 to 9 AM.
Group A END]
Group D END]
Updated January, 2022

## 2022 Load In Out
How to use: find your group letter. Use the rows and columns to see the number of days, exhibit dates, and load in/out specifics.
Building is open to public 10 AM to 9 PM daily |  |  |  | LOAD IN - Times and Dates |  |  |  | LOAD OUT - Times and Dates
EXHIBITOR DETAILS
Group | Exhibits on these fair days | # of exhibit days | Exhibit dates | How soon can I start load in? | Dates | When does load in end? | Dates | How soon can I start load out? | Dates | When does load out end? | Dates
A | 1 thru 17 (Friday - Sunday) | 17 | 9/16-10/2 | Tuesday before the fair starts | 9/13-9/15 | 2 PM before exhibit start date (must be done by 5 PM) - Thursday (AKA day before fair starts) | 2022-09-15 | Exhibit end date (also last day of fair) - Sunday evening - between ~ 9 & 10:30 PM | 2022-10-02 | 6:30 AM to noon day after the fair (Monday) | 2022-10-03
B | 1 thru 6 (Friday - Wednesday) | 6 | 9/16-9/21 | 2 PM before exhibit start date (Thursday afternoon) | 2022-09-15 | 3 PM before exhibit start date must be done by 5 PM (Thursday) | 2022-09-15 | Exhibit end date - between ~ 9 & 10:30 PM (Wednesday after Building closes to public) | 2022-09-21 | 6 AM to 8:30 AM day after exhibit end date (Thursday before Building opens to public) | 2022-09-22
C | 7 thru 12 (Thursday - Tuesday) | 6 | 9/22-9/27 | Evening before exhibit start date - between ~ 9 & 10:30 PM (Wednesday after Building closes to public) | 2022-09-21 | 6 AM to 8:30 AM on your exhibit start date (Thursday before Building opens to public) | 2022-09-22 | Exhibit end date - between ~ 9 & 10:30 PM (Tuesday after Building closes to public) | 2022-09-27 | 6 AM to 8:30 AM day after exhibit end date (Wednesday before Building opens to public) | 2022-09-28
D | 13 thru 17 (Wednesday - Sunday) | 5 | 9/28-10/2 | Evening before exhibit start date - between ~ 9 & 10:30 PM (Tuesday after Building closes to public) | 2022-09-27 | 6 AM to 8:30 AM on your exhibit start date (Wednesday before Building opens to public) | 2022-09-28 | Exhibit end date - between ~ 9 & 10:30 PM Sunday evening (also last day of fair) | 2022-10-02 | 6:30 AM to noon day after the fair (Monday) | 2022-10-03
E | 1 (Saturday) | 1 | 2022-09-16 | 7 AM to 9 AM same day as exhibit date (Saturday morning) | 2022-09-16 | Same as exhibit date 7 AM to 9 AM on exhibit date (Saturday morning) | 2022-09-16 | 5 PM - same day as exhibit date (Saturday evening) | 2022-09-16 | 7 PM - same day as exhibit date (Saturday evening) | 2022-09-16

## 2022 Fair Dates
2022 Fair Dates
SUN. | MON. | TUES. | WED. | THURS. | FRI. | SAT.
KEY: |  | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17
Group A | Group D
Group B | Group E
Group C
2022-09-18 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24
2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01
2022-10-02

## 2022 Meeting Dates
Maine Building Exhibitor – Meeting, Orientation, Open Office Dates 2022
Please save the dates—invitation details will be sent separately:
April
Welcome and Orientation – Webinar Call; required for all exhibitors
3 PM to 5 PM, Thursday April 14, 2022
Agenda:
o Welcome & Introductions – 30 minutes
§ Building Management
§ Exhibitors
§ Others
o Contact Information – 5 minutes
o Logistics and required information – 45 minutes
§ Key dates
§ Agreements, Terms & Conditions
§ Billing
§ Code enforcement and compliance (fair, town, etc.)
§ Amenities and services
· Internet
· Storage rental
§ Q and A – 20 minutes
June
Open Office Hours; optional teleconference: Thursday 6/23/22 1 PM to 2 PM
Q and A; Building Management will be available to review questions
Meeting with Big E Fair: TBD/TBA
August
Open Office Hours; optional teleconference: Tuesday 8/23/22 10 AM to 11 AM
Q and A; Building Management will be available to review questions
September
Exhibitor Huddle (17-day exhibitors)
Maine Building, Thursday afternoon before fair opens (approximately 4 PM)
Updated March 2022