## Slide 1: Maine CDC
Review of SIM Work
August 24, 2016
National Diabetes Prevention Program Community Health Worker Initiative

## Slide 2: Hypothesis: National Diabetes Prevention Program
If the NDPP is integrated into population health management strategies in Maine, we can prevent or delay the progression/onset of Type 2 diabetes for those with prediabetes or at high risk for diabetes. For those who progress to a diabetes diagnosis, they consume 2.3 times more health care dollars.
Conclusion: As of July 2016 – 1,104 program eligible people in Maine have participated in the NDPP and are no longer at risk for Type 2 Diabetes. Further integration and acknowledgement of prediabetes and how to screen for it in clinical/non-clinical settings will continue under U.S. CDC Grant (DP13-1305).
  U.S. CDC Diabetes Risk Test (www.rethinkdiabetes.org)
  U.S. CDC Recognized Lifestyle Change Program a.k.a. NDPP
Notes:     Medical expenses for those with diabetes diagnosis on average 2.3 times more compared to those without diabetes
Citation: Diabetes Surveillance Report, Maine 2012.
Centers for Disease Control and Prevention. National diabetes fact sheet: National estimates and general
information on diabetes and prediabetes in the United States, 2011. Atlanta, GA. U.S. Department of
Health and Human Services, Centers for Disease Control and Prevention, 2011.Accessed at
http://www.cdc.gov/diabetes/pubs/factsheet11.htm on 14th Aug, 2012.

## Slide 3: National Diabetes Prevention Program
NDPP is based on a research study that demonstrated:
  Adults at high risk for type 2 diabetes can prevent or delay the disease by 58% (71% if over age 60) by making modest lifestyle changes through a structured program.
Lifestyle coaches work with a group to help them reduce their risk of developing type 2 diabetes by:
  Losing weight through healthy eating
  Being more physically active
  Learning to identify and address barriers to healthy eating and physical activity
  Even after ten years, those who participated had a 34% lower rate of type 2 diabetes.
DPP study, NEJM; Feb. 2002

## Slide 4: SIM Objective: Implementation of the National Diabetes Prevention Program
By September 30, 2016, there will be:
  At least 20 nationally accredited NDPP provider sites with written data sharing/fidelity agreements
  At least 80 trained/certified NDPP lifestyle coaches
  At least 600 eligible adults will have completed the program with fidelity
    Program fidelity = complete minimum of 9 sessions in first six months and minimum of 4 in second six months

## Slide 5: Benefits – Outcomes to Date Based on SST
Pre-SIM
9 NDPP US CDC recognized provider sites
42 trained and deployed lifestyle coaches
104 participants completed with program fidelity
As of August 2016
17 NDPP US CDC recognized provider sites (this is down from 20)
  11 additional sites since SIM
151 trained and deployed lifestyle coaches
  109 additional since SIM
  2 more trainings are scheduled for September 2016
1,104 participants completed with program fidelity
  1,000 additional since SIM

## Slide 6: Benefits
One Maine health plan (State of Maine) has added NDPP coverage to their health plan design.
One commercial health plan (Harvard Pilgrim) has begun researching NDPP to identify a way to incorporate coverage of this service into health plan offerings in Maine.
Claims/cost analysis for pre-diabetes and diabetes related to MaineCare members is underway to estimate the cost/benefit of adding NDPP for MaineCare beneficiaries to be completed by March 2017.
Promoted NDPP as an effective way to manage population health in payment structures for payers, ACOs and other value based purchasing strategies to 20 health care organizations in Maine.
CMS has announced intent and proposed provisions for NDPP coverage starting January 2017. As of today 17 out of 20 organizations in Maine are eligible to begin tracking/billing. Payment for eligible beneficiaries starts January 2018.
  Maintaining U.S. CDC DPRP Pending/Full Recognition impacts eligibility for billing.
Notes: Sites that lost Recognition in 2016:
Community Health and Counseling Services
St. Josephs Hospital
Waldo County General Hospital
New site that just joined in August 2016: Central Maine Conditioning Clinic

## Slide 7: Future Recommended Changes/Lessons Learned
Directly reached out to Commercial Payers from the beginning of the project.
SIM funds to support a NDPP representative to attend and drive the agenda on NDPP throughout the entire SIM project scope in all committees.
Identify and advise on Quality Measures for Population Health strategies that target people at high risk for Type 2 Diabetes; recommended protocol for use of evidence-based lifestyle change programs (NDPP).

## Slide 8: Sustainability Recommendations
NDPP Master Trainer Select business plans available to be shared with any organizations in Maine.
Maine NDPP Data Dashboard; Build a referral module for securely transmitting participant session data to PCPs for documentation/billing.
Prediabetes standard of care diagnosis/care planning that uses and tracks NDPP participation/completion.
  CPT 0403T (NDPP participation tracking code introduced January 2016)
NDPP provision for coverage for all payers in Maine. Maine CDC able to provide Technical Support for any Maine payer on health plan design before January 2018.

## Slide 9: Other
External Support for people at high risk for/with chronic diseases.
Better use of community-based organizations and help health systems understand how to contract for Population Health and Self-Management Support through ACOs/VBID.
Work with Payers to establish provision and performance-based coverage for people at risk for chronic diseases who are well managed or have moved themselves outside of risk.
  Prediabetes/Diabetes, Hypertension, Lipids…

## Slide 10: Next Steps Post SIM
Continue technical assistance/support to NDPP sites.
NDPP Data Dashboard for real time reporting by lifestyle coaches.
Technical Assistance to organizations offering NDPP Master Trainer Select and/or NDPP Lifestyle coach trainings.
Support use of guidelines/recommendations in the delivery system and health plan design through employers/payers under DP13-1305 Prevention and Control Grant from U.S. CDC through July 2018.
Continue http://rethinkdiabetes.org/ as the State of Maine information portal on NDPP – Referral and “Upcoming Classes.”
Continue to grow and support the integration of NDPP into Maine’s health care delivery system through DP13-1305 Prevention and Control Grant from U.S. CDC through July 2018.
  Policy/protocol in both clinical/non-clinical settings supporting populations at high risk for Type 2 Diabetes.
  Lifestyle Coach Network 151 and growing.
  Maine NDPP Annual Meeting (May 12th 2017).

## Slide 11: Hypothesis: Community Health Worker Initiative
If CHWs are recognized as valued members of the health care system in Maine, they can support improved health outcomes, appropriate utilization of health care services, and increased cost savings related to chronic disease support, cancer screening, and high risk or high consumers of health care services.
Conclusion:
  Achieved increased recognition of CHWs as a potential member of workforce.
  Pilot sites provided Maine-specific examples.

## Slide 12: Community Health Workers
Institute for Clinical and Economic Review report summarized results of studies related to CHWs – 2013
Contributions of CHWS:
  Improving health outcomes.
  Supporting appropriate utilization of health care services.
  Increased cost savings specific to:
    Chronic disease support
    Cancer screening
    High risk or high consumers of health care services
  Majority of the 14 studies showed net cost savings over 6 months to 2 years relative to control groups.
Institute for Clinical Effectiveness and Review:
http://cepac.icer-review.org/?page_id=1066

## Slide 13: CHWI Hypothesis Conclusion – Formal Recognition
CHWI achieved formal recognition of CHWs:
  DCW Registry to go live June, 2017
  Voluntary Components - CHWs may register for “training, education and compliance purposes”
  Standardized components set the path for payers to pursue payment models or reimbursement for CHW services
Notes: The goals under SIM-
(1) demonstrate the value of integrating CHWs into the health care team;
(2) provide models that can be replicated and emulated across the state;
(3) build a core group of experienced CHWs who can provide leadership and community engagement to drive the ongoing development of the system

## Slide 14: CHWI Hypothesis Conclusion- Recognition from System
CHWI Evaluation examined factors that contributed to successful integration of CHWs, two key observations -
  Clinical provider familiarity and desire to integrate CHWs was observed as growing.
  Grantees reported that providers appreciated the pilot intervention.
I feel [leadership to sustain CHW interventions] is in place. It’s very easy to communicate. Staff and providers huddle each morning. In addition, we use the EMR. It’s very easy to access the providers with questions and to send notes. It’s huge. If I didn’t work directly with providers that would be a huge challenge. CHW.
Notes: Key Informant Interviews were conducted with ___ individuals who were CHWs, Supervisors, Clinicians, Community Partners and/or content experts. Site visits were completed with all four pilot projects.
Give examples of model spread- Androscoggin Home Health (CCT) and one of the pilots committing to hiring 3 new CHWs

## Slide 15: CHWI Hypothesis Conclusion - Provide Models that can be Replicated
CHWI effectiveness-
  Pilot Level - Individual performance metrics tied to intervention and population of focus (i.e. cancer screenings, chronic disease support and promoting appropriate utilization to high risk consumers).
  Capacity-Building-Level – Promote growing workforce in order to spread the model with a focus on long-term sustainability.
Notes: The goals under SIM-
(1) demonstrate the value of integrating CHWs into the health care team;
(2) provide models that can be replicated and emulated across the state;
(3) build a core group of experienced CHWs who can provide leadership and community engagement to drive the ongoing development of the system

## Slide 16: Benefits – SST Measures to Date
5.5 FTE CHWs hired by 4 Pilot Projects (9 individuals).
Referral Mechanisms or MOAs at all 4 Pilot Projects:
  MeGeneral- Referral Mechanism with 4 affiliated PC Practices
  Portland Public Health- MOA with primary partner (MaineHealth)
  DFD Russell- 2 MOAs with hospital and BCCP
  AAAs- 5 MOAs (hospital, FQHC, home care, EIM, behavioral health)
CHW process divided into clients and encounters:
  1726 total clients have been engaged with a CHW
  223 intensive clients (i.e. longer engagement/more time & attention)
  4908 Encounters completed
Notes: SST Measures included
300 clients to be served under CHW Pilot Projects
Pilots to establish formal referral mechanisms (expected 1-3 per pilot project)
Client – engaged beyond one time information sharing/outreach
Encounter – interaction beyond one time information sharing/outreach. May include patient assessment, referral and follow up, providing medication safety education, peer support
Intensive client – requires more than their first month of engagement. Three or more encounters per month with a total amount of time applied on behalf of the client equaling or exceeding 120 minutes.

## Slide 17: Benefits – Workforce
Workforce Expansion
    37 CHWs and 19 supervisors completed core training under Maine SIM (November 2014/October 2015).
    Training in 2015 integrated draft core competencies.
    Workforce model fills an emerging need by supporting clinicians practicing at top of license.
    Focus on Population Health - Maine disparities, chronic conditions.
    Involvement of CHWs in Capacity/Infrastructure Work of the Stakeholder Group.
    Final SIM training will focus on CHW Trainers (September).

## Slide 18: Benefits – CHWPP Contribution to Understanding of CHW Model
Notes: Community resources – LIHEAP, SNAP, legal assistance, transportation, link to local church for socialization, long term care in the home, assist signing up for Medicare Savings programs, Money Minders to help keep finances straight, housing application, pharmacy to make home deliveries

## Slide 19: Benefits – Capacity and Infrastructure
Convening of CHW Stakeholder Group:
  30 active members, 100 receiving information
Work completed to date:
  Definition of CHW (2014)
  Recruitment Guidance (2014)
  Core Role and Responsibilities (2014)
  Code of Ethics (2016)
  Core Competencies (2015)
  Standards for Qualifying CHWs (2015-present)

## Slide 20: Future Recommended Changes/Lessons Learned
CHW participation in decision making strengthens interventions.
Integration and provider buy-in takes time where no first hand experience with CHWs.
Shared data and communication systems are key to model uptake, monitoring and evaluation.
Ensure clarity about data collection roles and responsibilities.
Establish a common set of data metrics to measure CHW effectiveness.

## Slide 21: Sustainable Funding Models
Sustainable Funding Models for CHWs likely include a mix of options such as:
Promote CHWs as an effective way to manage population health in payment structures for all payers, ACOs and other value based purchasing strategies.
Explore CMS rule change that includes CHW services as a reimbursable service (i.e. preventive services rule-change).
Explore continued use of Medicaid state plan amendment that includes ability to reimburse practices for CHW services as part of PMPM payment (i.e. as under CCT SPA).
Promote integration of CHWs under prospective Medicare Payment Models.
Notes: New value based payment structures include CHWs as an effective way to provide culturally appropriate information and outreach to patients that may be difficult to reach in other ways
CHWs are integrated into team approaches to patient care such as community care teams or other community organizations
Infrastructure exists to support CHWs including training

## Slide 22: Sustainability Recommendations- Adopting CHW Payment Models
UMass Report- Sustainable Financing Models for CHWs in Maine - draft in process
Models are built on:
-Evidence of a population health need using ME data.
Best-Practice recommendations/model on addressing the need (research base).
Costs to deliver intervention based on data from 7 CHW Employers in ME and associated medical costs.
Projected changes in medical costs, health outcomes, improved quality metrics, ROI, SROI based on model.

## Slide 23: Sustainability Recommendations- Adopting CHW Payment Models

## Slide 24: Other
“We’re very happy with the [CHW] model and I try to push it a lot... Different models have RNs doing everything – social work, clinical management, home visits. The lesson we have learned is, however, that [for cost-efficacy] people need to work at the top of their license. Clinical Patient Specialists are RNs who do everything (fill medicines, etc.) but that means they are not working at the top of their licensure. Far less education and licensure are needed than a RN for many of the tasks. It’s not as sustainable as a CHW model.” QI Stakeholder
I often do work that a family member would do, but many don't have a family member to do that, or don’t have one who is knowledgeable and literate. CHW
Assisting with educating families and the public, helping people in their homes, assisting with keeping appointments, supporting prescription management, and facilitating connection to services. CHW services are not intended to take the place of higher level health services. They advance patient quality of care, help with repeat visits, allow individuals to stay home longer (rather than to need assisted living), and provide support for family members to consider next steps with more options. Workforce Development Specialist

## Slide 25: Next Steps Post SIM - Institutionalizing Infrastructure
Support CHW networking and convening to strengthen Maine's PH Workforce.
Support implementation of Direct Care Worker Registry as it pertains to CHWs.
  CHW specific recommendations for DCW Registry (qualifications, training standards) in place, assuring that Maine CHWs are able to use registry when opens June, 2017.
Promote and Institutionalize Standardized Training for CHWs in Maine.
Review evaluation recommendations for potential next steps.

## Slide 26: Next Steps Post SIM – Promoting Sustainable Payment Models
Disseminate findings from UMass Payment Model work to help promote CHWs and inform evolving payment models in Maine and region.
  Develop materials/mechanism/timeline for disseminating results to payers and employers.
  Determine next steps such as webinars or other forums.