# Evaluation SIM Subcommittee Monthly Summary for Steering Committee

Meeting date: 7/22/2015

Number of participants: 24

Organizations Represented: DHHS/OCQI, MaineCare, Maine Medical Association, Maine Osteopathic Association, MHMC, Maine CDC, ME Association of Health Plans, Health InfoNet, Anthem BCBS, Consumers, Lewin, Market Decisions, Crescendo Consulting

- Please state the subcommittees strategic focus for the month:

- Review/discussion of MaineCare Targets for SIM Core Measures

- Review/ discussion of Consumer Interview results and potential opportunities to improve the patient experience of care

- Please state the subcommittees key findings/work/impact for the month:

- Committee feedback and recommendations for provider communication strategy related to MaineCare Targets will be presented at August Steering Committee.

- Requested additional analysis of consumer interview results by demographics and duration of time in SIM interventions

- Please describe which SIM goals were the primary focus of the subcommittee, and how they may be impacted:

- Maine SIM Core Measure Target setting serves to evaluate the impact of SIM interventions on cost and quality of care

- Consumer interview analysis provides insight as to how SIM interventions are impacting the patient experience of care and the patient’s engagement in their care

- Please state the subcommittees challenges for the month:

- Development of an effective provider communication strategy related to MaineCare Targets for SIM Core Measures.

- Please state the subcommittees risks for the month:

No risks were identified for July 2015; Several risks have been historically identified by the committee related to data availability for evaluation, and those risks have since been resolved so no need to raise to Steering Committee.

- Please summarize the goals for next month’s subcommittee meeting:

- Demonstration of & feedback to the latest iteration of the SIM Dashboard (extra meeting August 13, 2015)

- Review / discussion of findings from provider/stakeholder and consumer interviews

- Initiate Rapid Cycle Improvement discussions of evaluation data available to date