Provider Change Fatigue:

Risk Description-

- Define Provider, what does maxed out mean, target audience, and understanding what the burden of change is more specifically

- Many different structures that are duplicating functions, that is spurring on fatigue, Support structure Duplication

- PCPs and RNs other clinical staff, most providers don’t see this related to SIM, acceleration of change

- Primarily in Primary Care, burn out rates high

Root Causes-

Alignment

- Overlapping priorities, ACOs, Medicaid ACs, ACI

- Haven’t aligned existing structures in order to consolidate, need more alignment

- Lack of performance measure alignment

- Need to map out the changes, define, pacing, rewarding…

- Failure to link many initiatives to improved patient care

Transformation of Roles

- Challenge to trust that measures accurately reflect their work.

- Payment reform is not keep up with Deliver System Reform

- Transformation of role of provider- big ask of them

- Consumer empowerment, change from old system

- Current payment disconnected from goals of transformation

- Rate of Change and Volume of Change

Leadership Drivers

- Better we do, more we lose- Hospital system could attest

- Physicians are inherently not embracers of change

- Fear of poorly managed change

- Leadership sometimes conveys needs to drive RVUs, not intentional but how it’s perceived.

- PCP shoulder burden without tools – high expectations – Don’t want to just be cogs in a machine

Context/ Resources

- Resource challenge

- Lack of context, comes at them from all directions-

- Not providing tools to providers to accept transformation

Ideas for Mitigation-

Prioritization/Clarification

- Prioritize risks by what we can control

- Scan what is already in place in order to not duplicate

- Clarify what changes are and their impacts

- Prioritizing what changes need to be made

- ID inequity of care coordination and resources- GAP analysis

- Allow provider community prioritize the change

- Identify successes and positive change, highlight that, and celebrate it

- Creating all these changes priority over payment reform, backwards, transparency should come after payment reform.

Understanding and Tool Development

- If you don’t understand what SIM is you will be more concerned about negative impact

- Understanding where providers find duplication in the system and its impact

- Understanding what providers need to get in place before they can even start transformation

- Providers need to understand what is actionable and realistic and understand who owns it

- Allow provider community prioritize the change

- Understand what are the characteristics of high functioning practices with high satisfaction

- Using SIM, provide tools to provider community to make changes we are asking for

- Need to respect timing - Not create false sense of urgency- realistic timeframes

Alignment

- Change management practices

- Organize payers to align measures and payments- Coalition

- Change management alignment, could stick in leadership piece