## Sheet1
Item # | Risk/Issue/Dependency Name | Impacted SIM Objectives (SST Obj #, eg. MHMC #3, HIN #4, etc) | IF…. | THEN… | Accountability Target Impacts | Drivers Impacted | Item Owner (Project Manager Name) | Status (Open, In Progress, Resolved,Closed) | Creator (Originator) | Date Created and Date Closed | Updated by (name) | Date last updated | Weighted Priorty (1= Low, 3= Med, 5 = High) | Probability 1-3 (1=Low, 2= Med 3=High) | Impact 1-3 (1=Low, 2= Med 3=High) | Priority Calc | Details | Plan to address (free form) | Above (A) or Below (B) waterline for Risk Mitigation Planning | Risk Plan Complete
26 | The current delivery system does not provide or foster robust, supported patient education across transitions of care, at wellness visits, or acute and chronic illness follow up that is patient centered. This results in poor patient understanding and satisfaction, additional cost and poor quality. |  | If Patients aren't effectively educated about ways to manage chronic disease | Then- consumer and patient engagement goals will be negatively influenced. |  |  |  | Open
Note on N1: Chenard, Randal: Weighted priority appropriately weights the risk based on the objectives that are potentidally impacted by the risks. If higher priority objectives are impacted by the occurance of the risk, then the risk would receive a higher Priority rating than if the risk may impact a less impactful objective. Refer to the Objecive weight assignments for determination, which is located on the 'weighted objective' tab in the spreadsheet. For example, a risk that may impact, the blue button pilot (HIN objective 5), will not be weighted as heavily as a risk that may impact the MaineCare Accountabile Community model development (MaineCare Objective #1)
Note on R1: Chenard, Randal: Free form, can capture additional descriptive info or any updates Chenard, Randal: