## Sheet1
Item # | Risk/Issue/Dependency Name | Impacted SIM Objectives (SST Obj #, eg. MHMC #3, HIN #4, etc) | IF…. | THEN… | Accountability Target Impacts | Drivers Impacted | Item Owner (Project Manager Name) | Status (Open, In Progress, Resolved,Closed) | Creator (Originator) | Date Created and Date Closed | Updated by (name) | Date last updated | Weighted Priorty (1= Low, 3= Med, 5 = High) | Probability 1-3 (1=Low, 2= Med 3=High) | Impact 1-3 (1=Low, 2= Med 3=High) | Priority Calc | Details | Plan to address (free form) | Above (A) or Below (B) waterline for Risk Mitigation Planning | Risk Plan Complete
5 | 20 | Change capacity for provider community may be maxed out – change fatigue – providers may not be able to adopt changes put forth under SIM | All SIM Delivery System Reform Initiatives MQC Obj 1 and 2 | If providers are overwhelmed with too many change initiatives at once, they may not be able to focus and prioritize the critical changes requried to transform the delivery system | Changes will be unable to be adopted or sustained; failure in delivery system reform |  | ????? | Steering Committee |  | Lisa Tuttle | 2014-02-25 |  | 4 | 2 | 3 | 24 |  | With DSR subcommittee for plan mitigation developmetn | A | N
Notes from June Steering Committee:
Provider Change Fatigue:
Risk Description-
Define Provider, what does maxed out mean, target audience, and understanding what the burden of change is more specifically
Many different structures that are duplicating functions, that is spurring on fatigue, Support structure Duplication
PCPs and RNs other clinical staff, most providers don’t see this related to SIM, acceleration of change
Primarily in Primary Care, burn out rates high
Root Causes-
Overlapping priorities, ACOs, Medicaid ACs, ACI
Challenge to trust that measures accurately reflect their work.
Build plane as you fly it
Haven’t aligned existing structures in order to consolidate, need more alignment
In between place
Payment reform is not keep up with Deliver System Reform
Lack of performance measure alignment
Resource challenge
Better we do, more we lose- Hospital system could attest
Stepping into Red Sea before Water is parted
Physicians are inherently not embracers of change
Transformation of role of provider- big ask of them
Lack of context, comes at them from all directions-
Consumer empowerment, change from old system
Poorly managed change
Need to map out the changes, define, pacing, rewarding…
Failure to link many initiatives to improved patient care
Not providing tools to providers to accept transformation
Current payment disconnected from goals of transformation
Leadership sometimes convey needs to drive RVUs, not intentional but how it’s perceived.
Rate of Change and Volume of Change
Ideas for Mitigation-
Prioritize risks we can control
Scan what is already inplace in order to not duplicate
Clarify what changes are and their impacts
Change management practices
If you don’t understand what SIM is you will be more concerned about negative impact
Understanding where providers find duplication in the system and it’s impact
Prioritizing what changes need to be made
Understanding what providers need to get in place before they can even start transformation
Providers need to understand what is actionable and realistic and understand who owns it
Organize payers to align measures and payments- Coalition
ID inequity of care coordination and resources
Change management, could stick leadership piece
Allow provider community prioritize the change
Understand what are characteristics of high functioning practices with high satisfaction
Identify successes and positive change, highlight that, celebrate it
Using SIM, provide tools to provider community to make changes we are asking for
Need to respect timing
Not create false sense of urgency- realistic timeframes
Creating all these changes priority over payment reform, backwards, transparency should come after payment reform.
Note on N1: Chenard, Randal: Weighted priority appropriately weights the risk based on the objectives that are potentidally impacted by the risks. If higher priority objectives are impacted by the occurance of the risk, then the risk would receive a higher Priority rating than if the risk may impact a less impactful objective. Refer to the Objecive weight assignments for determination, which is located on the 'weighted objective' tab in the spreadsheet. For example, a risk that may impact, the blue button pilot (HIN objective 5), will not be weighted as heavily as a risk that may impact the MaineCare Accountabile Community model development (MaineCare Objective #1)
Note on R1: Chenard, Randal: Free form, can capture additional descriptive info or any updates Chenard, Randal: