## Objective Summary
| Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| 10/1/13-9/30/14 |  |  |  | 10/1/14-9/30/15 |  |  |  | 10/1/15-9/30/16
Data Infrastructure Workstream | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
HIN Objective 1: | bar: 10/1/13-9/30/14 Q1 to 10/1/13-9/30/14 Q2
Provide real-time notifications from the HIE to MaineCare and Health System Care Managers when MaineCare members are admitted or discharged from impatient and emergency room settings across all provider organizations connected to the HIE
HIN Objective 2: | bar: 10/1/13-9/30/14 Q1 to 10/1/13-9/30/14 Q2
Provide HIT and HIE adoption incentives to up to 20 Behavioral Health provider sites/organizations
HIN Objective 3: | bar: 10/1/13-9/30/14 Q1 to 10/1/13-9/30/14 Q2
Provide Health Information Exchange access to Behavioral Health providers
HIN Objective 4: | bar: 10/1/13-9/30/14 Q1 to 10/1/13-9/30/14 Q2
Provide a clinical dashboard to MaineCare from the HIE enabling MaineCare to clinically monitor MaineCare members’ health care utilization and outcomes at the population and individual level. Develop and deploy real-time discrete data feeds for MaineCare Prescription data to HIN.
| Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| 10/1/13-9/30/14 |  |  |  | 10/1/14-9/30/15 |  |  |  | 10/1/15-9/30/16
Data Infrastructure Workstream | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
HIN Objective 5: | bar: 10/1/13-9/30/14 Q1 to 10/1/13-9/30/14 Q2
Provide Maine patients with access to their statewide HIE record leveraging the “Blue Button” standards promoted by the Office of the National Coordinator for HIT (ONC). HIN will conduct a twelve month pilot with a provider organization to make the patient chart available via a certified EHR portal administered by the pilot site.
Payment Reform Workstream
MHMC Objective 1: | bar: 10/1/13-9/30/14 Q1 to 10/1/13-9/30/14 Q2
Track health care costs to influence the market and inform policy - Construction and maintenance of robust valid data set and ongoing analytics
| Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| 10/1/13-9/30/14 |  |  |  | 10/1/14-9/30/15 |  |  |  | 10/1/15-9/30/16
Payment Reform Workstream | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
MHMC Objective 2: | bar: 10/1/13-9/30/14 Q1 to 10/1/13-9/30/14 Q2
Value based benefit design: Incentivize use of high value services and high value providers | 10/1/13-9/30/14 Q1: Year 1 Targets: (1) Adoption of core set of metrics against which plan designs may be benchmarked (2) Publication of initial rankings of benefit designs; 10/1/14-9/30/15 Q1: Year 2 Targets: 1) Refined metrics, as appropriate, based on trends and on market experience 2) Increase in number of covered lives enrolled in plans incorporating narrowly contstructed VBIC, to include alignment of copays/deductibles, utilization of high value providers as determined by MHMC Gent Better Maine rankings or ACI metrics and use of shared decision making of all preference senstives services. Enrollment in plans with such designs will grow from 0 to 10k in Year 1.; 10/1/15-9/30/16 Q1: Year 3 Targets: 1- Refined metrics, as appropriate, based on trends and on market experience 2- increase in number of covered lives enrolled in plans incorporating VBID from 10 k to 30k
Year 1 Targets: (1) Adoption of core set of metrics against which plan designs may be benchmarked (2) Publication of initial rankings of benefit designs
Year 1 Targets: (1) Adoption of core set of metrics against which plan designs may be benchmarked (2) Publication of initial rankings of benefit designs
Year 1 Targets: (1) Adoption of core set of metrics against which plan designs may be benchmarked (2) Publication of initial rankings of benefit designs
Year 1 Targets: (1) Adoption of core set of metrics against which plan designs may be benchmarked (2) Publication of initial rankings of benefit designs
Year 1 Targets: (1) Adoption of core set of metrics against which plan designs may be benchmarked (2) Publication of initial rankings of benefit designs
Year 1 Targets: (1) Adoption of core set of metrics against which plan designs may be benchmarked (2) Publication of initial rankings of benefit designs
MHMC Objective 3: | bar: 10/1/13-9/30/14 Q1 to 10/1/13-9/30/14 Q2
Identify common metrics across payers for public reporting and alignment with payment – This work relates to the provision of health information to influence markets and inform policy decisions. It figures prominently in efforts around the payment and delivery system reform drivers.
MHMC Objective 4: | bar: 10/1/13-9/30/14 Q1 to 10/1/13-9/30/14 Q2
Provide Primary Care providers access to claims data for their patient panels (portals) | 10/1/13-9/30/14 Q1: Year 1 Target: Complete design of portal and required analytics;.50 practices will adopt the portals in the first year.; 10/1/14-9/30/15 Q1: Year 2 Targets: Deliver portal functionality to all requesting providers. Estimated additional uptake: est. additional 20%, bearing in mind that adoption is voluntary; 10/1/15-9/30/16 Q1: Year 3 Targets: Deliver portal functionality to all requesting providers. Estimated additional uptake: est. additional 20%, bearing in mind that adoption is voluntary
| Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| 10/1/13-9/30/14 |  |  |  | 10/1/14-9/30/15 |  |  |  | 10/1/15-9/30/16
Payment Reform Workstream | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
MHMC Objective 5: | bar: 10/1/13-9/30/14 Q1 to 10/1/13-9/30/14 Q2
Provide practice reports reflecting practice performance on outcomes measures | 10/1/13-9/30/14 Q1: Produce practice reports for all primary care practices indicating their interest in receiving them. While we will be able to produce reports for any primary care practice that serve a critical mass of patients, practices themselves must make the decision to actively request, review and use the reports. PCMH practices represent approximately 25% of primary care practices; all receive the reports. We estimated 10% of non-PCMH practices will choose to receive reports in Year One. Each new practice will receive an outreach visit.
MHMC Objective 6: | bar: 10/1/13-9/30/14 Q1 to 10/1/13-9/30/14 Q2
Consumer engagement and education regarding payment and system delivery reform | 10/1/13-9/30/14 Q1: Go Live Target: Year 1 Target: Educate brokers, patient advocates, HR Specialists, union leaders on merits of VBID. Outreach to 200 people.
Go Live Target: Year 1 Target: Educate brokers, patient advocates, HR Specialists, union leaders on merits of VBID. Outreach to 200 people.
Go Live Target: Year 1 Target: Educate brokers, patient advocates, HR Specialists, union leaders on merits of VBID. Outreach to 200 people.
Delivery System Reform Workstream
MQC Objective 1: | bar: 10/1/13-9/30/14 Q1 to 10/1/13-9/30/14 Q2
Provide learning collaborative for MaineCare Health Homes | 10/1/13-9/30/14 Q1: Launch enrollment of up to 80 new HH practices in PCMH/HH Learning Collaborative to provide QI support for current 75 PCMH & new HH primary care practices, with total of up to 150 participating practices; determine final NCQA status of high risk practices (may not meet participation requirements by 12/31/13).; 10/1/14-9/30/15 Q1: Year 2 Targets: Facilitate Learning Collaborative for HH practices; sustain PCMH/HH Learning Collaborative offering support for 100% of Year 2 participating primary care practices.; 10/1/15-9/30/16 Q1: Year 3 Targets: Sustain PCMH/HH Learning Collaborative offering support for 100% of Year 3 participating practices.
[5 empty] | Year 2 Targets: Facilitate Learning Collaborative for HH practices; sustain PCMH/HH Learning Collaborative offering support for 100% of Year 2 participating primary care practices. |  |  |  | Year 3 Targets: Sustain PCMH/HH Learning Collaborative offering support for 100% of Year 3 participating practices.
[5 empty] | Year 2 Targets: Facilitate Learning Collaborative for HH practices; sustain PCMH/HH Learning Collaborative offering support for 100% of Year 2 participating primary care practices. |  |  |  | Year 3 Targets: Sustain PCMH/HH Learning Collaborative offering support for 100% of Year 3 participating practices.
[5 empty] | Year 2 Targets: Facilitate Learning Collaborative for HH practices; sustain PCMH/HH Learning Collaborative offering support for 100% of Year 2 participating primary care practices. |  |  |  | Year 3 Targets: Sustain PCMH/HH Learning Collaborative offering support for 100% of Year 3 participating practices.
[5 empty] | Year 2 Targets: Facilitate Learning Collaborative for HH practices; sustain PCMH/HH Learning Collaborative offering support for 100% of Year 2 participating primary care practices. |  |  |  | Year 3 Targets: Sustain PCMH/HH Learning Collaborative offering support for 100% of Year 3 participating practices.
MQC Objective 3: | bar: 10/1/13-9/30/14 Q2
Provide QI Support for Behavioral Health Homes Learning Collaborative | 10/1/13-9/30/14 Q1: Year 1 Target: Launch enrollment of up to 35 new BHHs into BHH Learning Collaborative to provide QI support for BHH organizations.; 10/1/14-9/30/15 Q1: Year 2 Targets: Facilitate BHH Learning Collaborative for up to 35 BHHs; sustain BHH Learning Collaborative offering support for 100% of Year 2 participating BHH organizations; 10/1/15-9/30/16 Q1: Year 3 Targets: Sustain BHH Learning Collaborative for up to 35 BHHs; sustain BHH Learning Collaborative offering support for 100% of Year 3 participating BHH organizations
MQC Objective 4: | bar: 10/1/13-9/30/14 Q2
Objective 4: Provide QI Support for Patient-Provider Partnership Pilots (P3 Pilots) | 10/1/13-9/30/14 Q1: Year 1 Target: Launch 3 Patient Provider Partnership (P3) Pilots with 9 provider sites.; 10/1/14-9/30/15 Q1: Year 2 Targets: Support and facilitate learning across 9 provider sites in P3 Pilots; sustain support for 100% of participating provider organizations
| Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| 10/1/13-9/30/14 |  |  |  | 10/1/14-9/30/15 |  |  |  | 10/1/15-9/30/16
MaineCare Workstream | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
MaineCare Objective 1: | bar: 10/1/13-9/30/14 Q1 to 10/1/13-9/30/14 Q2
Implement MaineCare Accountable Communities Shared Savings ACO Initiative | 10/1/13-9/30/14 Q1: Year 1 Target: Implement Accountable Communities that impact 50,000 patient lives above and beyond those impacted through Medical Homes, 3.8% of Maine's 1.3M population. Patients are not limited to MaineCare members attributed under Accountable Communities, since all patients, regardless of attribution status and payer, should be impacted through improved care coordination incented under model. Achieve participation from 6 Accountable Communities, including providers under current Medicare and commercial ACOs within the State (all 4 major health systems plus group of FQHC's). Achieve 25,000 MaineCare lives to Accountable Communities, 8.9% of the 281,000 MaineCare population.; 10/1/14-9/30/15 Q1: Year 2 Targets: Provide all Accountable Communities with monthly utilization reports drilled down to the Primary Care practice level, and quarterly reports on actual TCOC to date and quality benchmark achievement. Achieve participation by all MaineCare Accountable Communities in 90% of bimonthly ACI learning collaborative meetings. Implement Accountable Communities that impact an additional 5,000 patient lives above and beyond those impacted through Medical Homes, reaching 4.2% of Maine's population. Achieve participation from 2 additional Accountable Communities. Achieve attribution of additional 2,700 MaineCare lives to Accountable Communities, 9.8% of the MaineCare population.; 10/1/15-9/30/16 Q1: Year 3 Targets: Provide all Accountable Communities with monthly utilization reports drilled down to the Primary Care practice level, and quarterly reports on actual TCOC to date and quality benchmark achievement. Achieve participation by all MaineCare Accountable Communities in 90% of bimonthly ACI learning collaborative meetings. Implement Accountable Communities that impact an additional 5,500 patient lives above and beyond those impacted through Medical Homes, reaching 4.6% of Maine's population. Achieve participation from 2 additional Accountable Communities. Achieve attribution of additional 2,000 MaineCare lives to Accountable Communities, 10.5% of the MaineCare population.
MaineCare Objective 2: | bar: 10/1/13-9/30/14 Q1 to 10/1/13-9/30/14 Q2
Implement MaineCare Behavioral Health Homes Initiative | 10/1/13-9/30/14 Q1: Year 1 Target: Successfully recruit 15 Behavioral Health Home organizations (BHHOs) with 7000 enrolled members with SMI/ SED. There are 75 Behavioral Health Organizations that currently provide services being transformed through Behavioral Health Homes, and about 24,000 members with SMI/SED.; 10/1/14-9/30/15 Q1: Year 2 Targets: Increase enrolled members to 7700. 3 in-person learning sessions annually, monthly working group, monthly phone and webinar support for 15 BHHOs and partnering practices. There are 75 Behavioral Health Organizations that currently provide services being transformed through Behavioral Health Homes, and about 24,000 members with SMI/SED.; 10/1/15-9/30/16 Q1: Year 3 Targets: Increase enrolled members to 8500 total. 3 in-person learning sessions annually, monthly working group, monthly phone and webinar support for 15 BHHOs and partnering practices. There are 75 Behavioral Health Organizations that currently provide services being transformed through Behavioral Health Homes, and about 24,000 members with SMI/SED.
MaineCare Objective 3: | bar: 10/1/13-9/30/14 Q2
Develop and implement Physical Health Integration workforce development component to Mental Health Rehabilitation Technician/Community (MHRT/C) Certification curriculum.6 | 10/1/13-9/30/14 Q1: Go Live Target: Year 1 Target: Curriculum and training plan developed for Physical Health Integration component to Mental Health Rehabilitation Technician/Community Training; 10/1/14-9/30/15 Q1: Year 2 Targets: 500 direct service behavioral health individual providers trained in physical health integration.; 10/1/15-9/30/16 Q1: Year 3 Targets:
MaineCare Objective 4: | bar: 10/1/13-9/30/14 Q2
Provide training to Primary Care Practices on serving youth and adults with Autism Spectrum Disorder and Intellectual Disabilities.7 | 10/1/13-9/30/14 Q1: Go Live Target: Year 1 Target: Curriculum and training plan developed for Adult Practice Sites Curriculum piloted at 5 Adult Practice Sites Training conducted at 15 pediatric sites There are over 400 primary care practice sites in Maine.; 10/1/14-9/30/15 Q1: Year 2 Targets: Training conducted at 30 pediatric sites Training conducted at 55 adult practice sites There are over 400 primary care practice sites in Maine.; 10/1/15-9/30/16 Q1: Year 3 Targets: Training conducted at 15 pediatric sites Training conducted at 60 adult practice sites There are over 400 primary care practice sites in Maine.
| Year 1 |  |  |  | Year 2 |  |  |  | Year 3
| 10/1/13-9/30/14 |  |  |  | 10/1/14-9/30/15 |  |  |  | 10/1/15-9/30/16
CDC Workstream | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Maine CDC Objective 1: | bar: 10/1/13-9/30/14 Q1 to 10/1/13-9/30/14 Q2
NDPP: Implementation of the National Diabetes Prevention Program (NDPP) | 10/1/13-9/30/14 Q1: Year 1 Target: 5 out of 15 NDPP provider sites have written agreements and are delivering NDPP to MaineCare beneficiaries.; 10/1/14-9/30/15 Q1: Year 2 Targets: 1) Policy developed by MaineCare and Maine CDC to support the sustainable structure for NDPP reimbursement. 2) PCMH/ACO care delivery structures are utilizing pre-diabetes/diabetes algorithm to support/enhance patient care.; 10/1/15-9/30/16 Q1: Year 3 Targets: 1) Over 15 NDPP provider sites have written agreements and are delivering NDPP to MaineCare beneficiaries. Multiple payers are engaged in payment test demonstration linked to program outcomes. 2) 300 out of 29,312 NDPP eligible beneficiaries have completed program over 3 years of SIM Grant.
Maine CDC Objective 2: | bar: 10/1/13-9/30/14 Q1 to 10/1/13-9/30/14 Q2
Community Health Workers Pilot Project | 10/1/13-9/30/14 Q1: Year 1 Target: 1. Contracts for 5 CHW Pilot sites in place. 2. The 5 CHW pilot sites will have formal referral mechanisms with at least one and up to 3 providers.; 10/1/14-9/30/15 Q1: Year 2 Targets: 1. CHW clients identified with a caseload of 15-20 clients for intensive service, and 30-50 clients for less intensive service. 9; 10/1/15-9/30/16 Q1: Year 3 Targets: 1. CHW clients identified with a caseload of 15-20 clients for intensive service, and 30-50 clients for less intensive service.
Go Live Target:
RFP requirements prepared for presentation to DIS.
Year 1 Targets:
20 Behavioral health organizations3 demonstrate live use of EHR and milestone 1 incentive delivered.
Year 2 Targets:
20 organizations have access to the HIE portal and notifications and milestone 2 incentive delivered.
Year 3 Targets:
All 20 organization's participating in e-quality measurement using the data submitted to the HIE and milestone 3 incentive delivered.
Go Live Target:
Provide MaineCare BAA and DUA for AAG review and approval.
Year 1 Targets:
1. Consistent meeting with MaineCare established for MaineCare IT staff to facilitate discrete medication feeds and roles for the dashboard access.
2. DIS approval of data access strategy.
3. Go-Live with real-time medication feeds
4. Establishment of VPNs for MaineCare to access dashboard.
5. Provide training for MaineCare staff in Dashboard use.
6. Make 291,000+ population data available in HIN Dashboard.
Year 2 Targets:
Up to 7 sites go live with bi-directional HIE participation.
Year 3 Targets:
Up to 10 sites go live with bi-directional HIE participation.
Go Live Target:
RFP requirements prepared for presentation to DIS.
Year 1 Targets:
Up to 5 sites go live with bi-directional HIE participation.
Year 2 Targets:
1. Continued provision of Dashboard to MaineCare.
2. Consistent data flow for MaineCare medication information into the HIE.
Year 3 Targets:
1. Continued provision of Dashboard to MaineCare.
2. Consistent data flow for MaineCare medication information into the HIE.
Go Live Target:
As of October 1, 2013, criteria for PHR pilot prepared and finalized for presentation to the DIS in October.
Year 1 targets:
Establishment of contract with pilot site, establish project management process for implementation, implementation of PHR CCD export by month 6. Demonstrated download of CCD by 5%5 of the pilot sites active PHR users w/in go-live period of project.
Year 2 Targets:
Provide support for Subcommittee in manner that supports active participation of membership.
Year 3 Targets:
Provide support for Subcommittee in manner that supports active participation of membership.
Year 2 Targets: Clarify status of Maine enhanced payment for primary care practices, facilitating Learning Collaborative accordingly; Sustain PCMH/HH Learning Collaborative offering support for 100% of Year 2 participating primary care practices; Total combined active (seen in the past 2 years) patients reached with the medical/health home Learning Collaborative includes about 432,000 individuals.
Year 3 Targets: Facilitate the Learning Collaborative offering support for 100% of Year 3 particpating practices; Total combined active (seen in the past 2 years) patients reached with the medical/health home Learning Collaborative approximates 432,000 individuals.
Year 1 Target:
Build claims database that spans Medicare, MaineCare and commercial populations of Maine. This will represent approximately 900k covered lives who are eligible to receive services from Maine's provider community. Providers include all 39 Maine hospitals and all other non-hopsital providers in the state who contract with one or more commercial carriers, Medicare and/or MaineCare. (2) Develop/refine appropriate metrics and approach to measuring and tracking cost of care over time. (3) Publish initial edition of Healthcare Cost Fact Book and convene CEO Roundtable.
Year 2 Targets:
(1) Maintain access to broadbased dataset.
(2) Publish two updated editions of Fact Book.
(3) Convene 2 additional CEO Roundtables, increasing attendance from 20 to 30 opinion leaders.
Year 3 Targets:
(1) Maintain access to broadbased dataset.
(2) Issue two additional updates of Fact book.
(3) Convene two additional CEO Roundtables, increasing attendance from 30 to 50 CEOs.
Go Live Target:
Group will come into Testing Phase ready to work, having established ground rules
Identified candidates for PTE BH workgroup.
Year 1 Target:
Identification of core metrics for reporting, vetted and approved through PTE and Board. Publish initial benchmarked rankings.
Percent of Maine residents covered by alternative payment arrangement grows to 219,982 or 17%.
Identification of core metric set for Behavioral Health (integration and quality)
Identify core metrics for Adv Primary Care Recognition
Year 2 Targets:
Learning collaborative tracking metrics identified not only for public reporting, but a separate set of metrics identified for use in learning.
Number of Maine residents covered by an alternative payment arrangement grows to almost 462k, or 35.5% of population
Finalization of metrics for BH; publish first set of metrics
All metrics updated as appropriate
Year 3 Targets:
Percent of Maine residents covered by alternative payment arrangements grows to 789,936 or 61%. This puts on a trajectory to reach 80% coverage at the end of 5 years from start of test year.
All metrics updated as appropriate
Go Live Target:
October 1, 2013: Notifications available to 1,600 Medicaid Providers & Care Managers across the state.
Year 1 Target:
Increase weekly average from 4502 to 5500 unique provider organization users either accessing the ED notifications or the HIE portal
Year 2 Targets:
1) Increase making notifications available to 1,800 Medicaid Provider and Care Managers/Care Coordinators.
2) Increase to average of 600 unique provider organization users either accessing the ED notifications or the HIE portal per week.
Year 3 Targets:
1) Increase making notifications available to 2,000 Medicaid Provider & Care Managers/Care Coordinators.
2) Increase to an average of 800 unique provider organization users either accessing the ED notifications or the HIE portal per week.
Year 2 Targets:
20 organizations have access to the HIE portal and notifications and milestone 2 incentive delivered.
Year 3 Targets:
All 20 organization's participating in e-quality measurement using the data submitted to the HIE and milestone 3 incentive delivered.
Note on B99: Go Live Target = What are we testing beginning on 10/1/3 Year 1 Target - How will we be expanding that test More information s/b provided for Year 1 versus year 2 or 3
Note on B110: Go Live Target = What are we testing beginning on 10/1/3 Year 1 Target - How will we be expanding that test More information s/b provided for Year 1 versus year 2 or 3
Note on B112: Go Live Target = What are we testing beginning on 10/1/3 Year 1 Target - How will we be expanding that test More information s/b provided for Year 1 versus year 2 or 3