## Attendance
Sign In: SIM Steering Committee Meeting 10A - 12Noon
| 103 COB |  | 103 COB | 103 COB |  | 103 COB | 103 COB | 103 COB | 103 COB | 103 COB | 103 COB | 103 COB | 103 COB
| 2018-01-23 | 2018-02-27 | 2018-03-27 | 2018-05-01 | 2018-05-29 | 2018-06-26 | 2018-07-31 | 2018-08-28 | 2018-09-25 | 2018-10-28 | 2018-11-30 | 2019-01-01
Steering Committee:
Alfreds, Shaun | bar: 2018-01-23
Bliss, Jennifer
Chenard, Randal | bar: 2018-01-23
Cioppa, Eric | bar: 2018-01-23
Comart, Jack | bar: 2018-01-23
Delorenzo, Michael
Duby, Lynn | bar: 2018-01-23
Flanigan, Kevin | bar: 2018-01-23
Fullam-Harris, Katie | bar: 2018-01-23
Hamilton, Dale | bar: 2018-01-23
Jensen, Frances
Letourneau, Lisa | bar: 2018-01-23
Malaby, Rep. Richard
Masse, Stephanie | bar: 2018-01-23
Nadeau, Stefanie
Nesin, Noah
Ossenfort, Kristine
Peterson, Rep. Matthew
Probert, Michelle
Ryder, Rebecca
Selvin, Rhonda | bar: 2018-01-23
Sockabasin, Lisa
Strout, Rose | bar: 2018-01-23
Sylvester, Sara | bar: 2018-01-23
Townsend, Penny
Webber, Andy | bar: 2018-01-23
Wigand, Debra | bar: 2018-01-23
Yoe, Jay | bar: 2018-01-23

## Minutes
Agenda item |  | Discussion Summary | Issues to be Addressed | Responsible Person | Due Date | Follow-up Discussion | Solution/Decision
Welcome, Agenda overview, Consent to agenda items | 12/11 minutes were adopted as is, will be posted.
| Request for formatting with consistent heading for all committees under SIM umbrella. | [5 empty] | SIM branding discussed for all SIM communications and materials.
Payment Reform Update |  | Update was given regarding the subcommittee’s 12/10 ACI meeting | ACI Workgroup will present preliminary recommendations between June and July 2014 and will adopt a system by September. | Frank Johnson | 2014-09-02
Steering Committee Response: |  | A request was made of the coalition that there be an identified group of members of ACI responsible for work around SIM due to concerns regarding overlap committees regarding layers of ACI Committee and SIM Payment Reform. | These groups represent very talented and skilled individuals with skilled depth of understanding. | Randy Chenard |  | Yes | Under SIM governance, there should be a separation of SIM-related work.
Data Infrastructure Update | Data Infrastructure Activities & BH RFP | Communication regarding deliverables is under final review and will go out by email, as well as posted to SIM website | Lengthy conversation regarding how funding amount was decided on. | Katie Sendze |  |  | Allotted amount is based on at least 20 Health Home applicants, though we are anticipating 26 organizations to apply.
Steering Committee Response: |  | Alignment of Legislative actions & SIM Process. Noted: MHDO bill has impact on data infrastructure, and the Managed Care Bill effects payment reform and delivery | Initiatives and bills cannot go against each other |  |  |  | It would behoove SIM as an entity to be cognizant of what is going on in Legislation, and to be prepared for conversations in response to this when it occurs. SIM does not take a stance.
Delivery System Reform | DSR update & notes from Last Subcommittee meeting: 1/8 | Finished recommendations for Health Home learning collaborative for primary care practices, in addition to a learning session on behavioral health home initiative with Kitty Purington |  | Lisa Tuttle |  |  | Recommendation concerning the behavioral initiative and also incorporating learning collaborative
Issue #1 | Patients who are eligible for service under Stage B, but not currently receiving care from a Stage A practice | Lengthy discussion regarding Stage B behavioral health homes and primary care practice partnership. | Concerns about how we will differentiate between who is in the Stage B pilot. | Lisa Tuttle |  |  | This is similar to pilot project thus not all will be enrolled
Issue #2 | Patients living with substance abuse use disorders who fall through the gaps between Stage A and Stage B | Stage A Health Homes have not reserved significant primary and case management of these populations | Risks listed in packet | Lisa Tuttle/ Dr Letorneau |  |  | Review with State expectations and options
Issue #3 | No clear mechaniism to support the additional primary care practices who will come in as a result of the application re-opening, who will be serving Stage A and Stage B patients | There is a larger group of practices in Health Homes than projected and the number is growing. | How will these new Health Homes be supported? | Lisa Tuttle |  |  | Review with State expectations and options
Evaluation | Update on evaluation activities, including an update on the SIM Priority setting work | RFP sent at end of October with 4 bids by November 22, 2014. | Still in process of reviewing contest around award with no timeline | Jay Yoe/ Debra Wigand | n/a |  | Jay will report results to the Steering Committee. Testing performed prior to next SIM Steering Committee Meeting
Steering Committee Response: |  | SIM is charged with developing a higher level criteria and/or guide to focus and inform design of SIM. |  | Jay Yoe
|  | Handouts hilighting SIM Prioritizing Criteria & Workflow | How will criteria be used as items are escalated? | Jay Yoe |  |  | Guideline handout helps early on with a consistent plan | Post Handouts to SIM website
|  |  | How will SIM Steering Committee weigh in? | Jay Yoe |  |  | Proposed: Sub goup refines guide before going forward
CMMI Evaluation Maine Visit | Upcoming CMMI Evaluation visit | CMMI contract with RTI. CMMI will site visit February SIM Steering Committee Meeting, as well as Maine Leadership Team | Looking for interviews with other stakeholders to find who the right people are. | Randy Chenard | 2014-02-26
Steering Committee Response: |  |  | Who is the Lead Investigator? |  |  |  | Two components: Self Evaluation & Federal Implementation Evaluation at various intervals
|  | New SIM website | Randy requested feedback from the SIM Steering Committee |  | 2014-02-26 | 2014-02-26
Between Meeting Memo | Discuss recent trial run of "Between Meeting Memo Process" and obtain Steering Committee approval to amend, cease or continue | Recommended conflict of interest process to foster more of an informed decision-making process. |  | Dr. Flanigan |  |  | Input for evaluation and recommendations- Concensus was very helpful. Follow up: None
SIM Communication Plan and obtain feedback on updated SIM Website | No Comment
Public Comment | None | None