## September 2015
Obj. # | Brief Description | Pillar (s) | Hypotheses | Prior Month's Activity (August 2015) | Current Month's Activities (September 2015) | Next Month's Projection (October 2015)
MaineCare 1 Task 6 | Accountable Community Organizations | 1, 4 | If we implement a payment system where providers may share in savings, with savings payment based also on provider performance on quality measures, we will see reduction in total cost of care, improvement in quality, and improvement in population health. | OMS and Muskie continued working with two ACs to establish monthly claims feeds for the ACs’ analytic platforms. | OMS and Muskie continued working with an AC to establish monthly claims feeds for the AC’s analytic platform. OMS, MHMC, and Muskie had discussions with another AC that is performing its own analysis to cross walk from the quarterly TCOC reports to reports it was generating from its monthly claims feed. | In addition to the analytic reports listed under task MC 10: (1) Deloitte developed the methodology for calculating and reporting total cost of care (TCOC) in annual benchmark and quarterly TCOC reports; MHMC will do the calculations and the reports on an ongoing basis, with initial assistance from Deloitte as necessary. (2) OMS will work with Muskie to develop the AC portal as the mechanism for delivering monthly utilization reports, quarterly quality reports, and claims downloads. (3) OMS and Muskie will also work with ACs that would like to establish monthly claims feeds (separate from the portal) for the ACs’ analytic platforms.
QAT | # of Primary Care Practices Participating in AC's |  |  | 28 out of 30 targeted | 28 out of 30 targeted | target # of 30
MaineCare 2 Task 17 | Behavioral Health Home | 2 | If MaineCare members with serious mental health needs have access to an integrated and value-based model of care for case management and support, then they will have improved outcomes, a better service experience, and reductions in cost. | Enrollment efforts are ongoing. Opt –in packets were completed and mailed out in August.. Currently engaged in rate review. The Department with a consultant presented the proposed new rate to BHH providers and then opened up the website to allow BH providers to provide public comment on the proposed rate. Public comment period will close in September.. Received initial draft rate numbers. | Enrollment efforts are ongoing. Opt –in packets were completed and mailed out in August.. Currently engaged in rate review, the Public Comment period ended mid-September, the Department is making final adjustments and rate should be finalized mid-October. BHH staff currently prepping application and started communication process for opening mid-October. Provider recruitment is underway. | Opt-in packets were sent in August to 12,000 qualifying members. An independent review by Burns and Associates is wrapping up. Finalized rate to be established by mid-October.
QAT | # of Members enrolled in BHHO's |  |  | 2408 out of 2600 targeted | 2408 out of 2600 targeted | Target # of 2600
MaineCare 3 Task 24 | Health Homes | 1, 3 | If MaineCare members with multiple chronic conditions have access to enhanced primary care and care management services when needed, then they will have improved outcomes, a better service experience, and reductions in cost. | Training development is on track | Training development is on track | Implementation of new MHRT/C competency model with section focusing on integrated health set for January 2016. Muskie has begun development of online portal, and identified additional relevant training content for current Health Home Coordinators and others that are part of the BHH team, and those trainings will be accessible through the portal. Exploring licensing DVD’s through Missouri Institute of Mental Health. In addition a large number of electronic resources have been identified and are loaded into the portal. Final design and program decisions re: the portal and LMS are being vetted with OMS. Face to Face training for Motivational Interviewing is in development and will be offered beginning Q2.
QAT | # of Providers trained under new MHRT/C Curriculum |  |  | Trained 0 out of 100 targeted reported this month | Trained 0 out of 100 targeted reported this month | Target # of 100
MDDC Tasks 3, 4, 8 | ID/DD Program | 1 | If Targeted Case Managers and Primary Care Providers are trained have a better understanding of common physical health issues as they relate to specific displays of behaviors in the I/DD population, then it could help reduce unnecessary crisis calls and an increase in preventative health screenings. If the training proves effective, then recommendations for training requirements will be submitted to MaineCare Policy unit. | We continue to conduct training across the State. We are redesigning the TA part of the program with approval. We are looking at an application that individuals could use to manage the healthcare of those with DD. | We continue to conduct training across the State. We are redesigning the TA part of the program with approval. We are looking at an application that individuals could use to manage the healthcare of those with DD. We continue to provide trainings at medical practices. Recently we have been to Kathadin Valley HealthCare in Patten Maine and provided training to 20 PCP via their tele-communications at all of their 5 sites. Additionally we provided training at Martin’s point which involved 4 PCP. | Continue to provide training for case managers, DSPs, Case workers and guardians. Provide TA through the development of tools and applications that can be used by clinicians to better care for individuals with I/DD. In addition to our trainings that were provided at several medical practices we were also at the Maine Medical Association’s annual meeting in Bar Harbor. We provided an exhibitors booth and provided several handouts.
QAT | # of Targeted Case Managers Trained |  |  | Trained 88 out of 20 targeted | Trained 142 out of 20 targeted | Target # of 20
CDC 1 Tasks 3+4 | NDPP | 4, 6 | If the NDPP is integrated into population health management strategies in Maine, we can prevent or delay the progression/onset of type 2 diabetes for those with pre-diabetes or at high risk for diabetes. For those who progress to a diabetes diagnosis, they consume 2.3 times more health care dollars. | October and November 2015 are the next NDPP Lifestyle Coach trainings. Currently 18 out of 19 program in Maine with written agreement with Maine CDC. | September 10th & 11th 2015, 8 new National DPP Lifestyle Coaches were trained and deployed. October 8th-9th and November 3rd-4th 2015 are the next NDPP Lifestyle Coach trainings. Currently 18 out of 20 program in Maine with written agreement with Maine CDC. | Business plan drafts are provide in the provider(s) contract progress reports. Planning with providers to have final business plans submitted by July 2016. CMMC have NDPP Lifestyle Coach trainings plan for March 16-17, June 15-16, and September 21-22, 2016. Task is ongoing for the remainder of the project period. This task will continue post SIM grant. New Written agreements for 2016 will be revised and sent out in December 2015. Due back to Maine CDC by the end of January 2016.
QAT | # of Written NDPP Agreements issued to providers |  |  | 18 out of 15 targeted | 18 out of 15 targeted | Target # of 15
CDC 2 Tasks 10+11 | CHW | 3, 6 | If CHWs are recognized as valued members of the health care system in Maine, they can support improved health outcomes, appropriate utilization of health care services, and increased cost savings related to chronic disease support, cancer screening, and high risk or high consumers of health care services. | Patient/Client-level services are ongoing. CHW Pilot Project technical assistance meeting focused on a high needs client for the case study, resource sharing and troubleshooting on use of new data reports were also discussed. One face to face quarterly data consultation was held. External engagement of stakeholders and allies focused on standardized training and qualifications of CHWs. As reported in July many of these activities will inform recommendations for the Direct Care Workers’ Registry. Meetings focusing on operationalizing this opportunity included CHWI Stakeholder Training Work Group (3 times) and the RHEC CHW national collaborative. | Patient/Client-level services are ongoing. CHW Pilot Project technical assistance meeting focused on use of aggregated process measure data. Two site visits were conducted with a focus on priorities for YR2 of Pilots, technical assistance needs and the JSI evaluation. Sustainability efforts via a workgroup of the Stakeholder Group finalized a draft recommendation on CHW Core Competencies to be used to inform standardized training of CHWs in Maine. In addition, sustainability discussions around future payment models took place with the ME Association of Health Plans and one of the pilot sites. | A new CHW joined DFDR replacing one of the original CHWs/ Am update on the CHW services provided under the SIM project was provided to both the SIM Delivery System Reform subcommittee and the Maine Healthcare Workforce Forum. Year 3 activities will focus on finalization of training and payment recommendations. Continued engagement of partners will also support model spread, and promotion of the CHW workforce. Other September meetings included- New England CHW Coalition, the CCT Steering Committee, and the RHEC CHW Subcommittee.
QAT | Number of Clients served through CHW Pilot |  |  | 243 out of 275 targeted reported this month | 243 out of 275 targeted reported this month | Target # of 275
HIN 1 Task 5 | HIE for MC, care management | 1, 5 | If HIN can release, build, and deliver real-time ADT & document notifications to MaineCare Care Management staff; MaineCare will have increased their data resources and thereby add efficiencies in staff workflows that will improve the desired results related to appropriate member ED/Admissions utilization. | Email notifications are active and continuous between HIN and the Care Management team at MaineCare. Tracy Emerson oversees the project ongoing and is actively working on implementation and workflows with her team. Lean Health Care East has begun to meet with the project team to explore workflow on the MaineCare team. | Email notifications are active and continuous between HIN and the Care Management team at MaineCare. Tracy Emerson oversees the project ongoing and is actively working on implementation and workflows with her team. MC requested that HIN add the members "name" into the subject field of the secure emails to better search and locate documents sent under this project. That was completed in September successfully. | HIN continues to provide the service per contract. HIN is actively working with remaining hospitals to send "Chief Complaint" in addition to diagnosis from the ED to be included in the notifications.
QAT | # of Active Users of the Clinical Portal |  |  | 1136 out of 875 targeted | 1189 out of 875 targeted | Target # of 875
HIN 2 Task 10 | Incentives for E H R | 2 | If BH organizations in Maine have access to funding reimbursements to support Electronic Health Record interoperability improvements and HIE connection, they will choose to invest in their EHR and participate in Maine’s statewide HIE. | There are now 14 organizations that have passed M1 activities and were approved for payment. As of August 31st, $550,000 was approved for payment. The remaining 6 organizations have requested extensions to allow more time for their vendors to complete requested upgrades to enable HIE integrated testing to begin. | There are now 14 organizations that have passed M1 activities and were approved for payment. As of September 30th, $600,000 was approved for payment in this area. There were 6 organizations that previously requested extenstions to allow more time for their vendors to complete requested upgrades to enable HIE integrated testing to begin. Several have begun to move forward with technical work and implementation now that ICD 10 has been upgraded in their systems. | HIN is focused on weekly technical calls with each team and vendor to push deadlines forward in a positive direction for the bidirectional connection. Several orgainzations HIN expected to move forward with data sharing were delayed in September and this will continue into the fall due to challenges with billing and revenue related to the ICD 10 implementation.
QAT | Amount of money for milestones incentives paid out |  |  | Paid out $590,000 out of $700,000 targeted | Paid out $600,000 out of $700,000 targeted | Target # of $700,000
HIN 3 Task 17 | BH connect to HIE | 2 | If reimbursements are available to BH organizations under SIM, BH organizations can move forward with bidirectional connections to the HIE. | Data sharing: 4 organizations are bi-directional and sharing data, 2 are in final production validation phase testing substance abuse blocking scenarios as their final step to go-live approval. Testing timelines depend on staff to take the time for the testing process with HIN's staff. HIN staff are prepared to move forward. | Data sharing: 5 organizations are bi-directional and sharing data, 2 are in final production validation phase testing substance abuse blocking scenarios and new ICD 10 codes as their final step to go-live approval. Testing timelines depend on staff to take the time for the testing process with HIN's staff. HIN staff are prepared to move forward. | One new organization went live with bi-directional connection since August's report. At least two more should follow by the end of the month now that all organizations have upgraded to ICD 10. An extra round of testing for substance abuse data blocking was required due to a vendor upgrade involving this workflow. This set the go live back about 8 weeks. Because we are so close to completeing testing, we still feel this is a yellow status and not Red.
QAT | # of sites connected to HIE for BHH |  |  | 16 out of 11 targeted | 16 out of 11 targeted | Target # of 11
HIN 4 Task 24 | Dashboard | 5 | If HIN has access to MaineCare Claims files, HIN can build an interactive analytical dashboard that presents clinical HIE and claims data to MaineCare, and the HIN Dashboards will be used to support/inform MC policy and program activities addressing utilization and member outcomes. If HIN has access to MaineCare Claims files, HIN will be able to integrate discrete MaineCare prescription data into the Clinical Portal improving medication reconciliation workflows for all HIE users. | A testing work plan was created by Steve Musica and the team and HIN participated in this process and will continue per the work plan. | A testing work plan was created by Steve Musica and the team and HIN participated in this process and will continue per the work plan. | The testing workplan will lead this work as testing and workflows interate. The MaineCare team began testing the tool in September and this will continue through October. Results will be reviewed in November.
HIN 5 Task 33 | Patient Portal | 6 | If HIN creates the technical solution to provide patients with direct access to their state-wide HIE record Continuity of Care Document (CCD) via their local provider's Patient Portal; patients will access their CCD to better engage in their care. | HIN met virtually with EMHS project leadership to present initial survey data. Second email survey was sent out to pilot participants. | HIN analyzed the data collected their surveys and patient advisory committees and drafted a final report and presentation. | HIN has drafted the final report and presentation for the SIM Steering Committee. HIN is awaiting for a date to present its findings in November as planned with Randy.
QC 1 Task 3 | LC for HH | 1, 2, 3, 4 | Primary care practices participating in the MaineCare Health Homes (HH) initiative and the HH Learning Collaborative will successfully implement the PCMH/HH 10 Core Expectations and HH required screenings, resulting in improvements in clinical quality, integrated care, and patient experience, and decreasing avoidable health care spending for individuals with chronic conditions. | The August 26 webinars were convened as planned, with content posted to our QC HH Learning Collaborative webpage. This webinar series brought together Health Home practice teams to discuss the role of Community Care Teams (CCTs) in working with practice teams to help improve the health of 'super utilizer' patients with complex conditions and reduce readmissions. We explored sustainability of the HH initiative as the enhanced primary care model through the SIM Governance and through our multi-stakeholder work on advancing primary care payment reform. | The September 23 webinars were convened as planned, with content posted to our QC HH Learning Collaborative webpage. This webinar series brought together Health Home practice teams, Behavioral Health Home teams, and Community Care Teams to discuss challenges and best practices in improving care transitions and reducing readmissions. This webinar series was used also as a platform for pre-work and team preparation for the October 2 Learning Session. | We will continue to focus specifically on completing the final project planning details for the October 2 Learning Session that will bring together Health Homes, CCTs, BHHOs, acute care hospital teams, and patient/consumer partners to focus on strengthening collaborative work to reduce re-admissions and improve care transitions. We are also continuing to finalize project planning efforts on the Fall Regional Forums which will bring Health Homes and their medical neighborhood partners together to explore the role of primary care teams in improving palliative care and quality of life.
QAT | # of Active Participating HH Single payer practices supported by Learning Collaboratives |  |  | 111 out of 114 targeted | 109 out of 114 targeted | Target # of 114
QC 3 Tasks 15, 19 | LC for BHH | 2, 3 | If BHHO teams receive QI support through the BHH Learning Collaborative, they will be successful in fulling the 10 BHH Core Expectations, resulting in improvements in integrated care, improved physical and behavioral health outcomes, increased communication between health care providers, greater use of preventive services, community supports, and self-management tools for adults with Serious Mental Illness and children with Serious Emotional Disturbance. | Catholic Charities agreed to share their experiences scheduling and hosting consumer forums at the September 21st BHH Working Group. In additional, OHI agreed to participate in QC BH Committee to facilitate a discussion of what BH information is most relevant to share in the HIE. The August 11th BHH Webinar discussed efforts toward integrated Behavioral Health and Primary Care by two highlighted Maine BHHO sites, Penobscot Community Health Center and Tri-County Mental Health Services, in an AHRQ Report. BHH LC team worked closely with the CCT project manager in designing a presentation for BHH, CCTs, and Health Home providers | On September 21st, Quality Counts hosted the QC BH Committee and supported BHH Working Group meetings. The QC BH Committee provided time for discussion on the inclusion of BH information on the Health Information Exchange, led by OHI (a BHHO and a participant in HIN's BH initiative). The BHH Working Group meeting provided highlights from Catholic Charities, a BHHO, on their work to meaningfully involve consumers in providing feedback on BHH services. On September 23rd the BHH and HH Learning Collaboratives hosted a combined webinar focused on kicking off a strengthened content focus of reducing admissions and readmissions. Also in September, the BHH LC hosted 3 regional BHH Nurse Care Manager meetings, in order foster the collaboration and peer learning among nurse care managers on BHHO teams. | In October, the BHH LC team will work with the QC BH Committee Chair and MaineCare's BHH team to organize and plan content and focus for the November 16th meetings. The next months webinars (October, November, December), will highlight the opportunities and strategies Behavioral Health Home Organizations can pursue to reduce admissions to the emergency room, and subsequently readmissions.
QAT | % of BHHO's supported by BHH Learning Collaboratives |  |  | 0% out of 100% targeted reported this month | 100% out of 100% targeted reported this month | Target % is 100%
MHMC l Tasks 7+8 | Track health care costs | 5 | Hypothesis One: That a robust data and analytics function helps stimulate better informed decisions regarding quality improvement, patient experience of care and payment reform, as well as strategies to address cost of care. | In August, the Coalition processed statewide commercial claims. Data staff is QC’ing preliminary data extract for review and data decisions. | Q12015 data processed by HDMS and sent to quality control. Staff began the initial review of Medicare data and began discussions about how to use the data in practice reports. | Staff will perform quality control and release Q12015 extracts. In October, the data team will perform further quality control on the data and make decisions on implementation business rules. The status for this item is one of timing, not inability to complete. Data is being reviewed and implementation is underway.
MHMC l Task 14 | Track health care costs | 5 | Hypothesis Two: By providing information and data regarding the health care environment to a broad audience, including those who make purchasing decisions for groups of employees, they are better prepared to make informed coverage decisions. | August activities included securing of a host and venue (Bowdoin College) for next summit, as well as identification of other potential sponsors and speakers and development of initial meeting agenda. | September activities included working with host (Bowdoin College) on potential dates for Mid Coast Summit, which is now scheduled for January. | October activities will include continued preparation for next summit. Activities include finalization of date, exploring additional co-sponsors, and further development of agenda.
MHMC l Tasks 12+12.3 | Track health care costs | 5 | Hypothesis Three: Through the use of a consensus-based process involving informed stakeholders, sound guidance regarding strategies to address health care costs may be developed to guide purchasing and policy decisions and that guidance will be adopted by decision makers. | The Healthcare Cost Workgroup met on August 20, at which time it made a recommendation on a set of principles and criteria that could be used—on a voluntary basis—to evaluate infrastructure realignment proposals. The recommendation was later approved by the Payment Reform Subcommittee and will next be brought before the MHMC board, as the workgroup recommended the Coalition as the organization to conduct reviews. If the recommendation is accepted by the MHMC board, it will then be presented to the SIM Steering Committee. The group also reached agreement on a scope of work for an inventory of health resources in Maine. After hearing about an emerging MeHAF effort on health infrastructure in Maine, the workgroup agreed that Coalition staff should work with MeHAF to see how much of the scope of work can be accomplished through the MeHAF effort. | The Behavioral Healthcare Cost Workgroup met on September 16, at which time it reviewed and provided feedback on Data Department analyses that the workgroup had requested at its last meeting regarding utilization and cost patterns. The workgroup discussed how the data should be expanded and refined in order to help clinicians better understand patient utilization and cost, and asked for a series of additional analyses to be conducted for the group’s next meeting. | October activities will include a Healthcare Cost Workgroup meeting on October 22 and a meeting of the Subcommittee of Multi-stakeholder strategies (originally scheduled for 10/14, but being rescheduled due to participant scheduling conflicts). The Healthcare Cost Workgroup will turn to a review of consumer engagement strategies that could improve affordability. That work will be assisted by a framework of consumer engagement strategies that includes potential cost impacts. The Subcommittee on Multi-stakeholder Strategies hopes to finalize its recommendations and prepare to report back to the Healthcare Cost Workgroup. Data Department will also begin work on requests from Behavioral Healthcare Cost Workgroup in preparation for a November meeting of that group.
MHMC 2 Task 18 | VBID | 4 | Hypothesis One: The development of a baseline value based benefit design that appropriately balances cost of care and value of services will speed adoption and use of such coverage in Maine. When adopted, this type of coverage will lead to improved patient outcomes and experience of care, as well as more appropriate costs of care. | Administrative Simplification (participants from all major health plans, practices, and purchasers) recommended a standardized provider enrollment application using the Health Care Administrative Solutions (HCAS) application as a template. This group also agreed, by consensus, to create a web-based provider enrollment guide intended to house in one place credentialing and enrollment information specific to each health plan with links to their websites. | There were no workgroup sessions planned for September. Throughout the month, recommendations of the workgroups have been in development. Where workgroup feedback and participant comments on documents are necessary to progress, email was used to communicate among the groups. Tasks pursued through September: New Provider Enrollment application, tip sheet, and summary guide are being finalized with health plan review, while internal staff at the Coalition determines the most appropriate web-based location for it. The Clinical workgroup is continuing to review services for appropriate exclusion under the VBID model. | The Administrative Simplification team is scheduled to meet on October 13, the Wellness workgroup will meet on October 9, and the Clinical workgroup will meet on October 15.
MHMC 3 Task 39 | Public report for QI and payment reform | 3, 4, 5 | Hypothesis One: The identification and adoption of a set of core metrics for ACOs will allow for benchmarking performance across plans and more informed purchasing decisions on the part of purchasers, as well as decreasing pressure on providers (in terms of reporting burdens). | The measure set for ACO payment has been recommended and endorsed by stakeholders. A total of 27 measures for payment and 17 measures for monitoring performance have been adopted. A subset of measures has been forwarded to PTE for consideration for public reporting. | Task Completed | Task Completed
MHMC 3 Task 40 | Public report for QI and payment reform | 3, 4, 5 | Hypothesis Two: Investment in a stakeholder based process to support development of alternative payment arrangements - including ACOs - will lead to an increased uptake/spread of these arrangements in the Maine marketplace, furthering our objective of moving further away from paying on the basis of volume to a greater emphasis on value. | The Workgroup will periodically identify/confirm the use of core measures by contracting parties to ACO agreements. Current data indicates between 62-72% of risk contract measures are from the core measure set. | The Workgroup will periodically identify/confirm the use of core measures by contracting parties to ACO agreements. Current data indicates between 62-72% of risk contract measures are from the core measure set. | A biannual report will document the group’s progress on this task. Work on this report will continue into October.
QAT | # of Maine Residents covered by Alternative Payment Arrangements |  |  | 328,200 out of 455,000 targeted reported on this month (72%) | 328,200 out of 455,000 targeted reported on this month (72%) | Target # of 455,000
MHMC 3 Task 32 | Public report for QI and payment reform | 3, 4, 5 | Hypothesis Three: The development and public reporting of quality measures for behavioral health will serve to introduce more public accountability in behavioral health care and will provide consumers with information that will assist them in assessing where they might seek care. | Staff collected and prepared data for Oct 1 web update, including the data to report Total Cost of Care for practice groups. | Staff collected and prepared data for Oct 1 web update, including the data to report Total Cost of Care for practice groups. | Launch data for Oct 1 web update, including the data to report Total Cost of Care for practice groups.
MHMC 3 Task 40.6 | Public report for QI and payment reform | 3, 4, 5 | Hypothesis Four: The advancement of public reporting on an advanced primary care recognition will further the promote quality improvement in primary care. | Content and scheduling of learning sessions will commence upon completion of health systems and health plan interviews and reporting of findings. The ACI Steering Committee, SIM Payment Reform Subcommittee, and the Delivery System Subcommittee will be consulted on primary care payment models that may be appropriate for the Maine market and which may generate stakeholder support. Outreach continues with Catalyst of Payment Reform (CPR) and the Health Care Transformation Task Force to present findings on key components for ACO contracts. | Content and scheduling of learning sessions will commence upon completion of health systems and health plan interviews and reporting of findings. The ACI Steering Committee, SIM Payment Reform Subcommittee, and the Delivery System Subcommittee will be consulted on primary care payment models that may be appropriate for the Maine market and which may generate stakeholder support. Outreach continues with Catalyst of Payment Reform (CPR) and the Health Care Transformation Task Force to present findings on key components for ACO contracts. | October activities will continue contingent on feedback from stakeholders. Basic questions on primary care payment reform in current ACO environment remains a central issue for discussion.
MHMC 4 Tasks 58+59 | PCP access to provider portals | 1 | Hypothesis One: By facilitating access to claims data for their patient panels, providers will have access to a potentially powerful tool to help them understand how their patients are accessing services. | Ongoing discussion for AC portal mechanics and attribution data needs. Continue re-send of previous practice reports as requests are made and new contacts identified | Ongoing discussion for AC portal mechanics and attribution data needs. No portals rolled out this month. | Staff will continue to provide support for AC data in portals. Activity on this task is TBD. The Coalition will continue to engage in ongoing discussions with state regarding revised scope for this objective.
MHMC 5 Task 62.2 | Practice reports | 1, 4 | Hypothesis One: By providing practices with practice-specific reports on patient panels (by payer source), providers and practice owners will gain a better appreciation for the trends in utilization, cost and quality demonstrated by their own practice as compared to a statewide benchmark, leading to efforts to improve their own performance. | Commercial reports will be released in Y2 Q4. | Commercial reports will be released in Y2 Q4. (This is Y2, Q4.) | Staff anticipates the release of commercial reports in September or October of 2015.
MHMC 6 Task 64 | Consumer engagement | 6 | Hypothesis One: By engaging the public around issues related to payment reform (with this term being taken broadly), cost and quality, we will have more informed consumers and decision makers who will be able to make better decisions regarding their own health and care, as well as participate in broader discussions of health policy. | Mainebiz published two articles pertinent to the Coalition’s value-based insurance design work: Quality Ratings for Maine's Hospitals with distribution to: 8,814 and Stakeholders Tackle Big Health Care Challenges with distribution to 8,814. | Reporters have been contacted to save the date for our annual symposium in November. No stories were published but staff continues to seek opportunities to speak with journalists/reporters about newsworthy events and information pertaining to payment reform. We are also exploring the potential for a book club focused on overuse of medical services. 16,000 participated in a previous book club held in Maine (non-SIM related), and staff anticipate this would produce the same result to significantly raise awareness of healthcare challenges in this state and what we all can do to address them | Staff will reach out to reporters to personally invite them to the symposium. The book club will continue to be developed and staff will continue to pursue opportunities to speak with others to identify media opportunities for BID/payment reform.
QAT | # of People participating in payment reform education |  |  | 0 out of 400 targeted reported this month | 0 out of 400 targeted reported this month | Target # of 400
Legend | Pillars |  | 1. Strengthen Primary Care 2. Integrate Physical and Behavioral Health 3. Develop New Workforce Models 4. Develop New Payment Models 5. Centralize Data and Analysis 6. Engage People and Communities
Quarterly Accountability Color code |  |  | Green 90% to 100% | Yellow 75% to 89% | Red 0% to 74%
Projection Color Codes |  |  | Green (75% - 100% confident) | Yellow (50 – 75% confident) | Red (<50% confident)

## August 2015
Obj. # | Brief Description | Pillar (s) | Hypotheses | Prior Month's Activity (July 2015) | Current Month's Activities (August 2015) | Next Month's Projection (September 2015)
MaineCare 1 Task 6 | Accountable Community Organizations | 1, 4 | If we implement a payment system where providers may share in savings, with savings payment based also on provider performance on quality measures, we will see reduction in total cost of care, improvement in quality, and improvement in population health. | OMS and Muskie continued discussions with two ACs to establish monthly claims feeds for the ACs’ analytic platforms. The Department delivered four reports to each AC: monthly dashboard utilization reports, quarterly quality and cost reports, and year 2 preliminary benchmarks reports | OMS and Muskie continued working with two ACs to establish monthly claims feeds for the ACs’ analytic platforms. | In addition to the analytic reports listed under task MC 10: (1) Deloitte developed the methodology for calculating and reporting total cost of care (TCOC) in annual benchmark and quarterly TCOC reports; MHMC will do the calculations and the reports on an ongoing basis, with initial assistance from Deloitte as necessary. (2) OMS will work with Muskie to develop the AC portal as the mechanism for delivering monthly utilization reports, quarterly quality reports, and claims downloads. (3) OMS and Muskie will also work with ACs that would like to establish monthly claims feeds (separate from the portal) for the ACs’ analytic platforms.
QAT | # of Primary Care Practices Participating in AC's |  |  | 28 out of 30 targeted | 28 out of 30 targeted | target # of 30
MaineCare 2 Task 17 | Behavioral Health Home | 2 | If MaineCare members with serious mental health needs have access to an integrated and value-based model of care for case management and support, then they will have improved outcomes, a better service experience, and reductions in cost. | Behavioral Health Homes - initial auto-enrollment completed; enrollment efforts ongoing. Opt –in packet completed. Currently engaged in rate review. | Enrollment efforts are ongoing. Opt –in packets were completed and mailed out in August.. Currently engaged in rate review. The Department with a consultant presented the proposed new rate to BHH providers and then opened up the website to allow BH providers to provide public comment on the proposed rate. Public comment period will close in September.. Received initial draft rate numbers. | Created success stories. Cost data was sent to contractor. An independent review by Burns and Associates is wrapping up. Finalized rate to be established by the end of September.
QAT | # of Members enrolled in BHHO's |  |  | 2325 out of 2600 targeted | 2408 out of 2600 targeted | Target # of 2600
MaineCare 3 Task 24 | Health Homes | 1, 3 | If MaineCare members with multiple chronic conditions have access to enhanced primary care and care management services when needed, then they will have improved outcomes, a better service experience, and reductions in cost. | Muskie has begun development of online portal, and identified additional relevant trainings for current Health Home Coordinators and others that are part of the BHH team, and those trainings will be accessible through the portal | Training development is on track | Implementation of new MHRT/C curriculum with section focusing on integrated health set for January 2016. Muskie has begun development of online portal, and identified additional relevant trainings for current Health Home Coordinators and others that are part of the BHH team, and those trainings will be accessible through the portal That should also go live in January, 2016.
QAT | # of Providers trained under new MHRT/C Curriculum |  |  | Trained 0 out of 100 targeted | Trained 0 out of 100 targeted reported this month | Target # of 100
MDDC Tasks 3, 4, 7 | ID/DD Program | 1 | If Targeted Case Managers and Primary Care Providers are trained have a better understanding of common physical health issues as they relate to specific displays of behaviors in the I/DD population, then it could help reduce unnecessary crisis calls and an increase in preventative health screenings. If the training proves effective, then recommendations for training requirements will be submitted to MaineCare Policy unit. | Targeted Case Manager training continues across the State with 2 trainings and 34 participants in July. We are looking at an application that individuals could use to manage the healthcare of those with DD. We are currently looking at the CMS chronic care code to be used for patients with DD. If medical providers used this code they could dedicate a nurse to the management of patient’s with DD. Improving their quality of care. | We continue to conduct training across the State. We are redesigning the TA part of the program with approval. We are looking at an application that individuals could use to manage the healthcare of those with DD. | Provide training for case managers, DSPs, Case workers and guardians. Provide TA through the development of tools and applications that can be used by clinicians to better care for individuals with I/DD. We are looking at ways that medical practices can improve the quality of care they are providing patient with DD.
QAT | # of Targeted Case Managers Trained |  |  | Trained 34 out of 20 targeted | Trained 88 out of 20 targeted | Target # of 20
CDC 1 Tasks 3+4 | NDPP | 4, 6 | If the NDPP is integrated into population health management strategies in Maine, we can prevent or delay the progression/onset of type 2 diabetes for those with pre-diabetes or at high risk for diabetes. For those who progress to a diabetes diagnosis, they consume 2.3 times more health care dolars. | CMMC led a National DPP Lifestyle Coach training, and 10 new Lifestyle Coaches were trained and deployed. The NDPP program still has 16 written agreements in place. It’s important to note that these agreements are not exclusive to delivering the program to MaineCare beneficiaries. | October and November 2015 are the next NDPP Lifestyle Coach trainings. Currently 18 out of 19 program in Maine with written agreement with Maine CDC. | Business plan drafts are provide in the provider(s) contract progress reports. Planning with providers to have final business plans submitted by July 2016. Task is ongoing for the remainder of the project period. This task will continue post SIM grant.
QAT | # of Written NDPP Agreements issued to providers |  |  | 16 out of 15 targeted | 18 out of 15 targeted | Target # of 15
CDC 2 Tasks 10+11 | CHW | 3, 6 | If CHWs are recognized as valued members of the health care system in Maine, they can support improved health outcomes, appropriate utilization of health care services, and increased cost savings related to chronic disease support, cancer screening, and high risk or high consumers of health care services. | Client identification, referral and patient-level services are ongoing. Customized data reporting grids were developed and distributed (in consultation with JSI evaluation) to all of the pilot projects to streamline data collection on CHW services. External engagement of stakeholders and allies focused on the establishment of a voluntary registry as a result of legislation passed during this past session. | Patient/Client-level services are ongoing. CHW Pilot Project technical assistance meeting focused on a high needs client for the case study, resource sharing and troubleshooting on use of new data reports were also discussed. One face to face quarterly data consultation was held. External engagement of stakeholders and allies focused on standardized training and qualifications of CHWs. As reported in July many of these activities will inform recommendations for the Direct Care Workers’ Registry. Meetings focusing on operationalizing this opportunity included CHWI Stakeholder Training Work Group (3 times) and the RHEC CHW national collaborative. | Two of the projects have expanded the scope of their services, in terms of geography for one and additional programmatic measure for another that is focused on chronic disease management. Year 3 activities will focus on finalization of training and payment recommendations. August meetings included- Aetna, partners with the New England Public Health Training Center and the Madison (WI) Health Department.
QAT | Number of Clients served through CHW Pilot |  |  | 0 out of 275 targeted reported this month | 243 out of 275 targeted reported this month | Target # of 275
HIN 1 Task 5 | HIE for MC, care management | 1, 5 | If HIN can release, build, and deliver real-time ADT & document notifications to MaineCare Care Management staff; MaineCare will have increased their data resources and thereby add efficiencies in staff workflows that will improve the desired results related to appropriate member ED/Admissions utilization. | Lean Health Care East has begun to meet with the project team to explore workflow on the MaineCare team. HIN responded to feedback regarding the timliness of discharge documents as well as formatting items for the documents. | Email notifications are active and continuous between HIN and the Care Management team at MaineCare. Tracy Emerson oversees the project ongoing and is actively working on implementation and workflows with her team. Lean Health Care East has begun to meet with the project team to explore workflow on the MaineCare team. | HIN continues to provide the service per contract. HIN is actively working with remaining hospitals to send "Chief Complaint" in addition to diagnosis from the ED to be included in the notifications. HIN responded to feedback regarding missing data and comments from Tracy's team. We have participated in the new meetings with Steve Musica the Lean consultant to learn about how the workflows and staff feedback can continue to grow the impact of this project
QAT | # of Active Users of the Clinical Portal |  |  | 1103 out of 875 targeted | 1136 out of 875 targeted | Target # of 875
HIN 2 Task 10 | Incentives for E H R | 2 | If BH organizations in Maine have access to funding reimbursements to support Electronic Health Record interoperability improvements and HIE connection, they will choose to invest in their EHR and participate in Maine’s statewide HIE. | There are now 14 organizations that have passed M1 activities and were approved for payment. The remaining 6 organizations requested extensions to allow more time for their vendors to complete requested upgrades to enable HIE integrated testing to begin. | There are now 14 organizations that have passed M1 activities and were approved for payment. As of August 31st, $550,000 was approved for payment. The remaining 6 organizations have requested extenstions to allow more time for their vendors to complete requested upgrades to enable HIE integrated testing to begin. | HIN is focused on weekly technical calls with each team and vendor to push deadlines forward in a positive direction for the bidirectional connection. HIN expects several vendors to complete technical work by the end of 9/30 moving several delayed organizations forward.
QAT | Amount of money for milestones incentives paid out |  |  | Paid out $550,000 out of $700,000 targeted | Paid out $590,000 out of $700,000 targeted | Target # of $700,000
HIN 3 Task 17 | BH connect to HIE | 2 | If reimbursements are available to BH organizations under SIM, BH organizations can move forward with bidirectional connections to the HIE. | Data sharing with Behavioral Health Organizations: 3 organizations are bi-directional and sharing data, 3 are in final production validation phase testing substance abuse blocking scenarios as their final step to go-live approval. | Data sharing: 4 organizations are bi-directional and sharing data, 2 are in final production validation phase testing substance abuse blocking scenarios as their final step to go-live approval. Testing timelines depend on staff to take the time for the testing process with HIN's staff. HIN staff are prepared to move forward. | One new organization went live with bi-directional connection. At least two more should follow by the end of the month. An extra round of testing for substance abuse data blocking was required due to a vendor upgrade involving this workflow. This set the go live back about 8 weeks. Because we are so close to completeing testing, we still feel this is a yellow status and not Red. The transition to ICD10 delayed the majority of teams from testing data flow. This may continue into October.
QAT | # of sites connected to HIE for BHH |  |  | 15 out of 11 targeted | 16 out of 11 targeted | Target # of 11
HIN 4 Task 24 | Dashboard | 5 | If HIN has access to MaineCare Claims files, HIN can build an interactive analytical dashboard that presents clinical HIE and claims data to MaineCare, and the HIN Dashboards will be used to support/inform MC policy and program activities addressing utilization and member outcomes. If HIN has access to MaineCare Claims files, HIN will be able to integrate discrete MaineCare prescription data into the Clinical Portal improving medication reconciliation workflows for all HIE users. | MaineCare Staff received training sessions regarding the Clinical Dashboard. | A testing work plan was created by Steve Musica and the team and HIN participated in this process and will continue per the work plan. | The testing workplan will lead this work thru testing and new workflows are established.
HIN 5 Task 33 | Patient Portal | 6 | If HIN creates the technical solution to provide patients with direct access to their state-wide HIE record Continuity of Care Document (CCD) via their local provider's Patient Portal; patients will access their CCD to better engage in their care. | HIN met with EMHS in July to finalize the last email feedback survey to be used to collect data for future implementation. | HIN met virtually with EMHS project leadership to present initial survey data. Second email survey was sent out to pilot participants. | Survey will stay open until mid-September. HIN staff members are working on final paper and presentation to be presented to EMHS leadership and SIM Steering Committee in November.
QC 1 Task 3 | LC for HH | 1, 2, 3, 4 | Primary care practices participating in the MaineCare Health Homes (HH) initiative and the HH Learning Collaborative will successfully implement the PCMH/HH 10 Core Expectations and HH required screenings, resulting in improvements in clinical quality, integrated care, and patient experience, and decreasing avoidable health care spending for individuals with chronic conditions. | The July webinars as part of the SIM Learning Collaborative were convened bringing together Health Home practice teams to highlight strategies and best practices for decreasing admissions and readmissions. | The August 26 webinars were convened as planned, with content posted to our QC HH Learning Collaborative webpage. This webinar series brought together Health Home practice teams to discuss the role of Community Care Teams (CCTs) in working with practice teams to help improve the health of 'superutilizer' patients with complex conditions and reduce readmissions.We explored sustainability of the HH initiative as the enhanced primary care model thorugh the SIM Governance and through our multi-stakeholder work on advancing primary care payment reform. | Continuing to focus specifically on project planning for the October 2 Learning Session that will bring together Health Homes, CCTs, BHHOs, acute care hospital teams, and patient/ consumer partners to focus on strengthening collaborative work to reduce re-admissions and improve care transitions. We are also continuing to focus project planning efforts on the Fall Regional Forums which will bring Health Homes and their medical neighborhood partners together to explore the role of primary care teams in improving palliative care and quality of life.
QAT | # of Active Participating HH Single payer practics supported by Learning Collaboratives |  |  | 117 out of 114 targeted | 111 out of 114 targeted | Target # of 114
QC 3 Tasks 15, 19 | LC for BHH | 2, 3 | If BHHO teams receive QI support through the BHH Learning Collaborative, they will be successful in fulling the 10 BHH Core Expectations, resulting in improvements in integrated care, improved physical and behavioral health outcomes, increased communication between health care providers, greater use of preventive services, community supports, and self-management tools for adults with Serious Mental Illess and children with Serious Emotional Disturbance. | In July, the BHH Beacon e-newsletter was distributed to nearly 300 individuals on 7/29/2015. | Catholic Charities agreed to share their experiences scheduling and hosting consumer forums at the September 21st BHH Working Group. In additional, OHI agreed to participate in QC BH Committee to facilitate a discussion of what BH information is most relevant to share in the HIE. The August 11th BHH Webinar discussed efforts toward integrated Behavioral Health and Primary Care by two highlighted Maine BHHO sites, Penobscot Community Health Center and Tri-County Mental Health Services, in an AHRQ Report. BHH LC team worked closely with the CCT project manager in designing a presentation for BHH, CCTs, and Health Home providers | In September, the Quality Counts will host the QC BH Committee and support the MaineCare BHH Working Group on September 21st. On September 23rd the BHH and HH Learning Collaboratives will host a combined webinar focused on kicking off the strengthened focus on reducing admissions and readmissions. Also in September, the BHH LC will host 3 regional Nurse Care Manager meetings, in order foster the collaboration and peer learning among nurse care managers on BHHO teams.
QAT | % of BHHO's supported by BHH Learning Collaboratives |  |  | 100% out of 100% targeted | 0% out of 100% targeted reported this month | Target % is 100%
MHMC l Tasks 7+8 | Track health care costs | 5 | Hypothesis One: That a robust data and analytics function helps stimulate better informed decisions regarding quality improvement, patient experience of care and payment reform, as well as strategies to address cost of care. | Q12015 data was received with run out data for 2014. The attribution for this data was run successfully. | In August, the Coalition processed statewide commercial claims. Data staff is QC’ing preliminary data extract for review and data decisions. | CY2014 data was from HDMS will be sent to the Coalition in September. Staff will use data to rebuild the warehouse to support practice reports. Analysis and review of Medicare will begin in September. Staff will revise attribution methodology as needed and prepare for implementation of revised business rules.
MHMC l Task 14 | Track health care costs | 5 | Hypothesis Two: By providing information and data regarding the health care environment to a broad audience, including those who make purchasing decisions for groups of employees, they are better prepared to make informed coverage decisions. | CEO Summit took place with 32 participants in attendance. (Purchasers: 44%; plans/brokers: 25%; providers: 22%; other: 9%) | August activities included securing of a host and venue (Bowdoin College) for next summit, as well as identification of other potential sponsors and speakers and development of initial meeting agenda. | September activities will include continued preparation for next summit, which—due to availability of host Bowdoin College—is expected to occur in early January. Activities will include finalization of date, exploring additional co-sponsors, and further development of agenda.
MHMC l Tasks 12+12.3 | Track health care costs | 5 | Hypothesis Three: Through the use of a consensus-based process involving informed stakeholders, sound guidance regarding strategies to address health care costs may be developed to guide purchasing and policy decisions and that guidance will be adopted by decision makers. | The Healthcare Cost Workgroup reached preliminary agreement on a set of principles and criteria that could be used to evaluate infrastructure realignment proposals. | The Healthcare Cost Workgroup met on August 20, at which time it made a recommendation on a set of principles and criteria that could be used—on a voluntary basis—to evaluate infrastructure realignment proposals. The recommendation was later approved by the Payment Reform Subcommittee and will next be brought before the MHMC board, as the workgroup recommended the Coalition as the organization to conduct reviews. If the recommendation is accepted by the MHMC board, it will then be presented to the SIM Steering Committee. The group also reached agreement on a scope of work for an inventory of health resources in Maine. After hearing about an emerging MeHAF effort on health infrastructure in Maine, the workgroup agreed that Coalition staff should work with MeHAF to see how much of the scope of work can be accomplished through the MeHAF effort. | September activities will include a Behavioral Healthcare Cost Workgroup meeting on September 16, as well as preparation for the October 22 Healthcare Cost Workgroup meeting and the October meeting of the Subcommittee of Multi-stakeholder strategies (date TBD). The Behavioral Healthcare Cost Workgroup will review Data Department analyses that the group requested at its last meeting regarding utilization and cost patterns. The Healthcare Cost Workgroup will turn to a review of consumer engagement strategies that could improve affordability. That work will be assisted by a framework of consumer engagement strategies that includes potential cost impacts. September preparation for the Subcommittee on Multi-stakeholder Strategies includes identification of sample strategies to include with each preliminary recommendation.
MHMC 2 Task 18.1 | VBID | 4 | Hypothesis One: The development of a baseline value based benefit design that appropriately balances cost of care and value of services will speed adoption and use of such coverage in Maine. When adopted, this type of coverage will lead to improved patient outcomes and experience of care, as well as more appropriate costs of care. | Administrative Simplification recommended a standardized provider enrollment application using the HCAS application as a template. This group also agreed, by consensus, to create a web-based provider enrollment guide intended to house credentialing and enrollment information specific to each health plan with links to their websites in one place. | Administrative Simplification (participants from all major health plans, practices, and purchasers) recommended a standardized provider enrollment application using the Health Care Administrative Solutions (HCAS) application as a template. This group also agreed, by consensus, to create a web-based provider enrollment guide intended to house in one place credentialing and enrollment information specific to each health plan with links to their websites. | Identify/develop an appropriate website to house the enrollment application and enrollment guide with the assistance of providers and health plans to ensure the technology meets the needs of those using it.
MHMC 3 Task 39 | Public report for QI and payment reform | 3, 4, 5 | Hypothesis One: The identification and adoption of a set of core metrics for ACOs will allow for benchmarking performance across plans and more informed purchasing decisions on the part of purchasers, as well as decreasing pressure on providers (in terms of reporting burdens). | The measure set for ACO payment has been recommended and endorsed by stakeholders. A total of 27 measures for payment and 17 measures for monitoring performance have been adopted. | The measure set for ACO payment has been recommended and endorsed by stakeholders. A total of 27 measures for payment and 17 measures for monitoring performance have been adopted. A subset of measures has been forwarded to PTE for consideration for public reporting. | Task Completed
MHMC 3 Task 40 | Public report for QI and payment reform | 3, 4, 5 | Hypothesis Two: Investment in a stakeholder based process to support development of alternative payment arrangements - including ACOs - will lead to an increased uptake/spread of these arrangements in the Maine marketplace, furthering our objective of moving further away from paying on the basis of volume to a greater emphasis on value. | The Workgroup will periodically identify/confirm the use of core measures by contracting parties to ACO agreements. Current data indicates between 62-72% of risk contract measures are from the core measure set. | The Workgroup will periodically identify/confirm the use of core measures by contracting parties to ACO agreements. Current data indicates between 62-72% of risk contract measures are from the core measure set. | A biannual report will document the group’s progress on this task. Work on this report will continue into September.
QAT | # of Maine Residents covered by Alternative Payment Arrangements |  |  | 0 out of 455,000 targeted reported on this month | 328,200 out of 455,000 targeted reported on this month (72%) | Target # of 455,000
MHMC 3 Task 32 | Public report for QI and payment reform | 3, 4, 5 | Hypothesis Three: The development and public reporting of quality measures for behavioral health will serve to introduce more public accountability in behavioral health care and will provide consumers with information that will assist them in assessing where they might seek care. | The Coalition began public reporting the performance of practice groups based on ownership. Staff continued preparations for reporting TCI for practice groups. | Staff collected and prepared data for Oct 1 web update, including the data to report Total Cost of Care for practice groups. | Continue to collect and prepare data for Oct 1 web update, including the data to report Total Cost of Care for practice groups.
MHMC 3 Task 40.6 | Public report for QI and payment reform | 3, 4, 5 | Hypothesis Four: The advancement of public reporting on an advanced primary care recognition will further the promote quality improvement in primary care. | The ACI Steering Committee, SIM Payment Reform Subcommittee and the Delivery System Subcommittee will be consulted on primary care payment models that may be appropriate for the Maine market and which may generate stakeholder support. | Content and scheduling of learning sessions will commence upon completion of health systems and health plan interviews and reporting of findings. The ACI Steering Committee, SIM Payment Reform Subcommittee, and the Delivery System Subcommittee will be consulted on primary care payment models that may be appropriate for the Maine market and which may generate stakeholder support. Outreach continues with Catalyst of Payment Reform (CPR) and the Health Care Transformation Task Force to present findings on key components for ACO contracts. | September activities will continue contingent on feedback from stakeholders. Basic questions on primary care payment reform in current ACO environment remains a central issue for discussion.
MHMC 4 Tasks 58+59 | PCP access to provider portals | 1 | Hypothesis One: By facilitating access to claims data for their patient panels, providers will have access to a potentially powerful tool to help them understand how their patients are accessing services. | Ongoing discussion for AC portal mechanics and attribution data needs. | Ongoing discussion for AC portal mechanics and attribution data needs. Continue re-send of previous practice reports as requests are made and new contacts identified | Staff will continue to provide support for AC data in portals. The Coalition plans to send out FY2014 Commercial/MaineCare reports. Discussions with MaineCare on preferences for delivery of MaineCare reports will continue.
MHMC 5 Task 62.2 | Practice reports | 1, 4 | Hypothesis One: By providing practices with practice-specific reports on patient panels (by payer source), providers and practice owners will gain a better appreciation for the trends in utilization, cost and quality demonstrated by their own practice as compared to a statewide benchmark, leading to efforts to improve their own performance. | MaineCare reports were released in June 2015. Forthcoming reports are due to the State in Y3Q1. | Commercial reports will be released in Y2 Q4. | Staff anticipates the release of commercial reports in September or October of 2015.
MHMC 6 Task 64 | Consumer engagement | 6 | Hypothesis One: By engaging the public around issues related to payment reform (with this term being taken broadly), cost and quality, we will have more informed consumers and decision makers who will be able to make better decisions regarding their own health and care, as well as participate in broader discussions of health policy. | MaineBiz reached out to Coalition staff to run a lead story on VBID work in Maine. Stories pitched by the Coalition staff are also being considered by Maine Magazine and The Wall Street Journal | Mainebiz published two articles pertinent to the Coalition’s value-based insurance design work: Quality Ratings for Maine's Hospitals with distribution to: 8,814 and Stakeholders Tackle Big Health Care Challenges with distribution to 8,814. | Staff is in communication with a large health plan and will work to develop a story to pitch to news outlets.
QAT | # of People participating in payment reform education |  |  | 0 out of 400 targeted reported this month | 0 out of 400 targeted reported this month | Target # of 400
Legend | Pillars |  | 1. Strengthen Primary Care 2. Integrate Physical and Behavioral Health 3. Develop New Workforce Models 4. Develop New Payment Models 5. Centralize Data and Analysis 6. Engage People and Communities
Quarterly Accountability Color code |  |  | Green 90% to 100% | Yellow 75% to 89% | Red 0% to 74%
Projection Color Codes |  |  | Green (75% - 100% confident) | Yellow (50 – 75% confident) | Red (<50% confident)

## July 2015
Obj. # | Brief Description | Pillar(s) | Hypotheses | Prior Month's Activity (June 2015) | Current Month's Activities (July 2015) | Next Month's Projection (August 2015)
MaineCare 1 Task 6 | Accountable Community Organizations | 1, 4 | If we implement a payment system where providers may share in savings, with savings payment based also on provider performance on quality measures, we will see reduction in total cost of care, improvement in quality, and improvement in population health. | The coming performance year (year #2) is the first year that MHMC will calculate the preliminary benchmark (Deloitte developed the methodology and did the year 1 calculations; moving forward, MHMC will implement the methodology each year). OMS, Deloitte, and MHMC had multiple calls regarding development of those preliminary benchmarks. | OMS and Muskie continued discussions with two ACs to establish monthly claims feeds for the ACs’ analytic platforms. The Department delivered four reports to each AC: monthly dashboard utilization reports, quarterly quality and cost reports, and year 2 preliminary benchmarks reports | OMS will work with Muskie to develop the AC portal as the mechanism for delivering monthly utilization reports, quarterly quality reports, and claims downloads. OMS and Muskie will also work with ACs that would like to establish monthly claims feeds (separate from the portal) for the ACs’ analytic platforms.
QAT | # of Primary Care Practices Participating in AC's |  |  | 28 out of 28 targeted | 28 out of 30 targeted | target # of 30
MaineCare 2 Task 17 | Behavioral Health Home | 2 | If MaineCare members with serious mental health needs have access to an integrated and value-based model of care for case management and support, then they will have improved outcomes, a better service experience, and reductions in cost. | Initial auto-enrollment completed; enrollment efforts ongoing. Opt –in packet completed. Will be sent in July. Working with vendor to mail out. Currently engaged in rate review. Met with consultant undergoing rate review to discuss details. | Behavioral Health Homes - initial auto-enrollment completed; enrollment efforts ongoing. Opt –in packet completed. Currently engaged in rate review. | Packet will be sent to @ 12,000 eligible in July. Opt-in packet finalized. Created success stories. Packet will be sent in August. Cost data was sent to contractor. An independent review will take place by Burns and Associates. Analysis to be completed in September.
QAT | # of Members enrolled in BHHO's |  |  | 2325 out of 2500 targeted | 2325 out of 2600 targeted | Target # of 2600
MaineCare 3 Task 24 | Health Homes | 1, 3 | If MaineCare members with multiple chronic conditions have access to enhanced primary care and care management services when needed, then they will have improved outcomes, a better service experience, and reductions in cost. | Sent mock ups of the MHRT/C curriculum. New curriculum available in January. Annotated bibliography complete. Additional training for health home coordinators will include on-line modules. | Muskie has begun development of online portal, and identified additional relevant trainings for current Health Home Coordinators and others that are part of the BHH team, and those trainings will be accessible through the portal | Muskie has begun development of online portal, and identified additional relevant trainings for current Health Home Coordinators and others that are part of the BHH team, and those trainings will be accessible through the portal That should also go live in January, 2016.
QAT | # of Providers trained under new MHRT/C Curriculum |  |  | No target this month | Trained 0 out of 100 targeted | Target # of 100
MDDC Tasks 3, 4, 7 | ID/DD Program | 1 | If Targeted Case Managers and Primary Care Providers are trained have a better understanding of common physical health issues as they relate to specific displays of behaviors in the I/DD population, then it could help reduce unnecessary crisis calls and an increase in preventative health screenings. If the training proves effective, then recommendations for training requirements will be submitted to MaineCare Policy unit. | Completed trainings in Aroostook County. We have decided to provide a website and or application to assist individuals who work or care for people with I/DD available access to information on best practices, pharmacology management, behavior strategies and community resources. The medical provider curriculum is complete and has been reviewed by medical personnel. Curriculum is currently being reviewed by the Maine Medical Association to gain CME credit approval. | Targeted Case Manager training continues across the State with 2 trainings and 34 participants in July. We are looking at an application that individuals could use to manage the healthcare of those with DD. We are currently looking at the CMS chronic care code to be used for patients with DD. If medical providers used this code they could dedicate a nurse to the management of patient’s with DD. Improving their quality of care. | We are working with Doris Babbage a DD nurse from CPI. She is helping us to redesign the TA program. We are looking at ways that medical practices can improve the quality of care they are providing patient with DD.
QAT | # of Targeted Case Managers Trained |  |  | No target this month | Trained 34 out of 20 targeted | Target # of 20
CDC 1 Tasks 3+4 | NDPP | 4, 6 | If the NDPP is integrated into population health management strategies in Maine, we can prevent or delay the progression/onset of type 2 diabetes for those with pre-diabetes or at high risk for diabetes. For those who progress to a diabetes diagnosis, they consume 2.3 times more health care dolars. | No training offered in June 2015. Maine CDC now has 16 programs under written agreement for data sharing and DPRP reporting. | CMMC led a National DPP Lifestyle Coach training, and 10 new Lifestyle Coaches were trained and deployed. The NDPP program still has 16 written agreements in place. It’s important to note that these agreements are not exclusive to delivering the program to MaineCare beneficiaries. | MaineGeneral has training planned in Northern Maine @ Cary Medical Center August 10th & 11th 2015. Expecting to have 3 new agreements in place by the end of September 2015.
QAT | # of Written NDPP Agreements issued to providers |  |  | 16 out of 14 targeted | 16 out of 15 targeted | Target # of 15
CDC 2 Tasks 10+11 | CHW | 3, 6 | If CHWs are recognized as valued members of the health care system in Maine, they can support improved health outcomes, appropriate utilization of health care services, and increased cost savings related to chronic disease support, cancer screening, and high risk or high consumers of health care services. | Client identification, referral and patient-level services are ongoing. External engagement of stakeholders and allies to assure more widespread understanding of the CHW model and potential adoption to sustain efforts was a focus of webinar participation to BHH entities, and exploratory meetings with Maine Community Health Options and the Bureau of Licensing. | Client identification, referral and patient-level services are ongoing. Customized data reporting grids were developed and distributed (in consultation with JSI evaluation) to all of the pilot projects to streamline data collection on CHW services. External engagement of stakeholders and allies focused on the establishment of a voluntary registry as a result of legislation passed during this past session. | Data grids will be used for the CHWI Pilot Projects’ Q3 reports and pilots are also responsible for transferring prior quarters to reporting template as well. Three interviews with Maine’s payer entities/health plans will be completed this summer, as part of a US Office of Minority Health initiative.
QAT | Number of Clients served through CHW Pilot |  |  | 408 out of 250 targeted | 0 out of 275 targeted reported this month | Target # of 275
HIN 1 Task 5 | HIE for MC, care management | 1, 5 | “IF” HIN can release, build, and deliver real-time ADT notifications to MaineCare Care Management, HIN can add value to MC’s Care Management program by providing these real-time notifications. | Email notifications are active and continuous between HIN and the Care Management team at MaineCare is actively working on implementation and workflows with her team. Additional Technical Assistance has been hired and will be helping them starting in June. | Lean Health Care East has begun to meet with the project team to explore workflow on the MaineCare team. HIN responded to feedback regarding the timliness of discharge documents as well as formatting items for the documents. | HIN is actively working with remaining hospitals to send "Chief Complaint" in addition to diagnosis from the ED to be included in the notifications. We will be participating in the new meetings with Steve Musica the Lean consultant to learn about how the workflows and staff feedback can continue to grow the impact of this project.
QAT | # of Active Users of the Clinical Portal |  |  | 1095 out of 895 targeted | 1103 out of 875 targeted | Target # of 875
HIN 2 Task 10 | Incentives for E H R | 2 | “IF” BH organizations in Maine have access to funding reimbursements to support Electronic Health Record interoperability improvements and HIE connection, they will choose to invest in their EHR and participate in Maine’s statewide HIE. | There are now 14 organizations that have passed M1 activities and were approved for payment. The remaining 6 organizations requested extensions to allow more time for their vendors to complete requested configuration and IT development work to enable HIE integrated testing to begin. | There are now 14 organizations that have passed M1 activities and were approved for payment. The remaining 6 organizations requested extensions to allow more time for their vendors to complete requested upgrades to enable HIE integrated testing to begin. | HIN is focused on weekly technical calls with each team and vendor to push deadlines forward in a positive direction for the bidirectional connection.
QAT | Amount of money for milestones incentives paid out |  |  | Paid out $550,000 out of $600,000 targeted | Paid out $550,000 out of $700,000 targeted | Target # of $700,000
HIN 3 Task 17 | BH connect to HIE | 2 | “IF” reimbursements are available to BH organizations under SIM, BH organizations can move forward with bidirectional connections to the HIE. | Data sharing: 3 organizations are bi-directional and sharing data, 3 are in final production validation phase testing substance abuse blocking scenarios as their final step to go-live approval. Testing timelines depend on staff to take the time for the testing process with HIN's staff. HIN staff are prepared to move forward. | Data sharing with Behavioral Health Organizations: 3 organizations are bi-directional and sharing data, 3 are in final production validation phase testing substance abuse blocking scenarios as their final step to go-live approval. | In August the next 3 bidirectional connections should be approved to go-live. An extra round of testing for substance abuse data blocking was required due to a vendor upgrade involving this workflow. This set the go live back about 8 weeks.
QAT | # of sites connected to HIE for BHH |  |  | 14 out of 11 targeted | 15 out of 11 targeted | Target # of 11
HIN 4 Task 24 | Dashboard | 5 | “IF” HIN has access to MaineCare Claims files, HIN can build an interactive analytical dashboard that presents clinical HIE and claims data to MaineCare, and the HIN Dashboards will be used to support/inform MC policy and program activities addressing utilization and member outcomes. “IF” HIN has access to MaineCare Claims files, HIN will be able to integrate discrete MaineCare prescription data into the Clinical Portal for access by all HIE users. | MC Staff received a training session on June 29th as planned. | MaineCare Staff received training sessions regarding the Clinical Dashboard. | MC Care Managers will continue to be trained once Dr. Yoe completes evaluation instrcutions for intervention for Audrey Pratt and Tracy Emerson.
HIN 5 Task 33 | Patient Portal | 6 | “IF” patients have access to their state-wide HIE record Continuity of Care Document (CCD) via their local provider's Patient Portal, they will access it. | The project implementation is completed. | HIN met with EMHS in July to finalize the last email feedback survey to be used to collect data for future implementation. | Survey was released at the end of July and will run thru August.
QC 1 Task 3 | LC for HH | 1, 2, 3, 4 | Primary care practices participating in the MaineCare Health Homes (HH) initiative and the HH Learning Collaborative will successfully implement the PCMH/HH 10 Core Expectations and HH required screenings, resulting in improvements in clinical quality, integrated care, and patient experience, and decreasing avoidable health care spending for individuals with chronic conditions. | Our first multi-site Learning Session included a full day of workshops on building and sustaining resiliency for individuals and teams in primary care. The webinar content was posted to our QC HH Learning Collaborative webpage. This webinar series brought together Health Home practice teams to review the highlights and lessons learned from our Learning Session and specifically what is needed from leaders and teams in primary care to build and sustain resiliency in the primary care field. | The July webinars as part of the SIM Learning Collaborative were convened bringing together Health Home practice teams to highlight strategies and best practices for decreasing admissions and readmissions. | With continuing to focus specifically on project planning for the October 2 Learning Session that will bring together Health Homes, CCTs, BHHOs, and patient/consumer partners and will provide targeted workshops focused on strengthening collaborative work to decrease re-admissions and improve care transitions.
QAT | # of Active Participating HH Single payer practics supported by Learning Collaboratives |  |  | 117 out of 114 targeted | 111 out of 114 targeted | Target # of 114
QC 3 Tasks 15, 19 | LC for BHH | 2, 3 | If BHHO teams receive QI support through the BHH Learning Collaborative, they will be successful in fulling the 10 BHH Core Expectations, resulting in improvements in integrated care, improved physical and behavioral health outcomes, increased communication between health care providers, greater use of preventive services, community supports, and self-management tools for adults with Serious Mental Illess and children with Serious Emotional Disturbance. | The BHH LC hosted a webinar highlighting the work and opportunities to collaborate with Community Care Teams and the SIM Community Health Worker Pilot. BHH LC focused on performing quality improvement and engaging members and families. | In July, the BHH Beacon e-newsletter was distributed to nearly 300 individuals on 7/29/2015. | In August, the BHH LC team will be planning for the upcoming September 21st MaineCare BHH Working Group and QC BH Committee meetings. This will include highlighting the work of one BHH to present during the BHH Working Group and supporting the outreach to content experts for the QC BH Committee
QAT | % of BHHO's supported by BHH Learning Collaboratives |  |  | 100% out of 100% targeted | 100% out of 100% targeted | Target % is 100%
MHMC l Tasks 7+8 | Track health care costs | 5 | Hypothesis One: That a robust data and analytics function helps stimulate better informed decisions regarding quality improvement, patient experience of care and payment reform, as well as strategies to address cost of care. | The data team began processing Q42014 data. Initial processing and implementation continues of Medicare claims data. | Q12015 data was received with run out data for 2014. The attribution for this data was run successfully. | HDMS processing of Q12015 data. Release of preliminary data extract for review and data decisions will happen in August.
MHMC l Task 14 | Track health care costs | 5 | Hypothesis Two: By providing information and data regarding the health care environment to a broad audience, including those who make purchasing decisions for groups of employees, they are better prepared to make informed coverage decisions. | Next summit is scheduled for July 9 in Bangor. June activities included finalization of agenda, invitation distribution and follow-up, and securing and prepping of speakers. | CEO Summit took place with 32 participants in attendance. (Purchasers: 44%; plans/brokers: 25%; providers: 22%; other: 9%) | August activities will include initial preparation for next summit (to be scheduled in late November/early December), including work on date, venue, co-sponsors, keynote speaker, and agenda topics.
MHMC l Tasks 12+12.3 | Track health care costs | 5 | Hypothesis Three: Through the use of a consensus-based process involving informed stakeholders, sound guidance regarding strategies to address health care costs may be developed to guide purchasing and policy decisions and that guidance will be adopted by decision makers. | Healthcare Cost Workgroup meeting was rescheduled to July 1. June activities included preparation for the July 1 meeting, at which time the workgroup will consider a revised draft of principles and criteria it could use to evaluate--and potentially publicly support--resource realignment plans. | The Healthcare Cost Workgroup reached preliminary agreement on a set of principles and criteria that could be used to evaluate infrastructure realignment proposals. | August activities will include a Healthcare Cost Workgroup meeting (on August 20), at which time the workgroup expects to finalize its recommendation on principles and criteria, and potentially finalize its scope of work for a health resource inventory.
MHMC 2 Task 18.1 | VBID | 4 | Hypothesis One: The development of a baseline value based benefit design that appropriately balances cost of care and value of services will speed adoption and use of such coverage in Maine. When adopted, this type of coverage will lead to improved patient outcomes and experience of care, as well as more appropriate costs of care. | Three health plans agreed to accept a standardized provider enrollment application. All health plans agreed to participate in the creation of a repository to house each health plan's credentialing and enrollment requirements, forms, and specific contacts to assist providers. | Administrative Simplification recommended a standardized provider enrollment application using the HCAS application as a template. This group also agreed, by consensus, to create a web-based provider enrollment guide intended to house credentialing and enrollment information specific to each health plan with links to their websites in one place. | Identify/develop an appropriate website to house the enrollment application and enrollment guide with the assistance of providers and health plans to ensure the technology meets the needs of those using it.
QAT | # of covered lives enrolled in plan that incorporate VBID |  |  | No target this month | 0 out of 10000 targeted reported on this month | Target # of 10000
MHMC 3 Task 39 | Public report for QI and payment reform | 3, 4, 5 | Hypothesis One: The identification and adoption of a set of core metrics for ACOs will allow for benchmarking performance across plans and more informed purchasing decisions on the part of purchasers, as well as decreasing pressure on providers (in terms of reporting burdens). | The ACI workgroup recommended a measure set for ACO contracting/payment purposes and a subset of measures to be considered by the PTE Steering Committees for public reporting. Endorsement was received from all stakeholders to use the core measure set as the foundation for performance measurement in their ACO contracts. | The measure set for ACO payment has been recommended and endorsed by stakeholders. A total of 27 measures for payment and 17 measures for monitoring performance have been adopted. | Staff will continue to calculate hospital ratings for October 1st update for existing and new measures.
MHMC 3 Task 40 | Public report for QI and payment reform | 3, 4, 5 | Hypothesis Two: Investment in a stakeholder based process to support development of alternative payment arrangements - including ACOs - will lead to an increased uptake/spread of these arrangements in the Maine marketplace, furthering our objective of moving further away from paying on the basis of volume to a greater emphasis on value. | The workgroup is still addressing the challenges of implementation and adoption, as well as the longer term question of accessing clinical data. There are several threshold issues that remain to be resolved regarding denominator analysis, claims measures reporting timelines, reporting of the clinical measure “starter set,” and adoption of technical specifications. | The Workgroup will periodically identify/confirm the use of core measures by contracting parties to ACO agreements. Current data indicates between 62-72% of risk contract measures are from the core measure set. | A biannual report will document the group’s progress on this, which is to begin in August.
QAT | % of Maine Residents covered by Alternative Payment Arrangements |  |  | 24.60% out of 30% Targeted | 0% out of 35% targeted reported on this month | Target % of 35%
MHMC 3 Task 32 | Public report for QI and payment reform | 3, 4, 5 | Hypothesis Three: The development and public reporting of quality measures for behavioral health will serve to introduce more public accountability in behavioral health care and will provide consumers with information that will assist them in assessing where they might seek care. | Staff completed data collection for July 1 update for hospitals and practice groups. Total Cost of Care data targeted to go live for the October web update based on new data update. | The Coalition began public reporting the performance of practice groups based on ownership. Staff continued preparations for reporting TCI for practice groups. | In August, staff will collect and prepare data for October 1st web update including Total Cost of Care for practice groups.
MHMC 3 Task 40.6 | Public report for QI and payment reform | 3, 4, 5 | Hypothesis Four: The advancement of public reporting on an advanced primary care recognition will further the promote quality improvement in primary care. | Outreach has begun to invite Catalyst for Payment Reform (CPR) to present findings on ACO contract models and to share the core elements of ACO contracts developed by the Health Care Transformation Task Force. | The ACI Steering Committee, SIM Payment Reform Subcommittee and the Delivery System Subcommittee will be consulted on primary care payment models that may be appropriate for the Maine market and which may generate stakeholder support. | August activities will continue contingent on feedback from stakeholders.
MHMC 4 Tasks 58+59 | PCP access to provider portals | 1 | Hypothesis One: By facilitating access to claims data for their patient panels, providers will have access to a potentially powerful tool to help them understand how their patients are accessing services. | No new portal releases in June. Discussions of AC portal requirements were held. | Ongoing discussion for AC portal mechanics and attribution data needs. | Release of AC portal. Status reflects the narrow use of portals currently. Portals exist for all HH and BHH practices for MaineCare data, and for provider groups with ACO arrangements with commercial data. MaineCare AC portals are in development.
QAT | # of Practices that have adopted claims portals |  |  | 290 out of 275 targeted | 0 out of 275 targeted reported this month | Target # of 275
MHMC 5 Task 62.2 | Practice reports | 1, 4 | Hypothesis One: By providing practices with practice-specific reports on patient panels (by payer source), providers and practice owners will gain a better appreciation for the trends in utilization, cost and quality demonstrated by their own practice as compared to a statewide benchmark, leading to efforts to improve their own performance. | The Coalition released CY 2013 MaineCare reports to individual practices as well as owners/PHOs. | MaineCare reports were released in June 2015. Forthcoming reports are due to the State in Y3Q1. | Staff anticipates the release of commercial reports in September or October of 2015. MaineCare reports were released in June 2015. Forthcoming reports are due to the State in Y3Q1.
MHMC 6 Task 64 | Consumer engagement | 6 | Hypothesis One: By engaging the public around issues related to payment reform (with this term being taken broadly), cost and quality, we will have more informed consumers and decision makers who will be able to make better decisions regarding their own health and care, as well as participate in broader discussions of health policy. | On June 6, HR Power Hour, News Talk radio WLOB 1310 AM aired Nancy Morris' interview, High Deductible Plans; the Good, the Bad, and the Alternative. This presentation was built around the concepts of our VBID model. The program reaches an audience of 6,000–7,000 listeners a month. | MaineBiz reached out to Coalition staff to run a lead story on VBID work in Maine. Stories pitched by the Coalition staff are also being considered by Maine Magazine and The Wall Street Journal | MaineBiz will run a lead story on VBID in August. Staff is in communication with a large health plan and will work to develop a story to pitch to news outlets.
QAT | # of People participating in payment reform education |  |  | 80 out of 350 targeted | 0 out of 400 targeted reported this month | Target # of 400
Legend | Pillars |  | 1. Strengthen Primary Care 2. Integrate Physical and Behavioral Health 3. Develop New Workforce Models 4. Develop New Payment Models 5. Centralize Data and Analysis 6. Engage People and Communities