Draft workplan for Selection of Core Metrics for Maine SIM

| Timeline | Core Activities | Activity Needed from ME SIM Team |
| --- | --- | --- |
| Week of 11/11 | - Kick off meeting | - Identify key participants and their availability - Participate in kickoff |
| Weeks 11/18 – 11/25 | - TA team to gather candidate metrics and map to ME DD based on criteria refined in kickoff, identify key gaps - Develop agenda and hold second meeting to discuss draft mapping | - Assist TA team in identifying sources for candidate measures not included in ME’s OP - Participate in second discussion to refine draft mapping of metrics to DD |
| Week of 12/2 | - TA team to provide revised mapping and write up of decisions points from second meeting back to Maine team | None |
| Week of 12/9 |  | - Circulate revised mapping of DD to core metrics to additional stakeholders for feedback |
| Week of 12/16 | - TA team to make additional revisions if needed based on feedback gathered in week 5 | - Maine to vet final draft with steering committee |