## Slide 1: Maine State Innovation Model (SIM) Timeline Update
August 14, 2012

## Slide 2
n
Operational Plan Development and Review:
Timeline and Process
June 10 – 28 Operational Plan Development
June 28: Deadline for Content Submission
July 10: Steering Committee Begins Review and submits requests for more information
July 27:
Steering Committee Approval for Submission
Aug 1: Submission of SIM Operational Plan to CMMI
Oct 1: Deadline for CMMI approval to move into testing phase
July 29: Special Ops Plan Session
We are here

## Slide 3
n
Operational Plan Post Submission Activity Timeline/Milestones
Aug 1: Submission of SIM Operational Plan
Oct 1: Deadline for approval to move
into testing phase
Sep 11: Sub-Committee Membership Presented to Steering Committee for acceptance
We are here
Operational Plan
Adjustments and Sub-Committee
development