Department of Health and Human Service

Office of Substance Abuse and Mental Health Services

Third Quarter State Fiscal Year 2015

Report on Compliance Plan Standards: Community

May 1, 2015

|  | Compliance Standard | Report/Update |
| --- | --- | --- |
| I.1 | Implementation of all the system development steps in October 2006 Plan | As of March 2010, all 119 original components of the system development portion of the Consent Decree Plan of October 2006 have been accomplished or deleted per amendment. |
| I.2 | Certify that a system is in place for identifying unmet needs | See attached Cover: Unmet Needs May 2015 and Unmet Needs by CSN for FY15 Q2. Found in Section 7. |
| I.3 | Certify that a system is in place for Community Service Networks (CSNs) and related mechanisms to improve continuity of care | The Department’s certification of August 19, 2009 was approved on October 7, 2009. |
| I.4 | Certify that a system is in place for Consumer councils | The Department’s certification of December 2, 2009 was approved on December 22, 2009. |
| I.5 | Certify that a system is in place for new vocational services | The Department certification of September 17, 2011 was approved November 21, 2011. |
| I.6 | Certify that a system is in place for realignment of housing and support services | All components of the Consent Decree Plan of October 2006 related to the Realignment of Housing and Support Services were completed as of July 2009. Certification was submitted March 10, 2010. The Certification Request was withdrawn May 14, 2010. |
| I.7 | Certify that a system is in place for a Quality Management system that includes specific components as listed on pages 5 and 6 of the plan | Department of Health and Human Services Office of Adult Mental Health Services Quality Management Plan/Community Based Services (April 2008) has been implemented; a copy of plan was submitted with the May 1, 2008 Quarterly Report. A new quality improvement plan for 2015-2020 is being developed and should be available for review in 2015. |
| II.1 | Provide documentation that unmet needs data and information (data source list page 4 of compliance plan) is used in planning for resource development and preparing budget requests | Department has submitted funding requests to meet all identified needs under the Consent Decree, both through the supplemental budget and the next biennial budget, and the Governor has included those requests in his proposed budget. This is the first year that the Department has requested all funds be included in the base budget request instead of having 2 budget requests for grant funds. |
| II.2 | Demonstrate reliability of unmet needs data based on evaluation | See Cover: Unmet Needs and Quality Improvement Initiatives May 2015 and the Performance and Quality Improvement Standards: May 2015 for quality improvement efforts taken to improve the reliability of the ‘other’ and CI unmet resource data. SAMHS continues to review the reliability of the unmet needs data to ensure proper identifying, recording and implementation of services for unmet needs. |
| II.3 | Submission of budget proposals for adult mental health services given to Governor, with pertinent supporting documentation showing requests for funding to address unmet needs (Amended language 9/29/09) | The Director of SAMHS provides the Court Master with an updated projection of needs and associated costs as part of his ongoing updates regarding Consent Decree obligations. |
| II.4 | Submission of the written presentation given to the legislative committees with jurisdiction over DHHS … which must include the budget requests that were made by the Department to satisfy its obligations under the Consent Decree Plan and that were not included in the Governor’s proposed budget, an explanation of support and importance of the requests and expression of support … (Amended language 9/29/09) | See above. |
| II.5 | Annual report of MaineCare Expenditures and grant funds expended broken down by service area | MaineCare and Grant Expenditure Report for FY 14 provided in the May 2015 report section 15. |
| III.1 | Demonstrate utilizing QM System | See attached Cover: Unmet Needs May 2015 and the Performance and Quality Improvement Standards: May 2015 for examples of the Department Utilizing the QM system. |
| III.1a | Document through quarterly or annual reports the data collected and activities to assure reliability (including ability of EIS to produce accurate data) | This quarterly report documents significant data collection and review activities of the SAMHS quality management system. |
| III.1b | Document how QM data used to develop policy and system improvements | See compliance standard II.4 above for examples of how quality management data was used to support budget requests for systems improvement. Unmet need reports have been used to identify where additional funds are needed for delivery of services. |
| IV.1 | 100% of agencies, based on contract and licensing reviews, have protocol/procedures in place for client notification of rights | Contract and licensing reviews are conducted as licenses expire. A report from DLRS is available; during the last quarter 26 of 26 agencies had protocol/procedures in place for client notification of rights. |
| IV.2 | If results from the DIG Survey fall below levels established for Performance and Quality Improvement Standard 4.2, 90% of consumers report they were given information about their rights, the Department: (i) consults with the Consumer Council System of Maine (CCSM); (ii) takes corrective action a determined necessary by CCSM; and (iii) develops that corrective action in consultation with CCSM. (Amended language 1/19/11) | The percentage for standard 4.2 from the 2014 DIG Survey was 88.1%. These data are posted on the SAMHS website and provided to the Consumer Council of Maine. SAMHS met to address the methodology used for the survey and to boost consumer participation in the survey to be distributed in October of 2014. |
| IV.3 | Grievance Tracking data shows response to 90% of Level II grievances within 5 days or extension. | Standard no longer reported per amendment dated May 8, 2014. Report available upon request. |
| IV.4 | Grievance Tracking data shows that for 90% of Level III grievances written reply within 5 days or within 5 days extension if hearing is to be held or if parties concur. | Standard no longer reported per amendment dated May 8, 2014. Report available upon request. |
| IV.5 | 90% hospitalized class members assigned worker within 2 days of request - must be met for 3 out of 4 quarters | See attached Performance and Quality Improvement Standards: May 2015, Standard 5-2. This standard has not been met for the past 4 quarters. |
| IV.6 | 90% non-hospitalized class members assigned worker within 3 days of request - must be met for 3 out of 4 quarters | See attached Performance and Quality Improvement Standards: May 2015, Standard 5-3. This standard has not been met for the past 4 quarters. |
| IV.7 | 95% of class members in hospital or community not assigned within 2 or 3 days, assigned within an additional 7 days - must be met for 3 out of 4 quarters | See attached Performance and Quality Improvement Standards: May 2015, Standard 5-4. This standard has not been met for the past 4 quarters. |
| IV.8 | 90% of class members enrolled in CSS with initial ISP completed within 30 days of enrollment - must be met for 3 out of 4 quarters | See attached Performance and Quality Improvement Standards: May 2015, Standard 5-5. This standard has not been met for the past 4 quarters. |
| IV.9 | 90% of class members had their 90 day ISP review(s) completed within that time period - must be met for 3 out of 4 quarters | See attached Performance and Quality Improvement Standards: May 2015, Standard 5-6. This standard has not been met for the past 4 quarters. |
| IV.10 | QM system includes documentation that there is follow-up to require corrective actions when ISPs are more than 30 days overdue | Monitoring of overdue ISPs continues on a quarterly basis. As the data has been consistent over time and the feedback and interaction with providers had lessened greatly, reports are now created quarterly and available to providers upon request. Providers were notified of this change on May 18, 2011. |
| IV.11 | Data collected once a year shows that > 5% of class members enrolled in CS did not have their ISP reviewed before the next annual review | The 2014 data analysis indicates that out of 1,407 records for review, 142 (10.1%) did not have an ISP review within the prescribed time frame. |
| IV.12 | Certify in quarterly reports that DHHS is meeting its obligation re: quarterly mailings | On December 10, 2014, the court approved an amendment to a Stipulated Order that requires monitoring of class member addresses. If the percentage of unverified addresses exceeds 15%, the court master will review the efforts and make necessary recommendations. A list of class member’s addresses is available to the court master, plaintiff’s counsel and the court upon request. |
| IV.13 | In 90% of ISPs reviewed, all domains were assessed in treatment planning - must be met for 3 out of 4 quarters | See Section 9 Class Member Treatment Planning Review, Question 2A. This standard has been met in 4 out of the last 4 quarters. The current percentage is 100.0%. |
| IV.14 | In 90% of ISPs reviewed, treatment goals reflect strengths of the consumer - must be met for 3 out of 4 quarters | Standard no longer reported per amendment dated May 8, 2014. Report available upon request. |
| IV.15 | 90% of ISPs reviewed have a crisis plan or documentation as to why one wasn’t developed - must be met for 3 out of 4 quarters | Standard no longer reported per amendment dated May 8, 2014. Report available upon request. |
| IV.16 | QM system documents that SAMHS requires corrective action by the provider agency when document review reveals not all domains assessed | See Section 9 Class Member Treatment Planning Review, Question 6.a.1 that addresses plans of correction. N/A – all domains were assessed |
| IV.17 | In 90% of ISPs reviewed, interim plans developed when resource needs not available within expected response times - must be met for 3 out of 4 quarters | See attached Performance and Quality Improvement Standards: May 2015, Standard 8-2 and Class Member Treatment Plan Review, Question 3F. This standard has not been met in the last 4 quarters. |
| IV.18 | 90% of ISPs review included service agreement/treatment plan - must be met for 3 out of 4 quarters | See attached Performance and Quality Improvement Standards: May 2015, Standard 9-1 and Class Member Treatment Plan Review, Questions 4B & C. This standard has not been met in the last 4 quarters. |
| IV.19 | 90% of ACT/ICI/CI providers statewide meet prescribed case load ratios - must be met for 3 out of 4 quarters Note: As of 7/1/08, ICI is no longer a service provided by DHHS. | Standard no longer reported per amendment dated May 8, 2014. Report available upon request. |
| IV.19 | 90% of ICMs with class member caseloads meet prescribed case load ratios - must be met for 3 out of 4 quarters | ICMs’ work is focused on community forensic and outreach services. Individual ICMs no longer carry caseloads. Should this change in the future, SAMHS will resume reporting on caseload ratios. |
| IV.20 | 90% of OES workers with class member public wards - meet prescribed caseloads must be met for 3 out of 4 quarters | See attached Performance and Quality Improvement Standards: May 2015, Standard 10-5. This standard has been met in FY 15 Q2 and Q3. |
| IV.21 | Independent review of the ISP process finds that ISPs met a reasonable level of compliance as defined in Attachment B of the Compliance Plan |  |
| IV.22 | 5% or fewer class members have ISP-identified unmet residential support - must be met for 3 out of 4 quarters and | See attached Performance and Quality Improvement Standards: May 2015, Standard 12-1 Standard met for the 4th quarter FY08; the 1st, 3rd and 4th quarters of FY09; all quarters of FY10 and FY11; all 4 quarters of FY12, FY13; FY 14, Y15 Q1 and Q2. |
| IV.23 | EITHER quarterly unmet residential support needs for one year for qualified (qualified for state financial support) non-class members do not exceed by 15 percentage points those of class members OR if exceeded for one or more quarters, SAMHS produces documentation sufficient to explain cause and to show that cause is not related to class status and | Unmet residential supports needs for non-class members do not exceed 15 percentage points of the same for Class Members. See attached report Consent Decree Compliance Standards IV.23 and IV.43 |
| IV.24 | Meet RPC discharge standards (below); or if not met document reasons and demonstrate that failure not due to lack of residential support services 70% RPC clients who remained ready for discharge were transitioned out within 7 days of determination 80% within 30 days 90% within 45 days (with certain exceptions by agreement of parties and court master) | See attached Performance and Quality Improvement Standards: May 2015, Standards 12-2, 12-3 and 12-4 Standard met since the beginning of FY08. |
| IV.25 | 10% or fewer class members have ISP-identified unmet needs for housing resources - must be met for 3 out of 4 quarters and | See attached Performance and Quality Improvement Standards: May 2015, Standard 14-1 Standard met in FY 2014 Q3 and 28 out of the last 32 quarters. |
| IV.26 | Meet RPC discharge standards (below); if not met, document that failure to meet is not due to lack of housing resources. 70% RPC clients who remained ready for discharge were transitioned out within 7 days of determination 80% within 30 days 90% within 45 days (with certain exceptions by agreement of parties and court master) | See attached Performance and Quality Improvement Standards: May 2015, Standard 14-4, 14-5 & 14-6 Standard 14-4 met since the beginning of FY09, except for Q3 FY10. Standard 14-5 met for the 2nd, 3rd and 4th quarters FY09; the 2nd and 4th quarters of FY10; FY11;FY12, FY13 FY 14, and the 1st and 2nd quarters FY 15 Standard 14-6 met for the 2nd and 4th quarters FY09; the 2nd and 4th quarters FY10; FY11; FY12, FY13, and FY 14, and 1st quarter FY 15. |
| IV.27 | Certify that class members residing in homes > 8 beds have given informed consent in accordance with approved protocol | Standard no longer reported per amendment dated May 8, 2014. |
| IV.28 | 90% of class member admissions to community involuntary inpatient units are within the CSN or county listed in attachment C to the Compliance Plan | See attached Performance and Quality Improvement Standards: November 2014, Standard 16-1 and Community Hospital Utilization Review – Class Members 4th Quarter of Fiscal Year 2014. In FY12: 76.2% (16 of 21) in the 1st quarter, 63.6% (14 of 22) in the 2nd quarter, 77.8% (7 of 9) in the 3rd quarter, 73.7% (14 of 19) in the 4th quarter IN FY13: 100% (19 of 19) in the 1st quarter 92.9% (13 of 14) in the 2nd quarter 86.7% (13 of 15) in the 3rd quarter 90.0% (18 of 20) in the 4th quarter IN FY 14: 27.3%(3 of 11) in the 1st quarter 76.5% (13 of 17) in the 2nd quarter 84.6 % (11 of 13) in the 3rd quarter 100.0 % (12 of 12) in the 3rd quarter IN FY 15: 77.8%(14 of 18) in the 1st quarter 95.5%(21 of 22) in the 2nd quarter |
| IV.29 | Contracts with hospitals require compliance with all legal requirements for involuntary clients and with obligations to obtain ISPs and involve CSWs in treatment and discharge planning | See IV.30 below |
| IV.30 | Evaluates compliance with all legal requirements for involuntary clients and with obligations to obtain ISPs and involve CSWs in treatment and discharge planning during contract reviews and imposes sanctions for non-compliance through contract reviews and licensing | All involuntary hospital contracts are in place. |
| IV.31 | UR Nurses review all involuntary admissions funded by DHHS, take corrective action when they identify deficiencies and send notices of any violations to the licensing division and to the hospital | SAMHS reviews emergency involuntary admissions at the following hospitals: Maine General Medical Center, Spring Harbor, St. Mary’s, Mid-Coast Hospital, Southern Maine Medical Center, PenBay Medical Center, Maine Medical Center/P6 and Acadia. See Standard IV.33 below regarding corrective actions. |
| IV.32 | Licensing reviews of hospitals include an evaluation of compliance with patient rights and require a plan of correction to address any deficiencies. | 64 Complaints Received 49 Complaints investigated 6 Substantiated 1 Plan of correction sought 0 Rights of Recipients Violations |
| IV.33 | 90% of the time corrective action was taken when blue papers were not completed in accordance with terms 90% of the time corrective action was taken when 24 hour certifications were not completed in accordance with terms 90% of the time corrective action was taken when patient rights were not maintained | Standard no longer reported per amendment dated May 8, 2014. Report available upon request. |
| IV.34 | QM system documents that if hospitals have fallen below the performance standard for any of the following, SAMHS made the information public through CSNs, addressed in contract reviews with hospitals and CSS providers, and took appropriate corrective action to enforce responsibilities obtaining ISPs (90%) creating treatment and discharge plan consistent with ISPs (90%) involving CIWs in treatment and discharge planning (90%) | See attached report Community Hospital Utilization Review Performance Standard 18-1, 2, 3 by Hospital: Class Members 2nd Quarter of Fiscal Year 2015. The report displaying data by hospital for community hospitals accepting emergency involuntary clients is shared quarterly by posting reports on the CSN section of the Office’s website. Standard 18.1 has not been met for the past 4 quarters. Standard 18.2 has been met for the past 4 quarters Standard 18.3 has been met for the past 4 quarters |
| IV.35 | No more than 20-25% of face-to-face crisis contacts result in hospitalization – must be met for 3 out of 4 quarters | See attached Performance and Quality Improvement Standards: May 2015, Standard 19-1 and Adult Mental Health Quarterly Crisis Report Third Quarter, State Fiscal Year 2015 Summary Report. In FY12, standard met all 4 quarters. In FY 13, standard met all 4 quarters. In FY 14, standard met 1st quarter, 2nd quarter slightly above standard (26.3%), met 3rd quarter and 4th quarter slightly above standard (26.1%) In FY 15 Q1 standard met, slightly above standard inQ2 (25.6%), standard met Q3 |
| IV.36 | 90% of crisis phone calls requiring face-to-face assessments are responded to within an average of 30 minutes from the end of the phone call – must be met for 3 out of 4 quarters Per amendment dated May 8,2014 the standard now reads as follows: 90% of crisis calls requiring face-to-face assessments are responded to within an average of 60 minutes from the end of the phone call | See attached Adult Mental Health Quarterly Crisis Report Third Quarter, State Fiscal Year 2015 Summary Report. Starting with July 2008 reporting from providers, SAMHS collects data on the total number of minutes for the response time (calculated from the determination of need for face to face contact or when the individual is ready and able to be seen to when the individual is actually seen) and figures an average. Average statewide calls requiring face to face assessments are responded to within an average of 30 minutes from the end of the phone call was met for all 4 Quarters in FY12, 4 quarters in FY13 and 1st and 2nd quarter of FY14. Standard not met 3rd quarter FY14. Standard met FY14 Q4. Standard not met 1st quarter FY 15. Met 2nd and 3rd quarters FY 15 |
| IV.37 | 90% of all face-to-face assessments result in resolution for the consumer within 8 hours of initiation of the face-to-face assessment – must be met for 3 out of 4 quarters | See attached Adult Mental Health Quarterly Crisis Report Third Quarter, State Fiscal Year 2015 Summary Report. Standard has been met since the 2nd quarter of FY08 until FY 15 1st quarter when standard was slightly below (87.2%). Standard slightly below 2nd quarter FY 15 (87.7%), Standard slightly below 3rd quarter FY 15 (86.8%). |
| IV.38 | 90% of all face-to-face contacts in which the client has a CI worker, the worker is notified of the crisis – must be met for 3 out of 4 quarters | See attached Performance and Quality Improvement Standards: May 2015, Standard 19-4 and Adult Mental Health Quarterly Crisis Report Third Quarter, State Fiscal Year 2015 Summary Report. Standard met 3 out of 4 quarters. |
| IV.39 | Compliance Standard deleted 1/19/2011. |  |
| IV.40 | Department has implemented the components of the CD plan related to vocational services | As of quarter 3 FY10, the Department has implemented all components of the CD Plan related to Vocational Services. |
| IV.41 | QM system shows that the Department conducts further review and takes appropriate corrective action if PS 26.3 data shows that the number of consumers under age 62 and employed in supportive or competitive employment falls below 10%. (Amended language 1/19/11) | 2014 Adult Health and Well-Being Survey: 10.2 % of consumers in supported and competitive employment (full or part time). |
| IV.42 | 5% or fewer class members have unmet needs for mental health treatment services – must be met for 3 out of 4 quarters and | See attached Performance and Quality Improvement Standards: May 2015, Standard 21-1 This standard has not been met for the last 4 quarters. |
| IV.43 | EITHER quarterly unmet mental health treatment needs for one year for qualified non-class members do not exceed by 15 percentage points those of class members OR if exceeded for one or more quarters, SAMHS produces documentation sufficient to explain cause and to show that cause is not related to class status | Unmet mental health treatment needs for non-class members do not exceed 15 percentage points of the same for Class Members. See attached report Consent Decree Compliance Standards IV.23 and IV.43 |
| IV.44 | QM documentation shows that the Department conducts further review and takes appropriate corrective action if results from the DIG survey fall below the levels identified in Standard # 22-1 (the domain average of positive responses to the statements in the Perception of Access Domain is at or above 85%) (Amended language 1/19/11) and | 2014 Adult Health and Well-Being Survey: 83.3% domain average of positive responses. |
| IV.45 | Meet RPC discharge standards (below); if not met, document that failure to meet is not due to lack of mental health treatment services in the community 70% RPC clients who remained ready for discharge were transitioned out within 7 days of determination 80% within 30 days 90% within 45 days (with certain exceptions by agreement of parties and court master) | See attached Performance and Quality Improvement Standards: May 2015, Standards 21-2, 21-3 and 21-4 Standard met since the beginning of FY08 |
| IV.46 | The department documents the programs it has sponsored that are designed to improve quality of life and community inclusion for class members, including support of peer centers, social clubs, community connections training, wellness programs, and leadership and advocacy training programs. Standard amended per amendment dated May 8, 2014 | Standard no longer reported per amendment dated May 8, 2014. Report available upon request. |
| IV.47 | 10% or fewer class members have ISP-identified unmet needs for transportation to access mental health services – must be met for 3 out of 4 quarters | See attached Performance and Quality Improvement Standards: May 2015, Standard 28 This standard has been consistently met since FY08. |
| IV.48 | Provide documentation in quarterly reports of funding, developing, recruiting, and supporting an array of family support services that include specific services listed on page 16 of the Compliance Plan | Standard no longer reported per amendment dated May 8, 2014. Report available upon request. |
| IV.49 | Certify that all contracts with providers include a requirement to refer family members to family support services, and produce documentation that contract reviews include evaluation of compliance with this requirement. | Standard no longer reported per amendment dated May 8, 2014. Report available upon request. |
| IV.50 | The department documents the number and types of mental health informational workshops, forums, and presentations geared toward the general public that are designed to reduce myths and stigma of mental illness and to foster community integration or persons with mental illness. | Standard no longer reported per amendment dated May 8, 2014. Report available upon request. |