## Sheet1
Timeline Tool To Determine Dates For Withdrawal Agreements:
Important dates regarding timeline for Final vote on Withdrawal: |  |  | STATUTES TITLE 20 - A
Date of next Statewide General Election: | 2026-11-03 | (date for vote on withdrawal referendum)
At least 10 days prior to general election: | 2026-10-24 | (deadline for municipality to hold public hearing on upcoming vote) | 1466 - 6A
At least 35 days prior to general election: | 2026-09-29 | (absolute deadline for written notice from DOE of date of vote - must have final (after public hearing) conditional approval on withdrawal agreement) Note - some municipalities require a 45-day notice for referendum items in order to facilitate absentee ballots. | 1466 - 5B
Within 30 days after public hearing/at least two weeks prior to Deadline for Referendum Date by Commissioner: | 2026-09-15 | (Results of public hearing must be reported to Commissioner prior to final conditional approval or changes resulting from public hearing | 1466 - 5
Date of initial public hearing for conditional agreement - latest date it can be held is 8/13: | 2026-08-13 | (Initial public hearing to discuss merits of proposed withdrawal agreement) | 1466 - C2
At least 10 days prior to public hearing: | 2026-08-03 | (RSU board must post a public notice in each municipality of the time and location of the public hearing) | 1466 - C1
At least 20 days prior to public hearing: | 2026-07-24 | (DOE must notify municipality of conditional approval at least 20 days prior to public hearing date) | 1466 - C
Deadline for Submission of Signed Withdrawal Agreement to Commissioner: | 2026-06-30 | (This signficantly reduces the allowed time for review from 60 days to 30 days) | 1466 - 4B
Note: only the dates highlighted in blue can be changed - other dates recalculate automatically based on those dates.