## Sheet1
This report was last refreshed: 04/15/2024
# of Projects |  | # of Contracts
316 |  | 230
Contract No. | Town(s) |  | Fed Proj Num |  | Project ID | Program | Description | Prime Contractor |  | Resident | Project Manager |  | Construction Begin | Anticipate Complete
026786.00 | Addison, Beals, Columbia Falls, East Machias, Harrington, Jonesboro, Jonesport, Machias, Machiasport, Marshfield, Northfield, Roque Bluffs, Wesley, Whitneyville |  |  |  | 026786.00 | REGIONAL PROGRAM | MACHIAS AREA LCP | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
026122.00 | Albany Twp |  | 2612200 |  | 026122.00 | BRIDGE PROGRAM | ALBANY TWP, CROOKED RIVER BR DECK REPL | CPM CONSTRUCTORS |  | ALECIA COLE | Brian Nichols |  | 04/03/2024 | 10/30/2024
025321.00 | Alfred, Arundel, Bar Harbor, Buxton, Caribou, Dixfield, Falmouth, Fort Fairfield, Freeport, Gray, Hampden, Jay, Kittery, Lebanon, Limington, Livermore Falls, Lyman, Madison, Manchester, Mexico, Milford, Oxford, Prospect, Raymond, Rockport, Sabattus, Standish, Thomaston, Turner, Waldoboro, Warren, Waterboro, Yarmouth |  | 2532100 |  | 025321.00 | MULTIMODAL PROGRAM | STATEWIDE: ADVANCED SIGNAL CONTROL AND CONNECTED VEHICLE SYS | DAGLE ELECTRICAL CONSTRUCTION CORP. |  | TYLER CAMICK | Brian Keezer |  | 04/15/2024 | 12/31/2025
026768.00 | Alfred, Arundel, Eliot, Kennebunk, Kennebunkport, Kittery, North Berwick, Sanford, York |  |  |  | 026768.00 | REGIONAL PROGRAM | SANFORD AREA LCP | COASTAL ROAD REPAIR LLC. |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
022498.00 | Alfred, Sanford |  | 2374900 |  | 023749.00 | REGIONAL PROGRAM | SANFORD-ALFRED, US ROUTE 202 4" COLD IN PLACE RECYCLE, MILL | PIKE INDUSTRIES, INC. |  | MATTHEW GUESS | Laray Hamilton |  | 08/08/2021 | 06/30/2023
029085.00 | Alna |  | 029085.00 |  | 029085.00 | MAINTENANCE | ALNA, WETLAND CULVERT REPLACEMENT | LITTLEFIELD’S CONSTRUCTION |  | MATT WHITCOMB | ? |  | 08/08/2023
022898.00 | Alna |  | 022898.00 |  | 022898.00 | MAINTENANCE | ALNA INSTREAM CULVERT REPLACEMENT | LEE'S GENERAL TRUCKING AKA EMERY LEE & SONS, INC. |  | MATT WHITCOMB | Jamie Andrews |  | 08/24/2020 | 09/25/2020
026770.00 | Alna, Bristol, Damariscotta, Jefferson, Newcastle, Pittston, South Bristol, Whitefield, Wiscasset |  |  |  | 026770.00 | REGIONAL PROGRAM | BRISTOL AREA LCP | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
027051.00 | Alna, Newcastle, Pittston, Whitefield |  | 027053.00 |  | 027053.00 | MAINTENANCE | WHITEFIELD, FORESTRY & CANOPY CLEARING | COMPREHENSIVE LAND TECHNOLOGIES |  | MATT WHITCOMB | Brian Reeves |  | 09/14/2021 | 11/23/2022
018769.24 | Alton, Argyle Twp, Bangor, Dyer Brook, Edinburg, Hampden, Hermon, Houlton, Howland, Ludlow, Mattamiscontis Twp, New Limerick, Oakfield, Old Town, Orono, Smyrna, T2 R8 NWP, Veazie |  | 1876924 |  | 018769.24 | REGIONAL PROGRAM | INTERSTATE POLYUREA STRIPING | ON THE LINE, INC |  |  | Shawn Smith |  | 06/10/2024 | 11/01/2024
026458.00 | Alton, Argyle Twp, Benedicta Twp, Crystal, Dyer Brook, Edinburg, Herseytown Twp, Houlton, Howland, Island Falls, Ludlow, Medway, New Limerick, Oakfield, Old Town, Sherman, Smyrna, T1 R6 WELS, T2 R8 NWP, T2 R9 NWP |  | 2645800 |  | 026458.00 | REGIONAL PROGRAM | STATEWIDE INTERSTATE CRACK SEALING INTERSTATE 95 | COASTAL ROAD REPAIR LLC. |  |  | Shawn Smith |  | 06/03/2024 | 08/30/2024
028688.00 | Andover, Mexico, Roxbury, Rumford |  | 2868800 |  | 028688.00 | REGIONAL PROGRAM | EMERGENCY REPAIR ANDOVER - RUMFORD, ROUTE 120 WIN 28688.00 | PRATT & SONS, INC. |  | ROBERT LAROCHE | Emory Lovely |  | 01/02/2024 | 06/01/2024
023200.00 | Anson |  | 2320000 |  | 023200.00 | BRIDGE PROGRAM | ANSON, ROBERT GARLAND BR WEAR SURF REPL | WYMAN & SIMPSON, INC. |  | DAVID DOUCETTE | Jason Stetson |  | 02/01/2024 | 10/24/2024
027080.00 | Arrowsic, Woolwich |  |  |  | 027080.00 | BRIDGE MAINT. | ARROWSIC/WOOLWICH BRIDGE RETROFIT | SCOTT CONSTRUCTION CORPORATION |  |  | Ben Foster |  |  | 06/01/2024
022823.00 | Arundel |  | 2350900 |  | 023509.00 | MULTIMODAL PROGRAM | ARUNDEL, SIGNAL REPLACEMENT AT ROUTE 1 AND LIMERICK ROAD | ELECTRIC LIGHT CO. INC. |  | MATT INGALLS | Brian Keezer |  | 04/06/2024 | 06/30/2024
022823.00 | Arundel |  | 2282300 |  | 022823.00 | MULTIMODAL PROGRAM | ARUNDEL, REPLACE SIGNAL AT ROUTE 1 AND LOG CABIN ROAD | ELECTRIC LIGHT CO. INC. |  | MATT INGALLS | Brian Keezer |  | 04/06/2024 | 06/30/2024
026490.00 | Ashland |  | 2649000 |  | 026490.00 | REGIONAL PROGRAM | ASHLAND, ROUTE 163 MILL & FILL | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | PETER QUELLETTE | Roger Soucy |  | 06/07/2023 | 06/28/2024
027059.00 | Ashland |  | 027059.00 |  | 027059.00 | MAINTENANCE | ASHLAND HEADER REPAIR | BMB CONSTRUCTION LLC |  | KEVIN BUTLER | Brent Bubar
024987.10 | Ashland, Augusta, Bar Harbor, Belgrade, Brookton Twp, Carmel, Columbia, Columbia Falls, Damariscotta, Danforth, Edgecomb, Ellsworth, Etna, Gardiner, Hanover, Harrington, Hermon, Jonesboro, Livermore Falls, Masardis, Merrill, Moro Plt, Nashville Plt, Newcastle, Newport, Nobleboro, Norway, Orrington, Oxford, Plymouth, Poland, Portage Lake, Presque Isle, Richmond, Rockland, Rockport, Rumford, Sidney, T8 R5 WELS, T9 R5 WELS, Thomaston, Trenton, Vassalboro, Waldoboro, Warren, Wayne, Westfield, Weston, Whiting, Winslow |  | 2498700 |  | 024987.10 | REGIONAL PROGRAM | STATEWIDE RUMBLE STRIPS | ON THE LINE, INC |  | HEATHER GROVES | Timothy Pelotte |  | 09/04/2023 | 06/14/2024
024599.05 | Ashland, Castle Hill, Fort Kent, Hersey, Moro Plt, Mount Chase, Patten, Presque Isle, T11 R4 WELS, Wallagrass |  | 024599.05 |  | 024599.05 | REGIONAL PROGRAM | SHIM, ASHLAND, CASTLE HILL, HERSEY, FORT KENT, MOUNT CHASE, | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | KEVIN BUTLER | Brent Bubar
026488.00 | Ashland, Castle Hill, T11 R4 WELS |  | 2648800 |  | 026488.00 | REGIONAL PROGRAM | ASHLAND-T11 R4 1 1/4" OVERLAY | STEELSTONE INDUSTRIES, INC.AKA MCQUADE & TIDD |  |  | Roger Soucy |  | 05/27/2024 | 10/25/2024
026746.01 | Ashland, Chapman, Crystal, Dudley Twp, Dyer Brook, Grindstone Twp, Herseytown Twp, Houlton, Island Falls, Ludlow, Mapleton, Masardis, Millinocket, New Limerick, Oakfield, Presque Isle, Saint Croix Twp, Scopan Twp, Sherman, Smyrna, Stacyville, T1 R6 WELS, T11 R4 WELS, T3 Indian Purchase Twp, T9 R4 WELS, T9 R5 WELS, Webbertown Twp |  |  |  | 026746.01 | MULTIMODAL PROGRAM | NORTHERN MAINE: RAILROAD STONE BALLAST. | LEE'S GENERAL TRUCKING AKA EMERY LEE & SONS, INC. |  |  | Mackenzie Kersbergen |  | 06/17/2024 | 10/31/2025
026732.00 | Ashland, Masardis, T8 R5 WELS, T9 R5 WELS |  | 2673200 |  | 026732.00 | REGIONAL PROGRAM | T7 R5 WELS - ASHLAND, ROUTE 11 3/4" OVERLAY | STEELSTONE INDUSTRIES, INC.AKA MCQUADE & TIDD |  | JOSEPH STEWART | Roger Soucy |  | 08/11/2023 | 06/28/2024
026490.00 | Ashland, Nashville Plt, Portage Lake |  | 2662610 |  | 026626.10 | REGIONAL PROGRAM | ASHLAND, NASHVILLE PLT., PORTAGE LAKE, ROUTE 11 1 1/4 OVERLA | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | PETER QUELLETTE | Roger Soucy |  | 06/07/2023 | 06/28/2024
026778.00 | Athens, Bingham, Brighton Plt, Concord Twp, Cornville, Embden, Harmony, Hartland, Mayfield Twp, Moscow, Saint Albans, Solon, Wellington |  |  |  | 026778.00 | REGIONAL PROGRAM | ATHENS AREA LCP | MICHAEL HOPKINS DBA HOPKINS LANDSCAPING, HOPKINS PAVING |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
026688.00 | Auburn |  | 026690.00 |  | 026688.00 | PLANNING | AUBURN, SHIM & OVERLAY | ST. LAURENT & SON, INC |  | SUZANE NORTON | John Skelley |  | 08/07/2023 | 11/30/2023
025285.00 | Auburn |  | 2669800 |  | 026698.00 | REGIONAL PROGRAM | AUBURN ROUTE 122/HOTEL ROAD ULTRA-THIN BONDED WEARING COURSE | PRATT & SONS, INC. |  | JARROD GOOGINS | Laray Hamilton |  | 06/12/2023 | 09/15/2023
028047.00 | Auburn |  | 028047.00 |  | 028047.00 | MAINTENANCE | AUBURN, WEARING SURFACE REPLACEMENT #3895 | T BUCK CONSTRUCTION, INC. |  | DALTON THOMPSON | ?
025125.00 | Auburn |  | 2512500 |  | 025125.00 | REGIONAL PROGRAM | AUBURN, US ROUTE 202 MILL AND FILL | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | JARROD GOOGINS | Laray Hamilton |  | 07/10/2023 | 10/14/2023
028069.00 | Auburn, Baldwin, Cornish |  | 028269.00 |  | 028069.00 | MAINTENANCE | CORNISH/BALDWIN BRIDGE HEADER REPLACEMENT AND MILL & FILL | BMB CONSTRUCTION LLC |  | ROB BETZ | ?
026764.00 | Auburn, Buckfield, Cape Elizabeth, Cumberland, Falmouth, Gray, Hebron, Minot, Paris, Scarborough |  |  |  | 026764.00 | REGIONAL PROGRAM | CUMBERLAND AREA LCP | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Timothy Pelotte |  | 05/01/2024 | 10/12/2024
025767.00 | Augusta |  | 2576700 |  | 025767.00 | REGIONAL PROGRAM | AUGUSTA, ROUTE 9 ULTRA-THIN BONDED WEARING COURSE | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  |  | Robert K Betz |  | 07/10/2024 | 09/20/2024
025767.00 | Augusta |  | 2771800 |  | 027718.00 | REGIONAL PROGRAM | AUGUSTA, ROUTE 9/US ROUTE 201 ULTRA-THIN BONDED WEARING COU | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  |  | Robert K Betz |  | 07/10/2024 | 09/20/2024
021672.00 | Augusta |  | 2167200 |  | 021672.00 | BRIDGE PROGRAM | AUGUSTA, WESTERN AVE/ I95 BRIDGE REPLACEMENT | REED & REED, INC. |  | CRAIG HURD | Devan Eaton |  | 11/06/2023 | 07/16/2026
027923.00 | Augusta |  | 027923.00 |  | 027923.00 | MAINTENANCE | AUGUSTA - SIGN SUPPORT REPAIR | CPM CONSTRUCTORS |  | GARY PELLETIER | Brian Burne
021872.00 | Augusta |  | STP-2187(200) |  | 021872.00 | BRIDGE PROGRAM | AUGUSTA, RINES HILL BR SUPERSTRUCTURE REPL. | NEW ENGLAND INFRASTRUCTURE INC. |  | CRAIG HURD | Andrew Lathe |  | 01/18/2023 | 06/07/2024
024301.00 | Augusta, Belfast, Benton, China, Fairfield, Farmington, Gardiner, Norridgewock, Oakland, Randolph, Sanford, Waterville, Winslow |  | 02430100 |  | 024301.00 | MULTIMODAL PROGRAM | STATEWIDE TRAFFIC SIGNAL UPDATES, VARIOUS LOCATIONS | DAGLE ELECTRICAL CONSTRUCTION CORP. |  | STEVE HALL | Brian Keezer |  | 07/23/2021 | 12/31/2024
025869.00 | Augusta, Carrabassett Valley, Embden, Hallowell, Highland Plt, Lexington Twp, Manchester, New Portland |  | 025869.00 |  | 025869.00 | REGIONAL PROGRAM | NEW PORTLAND AREA LCP | GENERAL CONTRACTOR VAUGHN D. THIBODEAU II |  | CHRIS LEBLANC | Timothy Pelotte |  | 09/28/2023 | 07/26/2024
023098.00 | Avon |  | 2309800 |  | 023098.00 | BRIDGE PROGRAM | CUSHMAN BRIDGE (#6588) LOCATED 0.12 OF A MILE SOUTH OF AIRPO | T BUCK CONSTRUCTION, INC. |  |  | Jason Stetson |  | 01/17/2024 | 07/14/2025
025853.00 | Baldwin, Brownfield, Buxton, Denmark, Harrison, Hiram, Hollis, Limington, Sebago, Waterboro |  | 025853.00 |  | 025853.00 | REGIONAL PROGRAM | BROWNFIELD AREA LCP | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  | CLEM BAXTER | Timothy Pelotte |  | 07/11/2023 | 05/31/2024
025063.00 | Bangor |  | 2506300 |  | 025063.00 | BRIDGE PROGRAM | BANGOR, I395 - MAIN STREET BR JOINT REHAB. | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | RESIDENT? | Michael Wight |  | 05/13/2024 | 06/21/2024
021663.00 | Bangor |  | 022276.01 |  | 022276.01 | BRIDGE PROGRAM | BANGOR, I95/ BROADWAY BR REPL | NEW ENGLAND INFRASTRUCTURE INC. |  | BRIAN MOUSSEAU | Andrew Lathe |  | 07/12/2023 | 11/27/2024
021902.00 | Bangor |  | 021902.00 |  | 021902.00 | MATERIALS TESTING AND EXPLORATION | BANGOR - DESIGN AND BUILD STORAGE BUILDING | RALPH MCNAUGHTON CONSTRUCTION INC |  | STEVE HALL 592-7907 | Richard Bradbury
021663.00 | Bangor |  | HSIP-2166(300) |  | 021663.00 | MULTIMODAL PROGRAM | BANGOR, HIGHWAY SAFETY IMPROVEMENTS ON BROADWAY | NEW ENGLAND INFRASTRUCTURE INC. |  | BRIAN MOUSSEAU | Daniel Loring |  | 09/18/2023 | 10/30/2026
025325.00 | Bangor, Brewer |  | 2532500 |  | 025325.00 | MULTIMODAL PROGRAM | BANGOR / BREWER: NEW HIGHWAY TRAFFIC CAMERAS AT FIVE SITES | ELECTRIC LIGHT CO. INC. |  |  | Daniel Loring |  | 05/13/2024 | 05/16/2025
025263.00 | Bangor, Brewer, Orono |  | 2526300 |  | 025263.00 | MULTIMODAL PROGRAM | INSTALLATION OF TRAFFIC SIGNAL BACKPLATES IN GREATER BANGOR | DAGLE ELECTRICAL CONSTRUCTION CORP. |  |  | Gerald Dostie |  | 03/21/2024 | 07/31/2024
024239.00 | Bangor, Carmel, Hallowell, Hampden, Portland, Sidney, South Portland |  | 2423900 |  | 024239.00 | MULTIMODAL PROGRAM | REPLACEMENT OF CHANGEABLE MESSAGE SIGNS | MOULISON ELECTRIC, INC. |  | KAREN LIBBY | Daniel Loring |  | 08/21/2023 | 08/30/2024
025143.00 | Bar Harbor |  | 2672000 |  | 026720.00 | REGIONAL PROGRAM | BAR HARBOR, ROUTE 3 ULTRA-THIN BONDED WEARING COURSE | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | CARMEN FORZETTING | Randall Barrows |  | 06/11/2023 | 11/02/2023
025879.00 | Bar Harbor, Blue Hill, Bucksport, Ellsworth, Mount Desert, Sedgwick, Trenton |  | 025879.00 |  | 025879.00 | REGIONAL PROGRAM | TRENTON AREA LCP | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | JARED STANLEY | Timothy Pelotte |  | 05/08/2023 | 07/26/2024
025143.00 | Bar Harbor, Trenton |  | 2514300 |  | 025143.00 | REGIONAL PROGRAM | TRENTON-BAR HARBOR, ROUTE 3 | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | CARMEN FORZETTING | Randall Barrows |  | 06/11/2023 | 11/02/2023
026776.00 | Belfast, Brooks, Burnham, Dixmont, Jackson, Knox, Plymouth, Thorndike, Troy, Unity, Waldo |  |  |  | 026776.00 | REGIONAL PROGRAM | KNOX AREA LCP | GENERAL CONTRACTOR VAUGHN D. THIBODEAU II |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
026794.00 | Benedicta Twp, Herseytown Twp, Macwahoc Plt, Mattawamkeag, Medway, North Yarmouth Academy Grant Twp, Reed Plt, Sherman, T1 R5 WELS, T1 R8 WELS, T1 R9 WELS, T3 Indian Purchase Twp, Upper Molunkus Twp, Woodville |  |  |  | 026794.00 | REGIONAL PROGRAM | SHERMAN AREA LCP | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
025519.00 | Benton, Burnham, Clinton, Fairfield, Oakland, Pittsfield, Waterville |  | 2551900 |  | 025519.00 | REGIONAL PROGRAM | WATERVILLE-PITTSFIELD INTERSTATE 95 NORTHBOUND ULTRA-THIN BO | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | MICHAEL LENKO | Shawn Smith |  | 05/01/2022 | 06/24/2023
026460.00 | Benton, Burnham, Clinton, Pittsfield |  | 2646000 |  | 026460.00 | REGIONAL PROGRAM | PITTSFIELD TO FAIRFIELD INTERSTATE 95 SOUTHBOUND UNTRA-THIN | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | MICHAEL LENKO | Shawn Smith |  | 05/08/2023 | 11/03/2023
025129.00 | Bethel |  | 2584500 |  | 025845.00 | REGIONAL PROGRAM | BETHEL, PARKWAY CYCLICAL PAVEMENT RECYCLING | PIKE INDUSTRIES, INC. |  | WYATT JOHNSON | Guy Whittington |  | 06/05/2022 | 10/27/2023
025129.00 | Bethel |  | 2591500 |  | 025915.00 | REGIONAL PROGRAM | BETHEL, ROUTE 26 3/4" OVERLAY | PIKE INDUSTRIES, INC. |  | WYATT JOHNSON | Guy Whittington |  | 06/27/2022 | 10/27/2023
018574.00 | Biddeford |  | STP-1857(400) |  | 018574.00 | MULTIMODAL PROGRAM | BIDDEFORD, INTERSECTION IMPROVEMENTS, RTE.9. | SHAW BROTHERS CONSTRUCTION, INC. |  | PAT ROMA | Brian Keezer |  | 04/28/2022 | 06/28/2024
025017.00 | Biddeford |  | 2596300 |  | 025963.00 | REGIONAL PROGRAM | BIDDEFORD, ROUTE 111 MILL AND FILL | GLIDDEN EXCAVATING & PAVING, INC. |  | NOAH FRENCH | Laray Hamilton |  | 07/31/2023 | 09/09/2023
025017.00 | Biddeford |  | 2501700 |  | 025017.00 | REGIONAL PROGRAM | BIDDEFORD, SOUTH STREET MILL AND FILL | GLIDDEN EXCAVATING & PAVING, INC. |  | NOAH FRENCH | Laray Hamilton |  | 07/31/2023 | 10/20/2023
025017.00 | Biddeford |  | 2595900 |  | 025959.00 | REGIONAL PROGRAM | BIDDEFORD, HILL STREET/LANDRY STREET MILL AND FILL | GLIDDEN EXCAVATING & PAVING, INC. |  | NOAH FRENCH | Laray Hamilton |  | 07/31/2023 | 09/08/2023
017712.00 | Blue Hill |  | STP-1771(200)X |  | 017712.00 | BRIDGE PROGRAM | BLUE HILL, FALLS BRIDGE REPLACEMENT OVER SALT POND OUTLET. | CIANBRO CORPORATION |  | JOHN KNOWLES | Andrew Lathe |  | 02/10/2022 | 08/08/2024
027322.00 | Blue Hill, Ellsworth, Surry |  |  |  | 027322.00 | REGIONAL PROGRAM | BLUE HILL AREA LCP | GENERAL CONTRACTOR VAUGHN D. THIBODEAU II |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
025932.00 | Boothbay |  | 025932.00 |  | 025932.00 | MAINTENANCE | BOOTHBAY RIVER ROAD INSTREAM CULVERT REPLACEMENTS | LITTLEFIELD’S CONSTRUCTION |  | MATT WHITCOMB | Brian Reeves |  | 06/06/2022 | 10/03/2022
025861.00 | Boothbay Harbor, Jefferson, Newcastle, Nobleboro, Union, Waldoboro, Warren, Westport Island, Whitefield, Wiscasset |  | 025861.00 |  | 025861.00 | REGIONAL PROGRAM | NEWCASTLE AREA LCP | HAGAR ENTERPRISES, INC. |  | BRIAN COOLEY | Timothy Pelotte |  | 05/10/2023 | 05/31/2024
021751.01 | Boothbay Harbor, Southport |  | 2309401 |  | 021751.01 | BRIDGE PROGRAM | SOUTHPORT - BOOTHBAY HBR, SOUTHPORT BR REHAB | CIANBRO CORPORATION |  | SAM STILWELL | Jason Stetson |  | 12/07/2022 | 06/06/2025
026772.00 | Bowdoin, Bowdoinham, Farmingdale, Gardiner, Hallowell, Litchfield, Mount Vernon, Readfield, Richmond |  |  |  | 026772.00 | REGIONAL PROGRAM | HALLOWELL AREA LCP | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
026340.00 | Bowdoin, Bowdoinham, Gardiner, Richmond, Topsham, West Gardiner |  | 2634200 |  | 026342.00 | REGIONAL PROGRAM | BRUNSWICK-WEST GARDINER INTERSTATE 295 NORTHBOUND ULTRA-TH | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  |  | Shawn Smith |  | 05/06/2024 | 10/26/2024
026340.00 | Bowdoin, Bowdoinham, Gardiner, Richmond, Topsham, West Gardiner |  | 2634000 |  | 026340.00 | REGIONAL PROGRAM | WEST GARDINER-BRUNSWICK INTERSTATE 295 SOUTHBOUND ULTRA-TH | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  |  | Shawn Smith |  | 05/06/2024 | 10/26/2024
028595.00 | Bowdoin, Litchfield, Richmond, Wales |  | 028595.00 |  | 028595.00 | MAINTENANCE | RICHMOND, LITCHFIELD AND WALES FORESTRY & CANOPY CLEARING | COMPREHENSIVE LAND TECHNOLOGIES |  | MATT WHITCOMB | Brian Reeves
026679.00 | Bowdoinham, China, Richmond, Vassalboro |  | 026679.00 |  | 026679.00 | MAINTENANCE | BOWDOINHAM, INSTREAM CULVERT REPLACEMENTS | PRATT & SONS, INC. |  | MATTHEW WHITCOMB | Jamie Andrews |  | 05/17/2021
026340.00 | Bowdoinham, Gardiner, West Gardiner |  | 2688400 |  | 026884.00 | BRIDGE PROGRAM | BOWDOINHAM & GARDINER, INTERSTATE 295 BRIDGES #1534, #1552, | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  |  | Travis Hamel |  | 05/06/2024 | 10/25/2024
025377.00 | Brewer |  | 2537700 |  | 025377.00 | REGIONAL PROGRAM | BREWER, ROUTE 15 MILL & FILL | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | JOSEPH GRAHAM | Randall Barrows |  | 05/06/2024 | 08/30/2024
018915.00 | Brewer, Eddington, Holden |  | 1891500 |  | 018915.00 | HIGHWAY PROGRAM | BREWER - EDDINGTON, NEW CONNECTOR CONSTRUCTION, I395/RTE.9 | SARGENT CORPORATION |  | JEFFERY COFFIN | Rhobe Moulton |  | 01/20/2022 | 07/18/2025
024783.01 | Bridgewater |  | 023094.01 |  | 024783.01 | BRIDGE PROGRAM | BRIDGEWATER, WHITNEY BROOK BR REPL | REED & REED, INC. |  | CAMERON SLAUENWHITE | Jason Stetson |  | 02/07/2023 | 05/20/2024
022835.10 | Brighton Plt |  |  |  | 022835.10 | REGIONAL PROGRAM | LARGE CULVERT REPLACEMENT- MATERIAL CONTRACT BRIGHTON PLT, | MICHIE CORPORATION |  |  | Guy Whittington
028702.00 | Bristol |  | 2870200 |  | 028702.00 | REGIONAL PROGRAM | BRISTOL ROUTE 32 EMERGENCY HIGHWAY REHABILITATION | HAGAR ENTERPRISES, INC. |  | WAYNE WATSON | Emory Lovely |  | 02/12/2024 | 04/20/2024
026766.00 | Brownfield, Cornish, Hiram, Limerick, Newfield, Parsonsfield, Porter |  |  |  | 026766.00 | REGIONAL PROGRAM | PARSONSFIELD AREA LCP | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
025831.00 | Brownfield, Fryeburg, Hiram |  | 2583100 |  | 025831.00 | REGIONAL PROGRAM | HIRAM-BROWNFIELD-FRYEBURG (ROUTE 5) CYCLICAL PAVEMENT RESURF | GLIDDEN EXCAVATING & PAVING, INC. |  | MATTHEW GUESS | Laray Hamilton |  | 05/29/2023 | 08/11/2023
026917.00 | Brunswick |  | 026917.00 |  | 026917.00 | MAINTENANCE | BRUNSWICK ROUTE 1 CULVERT REPLACEMENT | GORDON CONTRACTING INC. |  | SUZANNE NORTON | John Skelley |  | 06/21/2021
025151.00 | Brunswick |  | 025151.00 |  | 025151.00 | BRIDGE PROGRAM | RIVER ROAD BRIDGE (#6267) OVER INTERSTATE 295. LOCATED 0.22 | WYMAN & SIMPSON, INC. |  | DALTON THOMPSON | Brian Nichols |  | 03/19/2024 | 07/23/2024
022603.00 | Brunswick, Topsham |  | STP-2260(300) |  | 022603.00 | BRIDGE PROGRAM | BRUNSWICK - TOPSHAM, FRANK J WOOD BRIDGE REPLACEMENT. | REED & REED, INC. |  | DALTON THOMPSON | Mackenzie Kersbergen |  | 04/25/2023 | 11/15/2026
022641.00 | Buxton, Gorham, Hollis, Lyman |  | NHPP-2264(100) |  | 022641.00 | HIGHWAY PROGRAM | LYMAN-HOLLIS, BUXTON & GORHAM ROUTE 202 HIGHWAY RECONSTRUCTI | R. J. GRONDIN & SONS |  |  | Douglas Coombs |  | 12/25/2023 | 06/12/2025
026788.00 | Cambridge, Corinna, Dexter, Harmony, Hartland, Newport, Palmyra, Pittsfield, Ripley, Saint Albans |  |  |  | 026788.00 | REGIONAL PROGRAM | PITTSFIELD AREA LCP | MICHAEL HOPKINS DBA HOPKINS LANDSCAPING, HOPKINS PAVING |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
025095.00 | Camden |  | 2509500 |  | 025095.00 | BRIDGE PROGRAM | RAWSON AVENUE BRIDGE (#3173) OVER MEGUNTICOOK RIVER. LOCATED | DANIELL FORD ENTERPRISES AKA FORD ENTERPRISES |  |  | Devan Eaton |  | 01/08/2025 | 06/09/2025
022608.00 | Camden |  | NHPP-2260(800) |  | 022608.00 | BRIDGE PROGRAM | CAMDEN, SPRING BROOK BR REPL | REED & REED, INC. |  |  | Andrew Lathe |  | 11/08/2023 | 07/14/2025
018283.10 | Camden, Lincolnville |  | 1828310 |  | 018283.10 | HIGHWAY PROGRAM | CAMDEN - FORESTRY CLEARING | COMPREHENSIVE LAND TECHNOLOGIES |  |  | Douglas Coombs |  | 10/10/2023 | 03/31/2024
029333.00 | Canton |  | 029333.00 |  | 029333.00 | MAINTENANCE | CANTON CULVERT LINING | VORTEX SERVICES LLC DBA TED BERRY CO. |  | BOB BOULAY | ?
027318.00 | Caribou |  | 2731800 |  | 027318.00 | REGIONAL PROGRAM | CARIBOU, ROUTE 164 CYCLICAL PAVEMENT RESURFACING | SODERBERG COMPANY, INC. |  |  | Roger Soucy |  | 05/13/2024 | 09/20/2024
018984.00 | Caribou |  | 018984.00 |  | 018984.00 | BRIDGE PROGRAM | CARIBOU, BRIDGE BIN WALL REPLACEMENT | BMB CONSTRUCTION LLC |  | RESIDENT? | Michael Wight |  | 12/04/2023 | 09/30/2024
026790.00 | Caribou, Chapman, Cross Lake Twp, Fort Fairfield, Limestone, Mapleton, Presque Isle, Saint Agatha |  |  |  | 026790.00 | REGIONAL PROGRAM | CARIBOU AREA LCP | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
021696.00 | Caribou, Limestone |  | STP-2169(600) |  | 021696.00 | BRIDGE PROGRAM | CARIBOU - LIMESTONE, GREENLAW BRK NO.2 BR REPL | MCGILLAN, INC. |  | CHARLES BARNARD | Jason Stetson |  | 06/03/2024 | 11/18/2024
027732.00 | Caribou, Limestone |  | 2773600 |  | 027736.00 | REGIONAL PROGRAM | CARIBOU - LIMESTONE, ROUTE 89 ULTRA-THIN BONDED WEARING CO | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Roger Soucy |  | 06/03/2024 | 10/11/2024
028680.00 | Carrabassett Valley |  | 2868200 |  | 028682.00 | REGIONAL PROGRAM | EMERGENCY REPAIR CARRABASSETT VALLEY ROUTE 16/27 BRIDGE #534 | JORDAN EXCAVATION AKA JORDAN LUMBER COMANY |  | ROBERT LAROCHE | Emory Lovely |  | 12/28/2023 | 06/01/2024
026818.10 | Cherryfield, Deblois |  | 026818.10 |  | 026818.10 | REGIONAL PROGRAM | CHERRYFIELD - DEBLOIS, ROUTE 193 HIGHWAY REHABILITATION | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | HARVEY SMITH | Randall Barrows |  | 08/14/2023 | 06/29/2024
027330.00 | Chesterville, Farmington, Jay, Wilton |  |  |  | 027330.00 | REGIONAL PROGRAM | WILTON AREA LCP | GENERAL CONTRACTOR VAUGHN D. THIBODEAU II |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
022296.01 | Chesterville, Farmington, Jim Pond Twp, Wilton |  | 2229601 |  | 022296.01 | BRIDGE PROGRAM | FRANKLIN COUNTY BRIDGE NUMBER 2273, 3265, 2341 BRIDGE REPL. | WYMAN & SIMPSON, INC. |  | MICHAEL PELLETIER | Michael Wight |  | 11/15/2021 | 10/04/2024
026959.00 | China, Vassalboro |  | 026959.00 |  | 026959.00 | MAINTENANCE | VASSALBORO & CHINA, INSTREAM CULVERT REPLACEMENTS | LITTLEFIELD’S CONSTRUCTION |  | MATTHEW WHITCOMB | Jamie Andrews |  | 06/15/2021 | 07/16/2021
024211.00 | Clifton, Monson, Prospect |  | 024211.00 |  | 024211.00 | MULTIMODAL PROGRAM | STATEWIDE, ROAD WEATHER INFORMATION SYSTEM REPLACEMENT | CAMPBELL SCIENTIFIC, INC. |  | KAREN LIBBY | Daniel Loring |  | 01/08/2024 | 03/29/2024
026486.00 | Columbia, Columbia Falls, Jonesboro |  | 2648600 |  | 026486.00 | REGIONAL PROGRAM | COLUMBIA - JONESBORO, US ROUTE 1 COLD IN-PLACE RECYCLED | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | WILLIAM BROWN | Randall Barrows |  | 08/02/2023 | 06/29/2024
028680.00 | Coplin Plt |  | 2868000 |  | 028680.00 | REGIONAL PROGRAM | EMERGENCY REPAIR COPLIN PLANTATION ROUTE 16 BRIDGE #3070 WIN | JORDAN EXCAVATION AKA JORDAN LUMBER COMANY |  | ROBERT LAROCHE | Emory Lovely |  | 12/28/2023 | 06/01/2024
023263.10 | Coplin Plt |  | 023263.10 |  | 023263.10 | REGIONAL PROGRAM | COPLIN PLANTATION CONCRETE BOX CUVERT PREBUY | SUPERIOR CONCRETE CO., INC. |  |  | Guy Whittington
022847.00 | Cornish |  |  |  | 022847.00 | BRIDGE PROGRAM | CORNISH, LITTLE RIVER BRIDGE (#2465) SLOPE STABILIZATION | JOE GAMMON AND SONS EXCAVATION LLC AKA JOE GAMMON |  |  | Brian Nichols |  | 01/31/2024 | 09/11/2024
027730.00 | Cross Lake Twp, Fort Kent, New Canada |  | 2773000 |  | 027730.00 | REGIONAL PROGRAM | CROSS LAKE TWP - NEW CANADA - FORT KENT, ROUTE 161 3/4" SHI | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Roger Soucy |  | 06/03/2024 | 10/11/2024
024153.00 | Damariscotta, Newcastle |  | 2528900 |  | 025289.00 | BRIDGE PROGRAM | EDGECOMB AND NEWCASTLE, U.S. ROUTE 1 BRIDGE JOINTS | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  | DEAN ROWLANDS | Travis Hamel |  | 05/01/2023 | 10/27/2023
024153.00 | Damariscotta, Newcastle, Nobleboro |  | 2544500 |  | 025445.00 | REGIONAL PROGRAM | NEWCASTLE-NOBLEBORO, US ROUTE1 MILL AND FILL | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  | DEAN ROWLANDS | Robert K Betz |  | 06/26/2022 | 06/30/2024
023551.00 | Dayton |  |  |  | 023551.00 | REGIONAL PROGRAM | DAYTON, ROUTE 5 LARGE CULVERT REHABILITATION | CULVERT REHABILITATION SERVICES (DIV. OF CLH & SON) |  |  | Laray Hamilton |  | 07/15/2024 | 10/05/2024
025297.00 | Deblois |  | 2529700 |  | 025297.00 | BRIDGE PROGRAM | DEBLOIS BRIDGE (#3152) OVER NARRAGUAGUS RIVER. LOCATED 0.14 | BMB CONSTRUCTION LLC |  |  | Mark Parlin |  | 02/21/2024 | 07/24/2024
025393.00 | Denmark |  |  |  | 025393.00 | REGIONAL PROGRAM | DENMARK, ROUTE 117 LARGE CULVERT REPLACEMENT | BALDWIN & SON, LLC AKA SKID STEER SERVICES |  |  | Laray Hamilton |  | 06/03/2024 | 07/31/2024
027459.00 | Dixfield |  | 027549.00 |  | 027459.00 | MAINTENANCE | DIXFIELD SALT STORAGE BUILDING | SUNKAZE PROJECT SOLUTIONS, INC. |  | BOB BOULAY | Joe Tedford |  | 05/02/2022 | 09/02/2022
027324.00 | Dixmont, Newburgh |  | 2732400 |  | 027324.00 | REGIONAL PROGRAM | DIXMONT - NEWBURGH US ROUTE 202, CYCLICAL PAVEMENT RESURFACI | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Randall Barrows |  | 04/10/2024 | 10/24/2024
023680.00 | Dover-Foxcroft |  | 023680.00 |  | 023680.00 | MAINTENANCE | DOVER-FOXCROFT, LARGE CULVERT REPLACEMENT | GORDON CONTRACTING INC. |  | MATTHEW CONNOR | John Devin |  | 07/13/2020
022421.00 | Dresden |  | 023906.00 |  | 023906.00 | MAINTENANCE | DRESDEN CULVERT REPLACEMENT | PRATT & SONS, INC. |  | MATT WHITCOMOB | Brian Reeves |  | 07/15/2021 | 09/30/2021
022421.00 | Dresden |  | 023906.00 |  | 023912.00 | MAINTENANCE | DRESDEN CULVERT REPLACEMENT | PRATT & SONS, INC. |  | MATT WHITCOMB | Brian Reeves |  | 07/15/2021 | 09/30/2021
022421.00 | Dresden |  | 023830.00 |  | 023830.00 | MAINTENANCE | DRESDEN CULVERT REPLACEMENT | PRATT & SONS, INC. |  | MATT WHITCOMB | Brian Reeves |  | 07/15/2021 | 09/30/2021
023657.00 | Durham |  | 2365700 |  | 023657.00 | BRIDGE PROGRAM | DURHAM, TRACY BROOK BRIDGE REPLACEMENT | SHAW BROTHERS CONSTRUCTION, INC. |  | MARK SMITH | Devan Eaton |  | 03/31/2023 | 02/09/2026
026764.00 | Durham, Freeport |  |  |  | 027352.00 | REGIONAL PROGRAM | CUMBERLAND AREA LCP | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Timothy Pelotte |  | 04/29/2024 | 10/05/2024
026792.00 | Dyer Brook, Houlton, Island Falls, Linneus, Littleton, Ludlow, Merrill, New Limerick, Smyrna |  |  |  | 026792.00 | REGIONAL PROGRAM | HOULTON AREA LCP | STEELSTONE INDUSTRIES, INC.AKA MCQUADE & TIDD |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
026486.00 | East Machias, Machias |  | 2663005 |  | 026630.05 | REGIONAL PROGRAM | MACHIAS - EAST MACHIAS, US ROUTE 1 COLD IN-PLACE RECYCLED | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | WILLIAM BROWN | Randall Barrows |  | 08/02/2023 | 06/29/2024
024153.00 | Edgecomb, Wiscasset |  | 2528300 |  | 025283.00 | REGIONAL PROGRAM | WISCASSET AND EDGECOMB, US ROUTE 1 MILL & FILL | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  | DEAN ROWLANDS | Robert K Betz |  | 06/26/2022 | 06/30/2024
027911.00 | Eliot |  | 027911.00 |  | 027911.00 | MAINTENANCE | ELIOT 145 BEECH ROAD CULVERT REPLACEMENT | PRATT & SONS, INC. |  | ROB BETZ | John Skelley |  | 07/15/2022 | 09/01/2022
025461.00 | Ellsworth |  | 2546100 |  | 025461.00 | HIGHWAY PROGRAM | ELLSWORTH ROUTE 1A - INTERSECTION IMPROVEMENTS | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Rhobe Moulton |  | 04/08/2024 | 11/15/2024
027726.00 | Ellsworth, Orland |  | 2772600 |  | 027726.00 | REGIONAL PROGRAM | ORLAND-ELLSWORTH, US ROUTE 1 ULTRA-THIN BONDED WEARING COUR | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Randall Barrows |  | 06/03/2024 | 09/20/2024
025143.00 | Ellsworth, Trenton |  | 2673000 |  | 026730.00 | REGIONAL PROGRAM | ELLSWORTH-TRENTON, ROUTE 3 ULTRA-THIN BONDED WEARING COURSE | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | CARMEN FORZETTING | Randall Barrows |  | 06/11/2023 | 11/03/2023
021720.00 | Falmouth |  | HSIP-2267(200) |  | 022672.00 | BRIDGE PROGRAM | FALMOUTH, I295 NB RAMP/BUCKNAM | WYMAN & SIMPSON, INC. |  | CLINTON SMITH | Devan Eaton |  | 08/16/2022 | 07/24/2024
021720.00 | Falmouth |  | 021720.00 |  | 021720.00 | BRIDGE PROGRAM | FALMOUTH, BUCKNAM ROAD BRIDGE REPL | WYMAN & SIMPSON, INC. |  | CLINTON SMITH | Devan Eaton |  | 08/16/2022 | 07/16/2024
021720.00 | Falmouth |  | 021721.00 |  | 021721.00 | BRIDGE PROGRAM | FALMOUTH, JOHNSON ROAD BRIDGE REPL | WYMAN & SIMPSON, INC. |  | CLINTON SMITH | Devan Eaton |  | 08/16/2022 | 07/16/2024
023767.04 | Falmouth, Freeport, Houlton, Saco, Scarborough |  | 02376704 |  | 023767.04 | TRAFFIC | IMPLEMENTATION OF ITS, TRAVEL TIME SIGNS | LIDDELL BROTHERS, INC. |  | LEWIS BENNER | Stephen Landry
026242.00 | Falmouth, Gray, Norway, Oxford, Portland |  | 2624400 |  | 026244.00 | MULTIMODAL PROGRAM | STATEWIDE: INSTALLATION OF SIGNAL BACKPLATES ON ROUTE 26 | ELECTRIC LIGHT CO. INC. |  |  | Gerald Dostie |  | 06/03/2024 | 12/31/2024
025427.00 | Farmington |  | 025427.00 |  | 025427.00 | MAINTENANCE | FARMINGTON CULVERT SLIP LINE | J. R. NUNES & SONS EXCAVATION, INC. |  | TIM ANDREWS | Tony Beaulieu |  | 07/10/2023 | 11/01/2023
027330.00 | Farmington, Jay, Wilton |  |  |  | 027334.00 | REGIONAL PROGRAM | WILTON AREA LCPP | GENERAL CONTRACTOR VAUGHN D. THIBODEAU II |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
027730.00 | Fort Fairfield |  | 2773800 |  | 027738.00 | REGIONAL PROGRAM | FORT FAIRFIELD US ROUTE 1A 3/4" SHIM AND OVERLAY | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Roger Soucy |  | 06/03/2024 | 10/11/2024
021724.00 | Fort Fairfield |  | 021724.00 |  | 021724.00 | BRIDGE MAINT. | FORT FAIRFIELD - BRIDGE PAINTING | GEMSTONE, LLC |  | JAMES BALL | ? |  | 09/20/2017 | 10/23/2017
027318.00 | Fort Fairfield, Presque Isle |  | 2732000 |  | 027320.00 | REGIONAL PROGRAM | PRESQUE ISLE-FORT FAIRFIELD, ROUTES 167, 10, & US ROUTE 1A | SODERBERG COMPANY, INC. |  |  | Roger Soucy |  | 05/13/2024 | 09/20/2024
021882.00 | Fort Kent |  | STP-2188(200) |  | 021882.00 | BRIDGE PROGRAM | FORT KENT, PERLEY BROOK BRIDGE REPLACEMENT. | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | CHARLES BARNARD | Jason Stetson |  | 07/05/2022 | 10/10/2023
022861.00 | Fort Kent |  | 2286300 |  | 022863.00 | MULTIMODAL PROGRAM | FORT KENT, TRAFFIC SIGNAL REPLACEMENT, ROUTE 1 AT ROUTE 161 | ED PELLETIER & SONS, CO. |  |  | Aurele Gorneau Ii |  |  | 11/29/2024
022861.00 | Fort Kent |  | 2286100 |  | 022861.00 | MULTIMODAL PROGRAM | FORT KENT, TRAFFIC SIGNAL REPLACEMENT, ROUTE 1 AT ROUTE 11 | ED PELLETIER & SONS, CO. |  |  | Aurele Gorneau Ii |  |  | 11/29/2024
024899.00 | Fort Kent, Frenchville |  | 024899.00 |  | 024899.00 | MULTIMODAL PROGRAM | RAILROAD SLOPE STABILIZATION IN FORT KENT AND FRENCHVILLE | ED PELLETIER & SONS, CO. |  | LEWIS BENNER | Mackenzie Kersbergen |  | 04/24/2023 | 11/01/2023
021726.01 | Freeport |  | 021726.01 |  | 021726.01 | BRIDGE PROGRAM | FREEPORT, APPROACH ROAD BR AND MERRILL ROAD BR REPL. | MCNAMEE CONSTRUCTION CORP. |  | BEN WALZ | Devan Eaton |  | 05/16/2022 | 11/14/2024
025151.00 | Freeport |  | 025291.00 |  | 025291.00 | BRIDGE PROGRAM | COUNTY ROAD/I-295 BRIDGE (#0585) OVER INTERSTATE 295. LOCATE | WYMAN & SIMPSON, INC. |  | DALTON THOMPSON | Brian Nichols |  | 03/19/2024 | 07/23/2024
022202.00 | Frenchboro |  | 2220200 |  | 022202.00 | MULTIMODAL PROGRAM | FRENCHBORO, FENDER SYSTEM CONSTRUCTION | PROCK MARINE COMPANY |  | ANTHONY JACQUES | Aurele Gorneau Ii |  | 04/25/2022 | 04/30/2024
027732.00 | Frenchville |  | 2773200 |  | 027732.00 | REGIONAL PROGRAM | FRENCHVILLE, US ROUTE 1 ULTRA-THIN BONDED WEARING COURSE | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Roger Soucy |  | 06/03/2024 | 10/11/2024
027732.00 | Frenchville |  | 2774000 |  | 027740.00 | REGIONAL PROGRAM | FRENCHVILLE US ROUTE 1 ULTRA-THIN BONDED WEARING COURSE | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Roger Soucy |  | 06/03/2024 | 10/11/2024
025301.00 | Gardiner, Randolph |  | 2530100 |  | 025301.00 | BRIDGE PROGRAM | GARDINER-RANDOLPH, PEARL HARBOR REMEMBRANCE BR WEAR SURF | WYMAN & SIMPSON, INC. |  | SETH WILLS | Devan Eaton |  | 09/12/2023 | 08/28/2024
026772.00 | Gardiner, Waterville |  |  |  | 027338.00 | REGIONAL PROGRAM | HALLOWELL AREA LCP | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
028690.00 | Grafton Twp, Newry |  | 2869000 |  | 028690.00 | REGIONAL PROGRAM | EMERGENCY REPAIR NEWRY-GRAFTON PLT, ROUTE 26 WIN 28690.00 | SHAW BROTHERS CONSTRUCTION, INC. |  | SHANE AMOROSO | Emory Lovely |  | 12/28/2023 | 06/01/2024
027732.00 | Grand Isle, Madawaska |  | 2773400 |  | 027734.00 | REGIONAL PROGRAM | GRAND ISLE - MADAWASKA US ROUTE 1 ULTRA-THIN BONDED WEARING | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Roger Soucy |  | 06/03/2024 | 10/11/2024
021727.01 | Greenbush |  | 2309401 |  | 021727.01 | BRIDGE PROGRAM | GREENBUSH, BOOM BRIDGE REPL | WYMAN & SIMPSON, INC. |  | RALPH PERKINS | Michael Wight |  | 12/06/2022 | 06/03/2024
029233.00 | Greene |  | 029233.00 |  | 029233.00 | MAINTENANCE | GREENE, LARGE CULVERT REPLACEMENT | T BUCK CONSTRUCTION, INC. |  | MATTEW WHITCOMB | ?
026975.00 | Greenville |  | 026975.00 |  | 026975.00 | MAINTENANCE | GREENVILLE CULVERT SLIPLINE | CULVERT REHABILITATION SERVICES (DIV. OF CLH & SON) |  | TIM ANDREWS | Mark Hume |  | 06/07/2021 | 10/01/2021
029533.00 | Greenwood |  | 029533.00 |  | 029533.00 | MAINTENANCE | GREENWOOD | SHAW BROTHERS CONSTRUCTION, INC. |  | ROBERT BOULAY JR | ? |  | 10/17/2023
025129.00 | Greenwood, Woodstock |  | 2512900 |  | 025129.00 | REGIONAL PROGRAM | WOODSTOCK-GREENWOOD, ROUTE 26 1 1/4" OVERLAY | PIKE INDUSTRIES, INC. |  | WYATT JOHNSON | Guy Whittington |  | 06/27/2022 | 10/27/2023
025463.00 | Hallowell |  | 2546300 |  | 025463.00 | BRIDGE PROGRAM | HALLOWELL, VAUGHN MEMORIAL BRIDGE REHAB | SCOTT CONSTRUCTION CORPORATION |  |  | Devan Eaton |  | 10/18/2023 | 08/07/2024
022581.10 | Hampden, Newburgh |  | 22581.55 |  | 022581.55 | MAINTENANCE | HAMPDEN NEWBURGH, RT. 69, STATE PUGMILL | MICHAEL HOPKINS DBA HOPKINS LANDSCAPING, HOPKINS PAVING |  | CARMEN FORZETTING | ? |  | 05/02/2022 | 08/31/2022
026712.00 | Hanover, Rumford |  | 2671200 |  | 026712.00 | REGIONAL PROGRAM | HANOVER-RUMFORD, US ROUTE 2 ULTRA-THIN BONDED WEARING COURSE | PIKE INDUSTRIES, INC. |  | WYATT JOHNSON | Guy Whittington |  | 06/01/2023 | 09/29/2023
028708.00 | Harpswell |  | 2870800 |  | 028708.00 | BRIDGE PROGRAM | Harpswell, Bailey Island Br Emergency Response | NEW ENGLAND INFRASTRUCTURE INC. |  |  | Michael Wight |  | 04/17/2024 | 05/18/2024
023198.00 | Harrison |  | 2319800 |  | 023198.00 | BRIDGE PROGRAM | HARRISON, BEAR RIVER BR WEAR SURF REPL AND SUBSTRUCTURE REHA | SCOTT CONSTRUCTION CORPORATION |  |  | Gerald.G. Libbyjr |  | 10/16/2023 | 12/25/2024
028686.00 | Highland Plt, Lexington Twp |  | 2868600 |  | 028686.00 | REGIONAL PROGRAM | EMERGENCY REPAIR LEXINGTON TWPT, LONG FALLS DAM ROAD WIN 286 | PRATT & SONS, INC. |  | TIM STORER | Emory Lovely |  | 01/02/2024 | 06/01/2024
026021.00 | Hollis |  | 2602100 |  | 026021.00 | MULTIMODAL PROGRAM | HOLLIS, TRAFFIC SIGNAL AT ROUTE 202 AND ROUTE 35 | DAGLE ELECTRICAL CONSTRUCTION CORP. |  | KAREN LIBBY | Gerald Dostie |  | 10/17/2023 | 07/31/2024
028437.00 | Houlton |  | 028437.00 |  | 028437.00 | MAINTENANCE | HOULTON, MAINTENANCE FACILITY PAVING | STEELSTONE INDUSTRIES, INC.AKA MCQUADE & TIDD |  | KEVIN BUTLER | ?
028439.00 | Houlton |  | 028439.00 |  | 028439.00 | MAINTENANCE | HOULTON INSTALLATION OF SEWER LINE & DRAIN LINE WITH WATER/O | STEELSTONE INDUSTRIES, INC.AKA MCQUADE & TIDD |  | KEVIN BULTER | ?
026998.00 | Houlton |  | 026998.00 |  | 026998.00 | REGIONAL PROGRAM | HOULTON, US ROUTE 1 MILL & FILL | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | JON BITHER | Roger Soucy |  | 08/02/2023 | 06/28/2024
023454.00 | Houlton |  | 24345.00 |  | 024345.00 | MULTIMODAL PROGRAM | HOULTON ,RAILROAD BRIDGE REHABILITATION | CPM CONSTRUCTORS |  | LEWIS BENNER | Nathaniel Benoit |  | 02/09/2022 | 12/27/2023
022885.00 | Houlton |  | 2288500 |  | 022885.00 | MULTIMODAL PROGRAM | HOULTON, TRAFFIC SIGNAL REPLACEMENT, ROUTE 1 AT ROUTE 2 | FRAZIER SIGNAL TECHNOLOGIES LLC |  |  | Daniel Loring |  | 04/15/2024 | 06/27/2025
025525.00 | Houlton, Ludlow, New Limerick, Oakfield, Smyrna |  | 2552500 |  | 025525.00 | REGIONAL PROGRAM | HOULTON-DYER BROOK, INTERSTATE 95 SOUTHBOUND ULTRA-THIN BOND | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | JON BITHER | Shawn Smith |  | 07/10/2023 | 06/29/2024
025087.00 | Howland |  | 2508700 |  | 025087.00 | BRIDGE PROGRAM | HOWLAND, I-95 SB/PISCATAQUIS RIVER BR 6069 | OLYMPUS PAINTING CONTRACTORS, INC. |  | TIMOTHY HEBERT | Devin Anderson |  | 07/11/2022 | 11/30/2024
025087.00 | Howland |  | 2554300 |  | 025543.00 | BRIDGE PROGRAM | HOWLAND, I-95 NB/PISCATAQUIS RIVER BR 1419 | OLYMPUS PAINTING CONTRACTORS, INC. |  | TIMOTHY HEBERT | Devin Anderson |  | 07/11/2022 | 11/30/2024
025087.00 | Howland |  | 2553500 |  | 025535.00 | BRIDGE PROGRAM | HOWLAND, ROUTE 155/ I-95 BR 6068 | OLYMPUS PAINTING CONTRACTORS, INC. |  | TIMOTHY HEBERT | Devin Anderson |  | 07/11/2022 | 11/30/2024
026774.00 | Islesboro |  | 026774.00 |  | 026774.00 | REGIONAL PROGRAM | ISLEBORO AREA LCP | HAGAR ENTERPRISES, INC. |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
026973.00 | Jay |  | 026973.00 |  | 026973.00 | MAINTENANCE | JAY CULVERT SLIP LINE | VORTEX SERVICES LLC DBA TED BERRY CO. |  | TIM ANDREWS | Mark Hume |  | 06/20/2022 | 09/30/2022
023759.10 | Jefferson |  | 024197.10 |  | 024197.10 | REGIONAL PROGRAM | JEFFERSON RTE 126 | HAGAR ENTERPRISES, INC. |  | QUINN WARREN | Robert K Betz |  | 08/21/2023 | 05/11/2024
026770.00 | Jefferson, Waldoboro |  |  |  | 027340.00 | REGIONAL PROGRAM | BRISTOL AREA LCP | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
023629.00 | Kennebunk |  | 2362900 |  | 023629.00 | BRIDGE PROGRAM | KENNEBUNK, NASH MILL BRIDGE #5756 DECK REPL | WYMAN & SIMPSON, INC. |  |  | Devan Eaton |  | 04/18/2024 | 12/04/2024
023188.00 | Kennebunk, Wells |  |  |  | 023188.00 | BRIDGE PROGRAM | BRANCH BROOK BRIDGE (#3091) OVER BRANCH BROOK. LOCATED ON TH | SCOTT CONSTRUCTION CORPORATION |  |  | Brian Nichols |  | 10/16/2024 | 11/26/2025
016710.01 | Kittery |  | 2415100 |  | 024151.00 | REGIONAL PROGRAM | KITTERY, US ROUTE 1 MILL AND FILL | PIKE INDUSTRIES, INC. |  | TYLER FENTON | Laray Hamilton |  | 07/24/2022 | 06/30/2023
016710.01 | Kittery |  | 016710.01 |  | 016710.01 | MAINTENANCE | KITTERY, US ROUTE 1 BYPASS INTERSECTION IMPROVEMENTS WITHOUT | PIKE INDUSTRIES, INC. |  | TYLER FENTON | John Skelley |  | 07/24/2022 | 06/30/2023
018653.00 | Kittery |  | NHPP-1865(300) |  | 018653.00 | MULTIMODAL PROGRAM | KITTERY: SAFETY IMPROVEMENTS ON 0.47 MILE OF ROUTE 103 | GLIDDEN EXCAVATING & PAVING, INC. |  |  | Brian Keezer |  | 05/01/2024 | 11/29/2024
016710.01 | Kittery |  | 026624.10 |  | 026624.10 | REGIONAL PROGRAM | KITTERY, VISITOR INFORMATION RAMPS I-95 NB MILL & FILL | PIKE INDUSTRIES, INC. |  | TYLER FENTON | Shawn Smith |  | 07/24/2022 | 06/30/2023
023121.00 | Knox |  | 023121.00 |  | 023121.00 | MAINTENANCE | KNOX, CULVERT REPLACEMENTS | F C WORK & SONS, INC. |  | MATT WHITCOMB | Brian Reeves |  | 07/18/2022 | 09/30/2022
025955.01 | Lebanon |  | 025955.04 |  | 025955.04 | MULTIMODAL PROGRAM | LEBANON: MODIFY TRAFFIC SIGNAL AT RT. 202 AND DEPOT RD. | DAGLE ELECTRICAL CONSTRUCTION CORP. |  | KAREN LIBBY | Mackenzie Kersbergen |  | 01/22/2024 | 11/06/2024
027098.10 | Levant |  | 2709810 |  | 027098.10 | BRIDGE PROGRAM | LEVANT, STRUCTURAL STEEL | HIGH STEEL STRUCTURES, INC. |  |  | Jason Stetson |  | 11/29/2023 | 09/30/2024
022018.00 | Lincoln |  | 2201800 |  | 022018.00 | MULTIMODAL PROGRAM | LINCOLN, RECONSTRUCT SIDEWALK ON ROUTE 2 | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | TRAVIS SOUTHWICK | Daniel Loring |  | 08/28/2023 | 06/14/2024
014862.00 | Lisbon |  | STP-1486(200)X |  | 014862.00 | HIGHWAY PROGRAM | LISBON, HIGHWAY RECONSTRUCTION, RTE.125 | MCGEE CONSTRUCTION |  | SHANE AMOROSO | Ernest Martin |  | 04/01/2022 | 11/17/2023
028467.00 | Litchfield, Richmond |  |  |  | 028467.00 | MAINTENANCE | RICHMOND/LITCHFIELD CULVERT REPLACEMENTS | PRATT & SONS, INC. |  |  | Brian Reeves |  | 07/17/2023 | 09/30/2023
025127.00 | Livermore Falls |  | 2512700 |  | 025127.00 | REGIONAL PROGRAM | LIVERMORE FALLS ROUTE 133 1 1/4" OVERLAY | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  | TIM STORER | Guy Whittington |  | 07/19/2023 | 10/13/2023
026786.00 | Machias, Marshfield, Northfield, Wesley, Whitneyville |  |  |  | 028518.00 | REGIONAL PROGRAM | MACHIAS-WESLEY PUGMILL | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Timothy Pelotte |  | 04/29/2024 | 10/12/2024
022250.00 | Macwahoc Plt |  | 2225000 |  | 022250.00 | BRIDGE PROGRAM | MACWAHOC PLT, KINGMAN ROAD BR REPL | CPM CONSTRUCTORS |  |  | Mark Parlin |  | 05/22/2024 | 12/18/2024
021736.00 | Madawaska |  | 2173600 |  | 021736.00 | BRIDGE PROGRAM | MADAWASKA - EDMUNDSTON NEW BRUNSWICK CANADA, INTL BR | REED & REED, INC. |  | PHIL ROBERTS | Andrew Lathe |  | 05/24/2021 | 07/28/2025
023454.00 | Mapleton |  | 23456.00 |  | 023456.00 | MULTIMODAL PROGRAM | MAPLETON, RAILROAD BRIDGE REHABILITATION | CPM CONSTRUCTORS |  | LEWIS BENNER | Nathaniel Benoit |  | 02/09/2022 | 11/01/2023
025211.00 | Marion Twp |  | 2521100 |  | 025211.00 | BRIDGE PROGRAM | MARION TWP, CLIFFORD BR REPL | SARGENT CORPORATION |  |  | Mark Parlin |  | 05/30/2024 | 11/28/2024
027061.00 | Masardis |  | 027061.00 |  | 027061.00 | MAINTENANCE | MASARDIS SQUA PAN BRIDGE SCOUR COUNTERMEASURES | J. MCLAUGHLIN CONSTRUCTION, LLC |  | KEVIN BUTLER | Brent Bubar
024897.10 | Matinicus Isle Plt, Muscle Ridge Twp, Owls Head, Rockland, Vinalhaven |  | 024897.10 |  | 024897.10 | MULTIMODAL PROGRAM | MATINICUS ISLAND, NEW FERRY BOAT CONSTRUCTION | STEINER SHIPYARD INC. |  | GEORGE DEAN | Mackenzie Kersbergen |  | 09/06/2022 | 06/30/2024
022922.00 | Mattawamkeag |  | 2292200 |  | 022922.00 | REGIONAL PROGRAM | MATTAWAMKEAG LARGE CULVERT REPLACEMENT | LEE'S GENERAL TRUCKING AKA EMERY LEE & SONS, INC. |  |  | Roger Soucy |  | 04/22/2024 | 10/31/2024
025285.00 | Mechanic Falls, Poland |  | 2669600 |  | 026696.00 | REGIONAL PROGRAM | POLAND-MECHANIC FALLS ULTRA THIN BONDED WEARING COURSE ROUTE | PRATT & SONS, INC. |  | JARROD GOOGINS | Laray Hamilton |  | 06/12/2023 | 09/23/2023
025631.01 | Medway |  | 2563100 |  | 025631.01 | BRIDGE PROGRAM | MEDWAY, I-95 SB VDM BR 1410 DECK REPL | NEW ENGLAND INFRASTRUCTURE INC. |  |  | Julie Brask |  | 03/25/2024 | 06/30/2028
025631.01 | Medway |  | 2563100 |  | 025631.04 | BRIDGE PROGRAM | MEDWAY, I-95 SB RT 116 BR 1411 DECK REPL | NEW ENGLAND INFRASTRUCTURE INC. |  |  | Julie Brask |  | 03/25/2024 | 06/30/2028
025631.01 | Medway |  | 2563100 |  | 025631.05 | BRIDGE PROGRAM | MEDWAY, I-95 SB RT 116 BR 1411 DECK REPL | NEW ENGLAND INFRASTRUCTURE INC. |  |  | Julie Brask |  | 03/25/2024 | 06/30/2028
025631.01 | Medway |  | 2563100 |  | 025631.03 | BRIDGE PROGRAM | MEDWAY, RT 157 / I-95 IC BR 6141 DECK REPL | NEW ENGLAND INFRASTRUCTURE INC. |  |  | Julie Brask |  | 03/25/2024 | 06/30/2028
027680.23 | Medway |  |  |  | 027680.23 | TRAFFIC | MEDWAY, CONTINOUS COUNT STATION | AMPIRE ELECTRIC |  |  | Kirsten Mcgowan
025631.01 | Medway |  | 2563100 |  | 025631.02 | BRIDGE PROGRAM | MEDWAY, I-95 NB VDM BR 6078 DECK REPL | NEW ENGLAND INFRASTRUCTURE INC. |  |  | Julie Brask |  | 03/25/2024 | 06/30/2028
021700.01 | Mexico, Rumford |  | 2189401 |  | 021700.01 | BRIDGE PROGRAM | RUMFORD - MEXICO, RED BRIDGE REPLACEMENT | CPM CONSTRUCTORS |  | CATHERINE METTEY | Michael Wight |  | 09/12/2023 | 11/12/2026
020502.01 | Milo |  | 2309401 |  | 020502.01 | BRIDGE PROGRAM | MILO, OLD TOLL BRIDGE REPLACEMENT | REED & REED, INC. |  | ERIC VALCOURT | Michael Wight |  | 10/24/2022 | 04/26/2024
028225.00 | Montville |  | 028227.00 |  | 028227.00 | MAINTENANCE | MONTVILLE CRUSHING AND BLENDING RECYCLED ASPHALT PAVEMENT | SUPERIOR CRUSHING, INC. |  | MATT WHITCOMB | Jamie Andrews |  | 06/30/2022
025958.00 | Montville |  | 025958.00 |  | 025958.00 | MAINTENANCE | MONTVILLE, CULVERT REPLACEMENTS | LITTLEFIELD’S CONSTRUCTION |  | MATT WHITCOMB | Jamie Andrews |  | 09/07/2021 | 09/30/2021
025285.00 | New Gloucester, Poland |  | 2528500 |  | 025285.00 | REGIONAL PROGRAM | NEW GLOUCESTER -POLAND, ROUTE 122 1 1/4" OVERLAY | PRATT & SONS, INC. |  | JARROD GOOGINS | Laray Hamilton |  | 06/12/2023 | 10/14/2023
022934.00 | New Sharon |  | 022934.00 |  | 022934.00 | REGIONAL PROGRAM | NEW SHARON ROUTE 27 LARGE CULVERT REPLACEMENT | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | JEFFREY WALLACE | Guy Whittington |  | 07/05/2023 | 11/10/2023
024355.00 | Newcastle |  | 024355.00 |  | 024355.00 | REGIONAL PROGRAM | NEWCASTLE ROUTES 1B & 215, DRAINAGE IMPROVEMENTS | PRATT & SONS, INC. |  | BEECHER WHITCOMB | Robert K Betz |  | 10/30/2023 | 05/22/2024
027324.00 | Newport |  | 2732800 |  | 027328.00 | REGIONAL PROGRAM | NEWPORT US ROUTE 2, CYCLICAL PAVEMENT RESURFACING | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Randall Barrows |  | 04/24/2024 | 11/07/2024
024153.00 | Nobleboro, Waldoboro |  | 2416110 |  | 024161.10 | REGIONAL PROGRAM | NOBLEBORO - WALDOBORO, US ROUTE 1 1 1/4" OVERLAY | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  | DEAN ROWLANDS | Robert K Betz |  | 06/26/2022 | 06/30/2024
023693.00 | North Yarmouth |  |  |  | 023693.00 | REGIONAL PROGRAM | NORTH YARMOUTH, ROUTE 115 LARGE CULVERT REPLACEMENT 2369 | A H GROVER, INC. |  |  | Laray Hamilton |  | 07/15/2024 | 10/05/2024
024153.00 | Northport |  | 2415900 |  | 024159.00 | REGIONAL PROGRAM | NORTHPORT, US ROUTE 1 MILL & FILL | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  | DEAN ROWLANDS | Robert K Betz |  | 06/26/2022 | 06/30/2024
025287.00 | Norway, Oxford |  | 025287.00 |  | 025287.00 | REGIONAL PROGRAM | OXFORD-NORWAY, ROUTE 26 MILL AND FILL | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | BRIAN MOUSSEAU | Laray Hamilton |  | 07/10/2023 | 10/14/2023
023697.00 | Oakfield |  |  |  | 023697.00 | REGIONAL PROGRAM | LARGE CULVERT REPLACEMENT | J. MCLAUGHLIN CONSTRUCTION, LLC |  |  | Roger Soucy |  | 07/24/2024 | 10/14/2024
025177.00 | Oakfield |  | 025177.00 |  | 025177.00 | MULTIMODAL PROGRAM | OAKFIELD, REPLACEMENT OF THOMAS BROOK RAIL BRIDGE (#7825) | SARGENT CORPORATION |  | JOHN RODRIGUE | Aurele Gorneau Ii |  | 06/03/2024 | 08/21/2026
029489.00 | Ogunquit |  |  |  | 029493.00 | MAINTENANCE | MILL & FILL REGION 1 OGUNQUIT | GLIDDEN EXCAVATING & PAVING, INC. |  |  | ?
025961.00 | Old Orchard Beach |  | 2596500 |  | 025965.00 | REGIONAL PROGRAM | OLD ORCAHRD BEACH ROUTE 5 MILL AND FILL | SHAW BROTHERS CONSTRUCTION, INC. |  | NOAH FRENCH | Laray Hamilton |  | 09/06/2023 | 05/15/2024
025961.00 | Old Orchard Beach |  | 2596100 |  | 025961.00 | REGIONAL PROGRAM | OLD ORCHARD BEACH UNION AVENUE MILL AND FILL | SHAW BROTHERS CONSTRUCTION, INC. |  | NOAH FRENCH | Laray Hamilton |  | 09/06/2023 | 05/15/2024
025087.00 | Old Town |  | 2510100 |  | 025101.00 | BRIDGE PROGRAM | OLD TOWN, I-95 INTERCHANGE 53 BR 6062 | OLYMPUS PAINTING CONTRACTORS, INC. |  | TIMOTHY HEBERT | Devin Anderson |  | 07/11/2022 | 11/30/2024
022950.01 | Old Town |  | 2189401 |  | 022950.01 | HIGHWAY PROGRAM | OLD TOWN, INTERSECTION IMPROVEMENTS, STILLWATER AVE. | GORDON CONTRACTING INC. |  | JOSEPH GRAHAM | Rhobe Moulton |  | 07/08/2023 | 11/20/2024
025087.00 | Old Town |  | 2553100 |  | 025531.00 | BRIDGE PROGRAM | OLD TOWN, I-95 NB/ KIRKLAND RD BR 6059 | OLYMPUS PAINTING CONTRACTORS, INC. |  | TIMOTHY HEBERT | Devin Anderson |  | 07/11/2022 | 11/30/2024
025087.00 | Old Town |  | 2553300 |  | 025533.00 | BRIDGE PROGRAM | OLD TOWN, ROUTE 43/ I-95 BR 6061 | OLYMPUS PAINTING CONTRACTORS, INC. |  | TIMOTHY HEBERT | Devin Anderson |  | 07/11/2022 | 11/30/2024
027563.00 | Orland |  | 027563.00 |  | 027563.00 | MAINTENANCE | ORLAND ROUTE 166 CULVERT REPLACEMENT | L.G. WHITCOMB LANDSCAPING |  | MATT CONNOR | John Devin |  | 06/20/2022
025999.00 | Orono |  | 2599900 |  | 025999.00 | MULTIMODAL PROGRAM | ORONO: LIGHTING IMPROVEMENTS AT I-95 EXIT193 | MOULISON ELECTRIC, INC. |  |  | Aurele Gorneau Ii |  | 04/01/2024 | 10/11/2024
022256.00 | Palmyra |  | 2225600 |  | 022256.00 | BRIDGE PROGRAM | PALMYRA, HANSON BRIDGE REPL | SARGENT CORPORATION |  |  | Mark Parlin |  | 06/05/2024 | 11/20/2024
028489.00 | Paris |  | 028489.00 |  | 028489.00 | MAINTENANCE | SOUTH PARIS SALT STORAGE BUILDING | J PRATT CONSTRUCTION |  | BOB BOULAY | Joe Tedford
023128.00 | Perham |  | 023128.00 |  | 023128.00 | BRIDGE PROGRAM | PERHAM, SALMON STREAM BRIDGE REPLACEMENT. | SODERBERG COMPANY, INC. |  | JOHN RODRIGUE | Jason Stetson |  | 05/29/2024 | 10/16/2024
025129.00 | Peru |  | 2544300 |  | 025443.00 | REGIONAL PROGRAM | PERU, ROUTE 108 1 1/4" OVERLAY | PIKE INDUSTRIES, INC. |  | WYATT JOHNSON | Guy Whittington |  | 06/27/2022 | 11/15/2023
023603.00 | Pittsfield |  | 2360300 |  | 023603.00 | BRIDGE PROGRAM | I-95 SB/ RTE 152 BR DECK REPL | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | TIMOTHY HEBERT | Devan Eaton |  | 09/19/2022 | 06/18/2024
023603.00 | Pittsfield |  | 2361300 |  | 023613.00 | BRIDGE PROGRAM | I95 SB/ SEBASTICOOK RIVER BR REHAB | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | TIMOTHY HEBERT | Devan Eaton |  | 09/19/2022 | 06/18/2024
023603.00 | Pittsfield |  | 2360900 |  | 023609.00 | BRIDGE PROGRAM | I95 SB/ NORTH MAIN ST BR REHAB | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | TIMOTHY HEBERT | Devan Eaton |  | 09/19/2022 | 06/18/2024
023603.00 | Pittsfield |  | 2360700 |  | 023607.00 | BRIDGE PROGRAM | I95 NB/ N MAIN ST BR SUPERSTR REPL AND RDWY REC | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | TIMOTHY HEBERT | Devan Eaton |  | 09/19/2022 | 06/18/2024
025275.00 | Poland |  | 2527500 |  | 025275.00 | MULTIMODAL PROGRAM | POLAND, INSTALL SIGNAL AT INTERSECTION OF ROUTE 26 AND ROUTE | ELECTRIC LIGHT CO. INC. |  | TYLER CAMICK | Aurele Gorneau Ii |  | 04/01/2024 | 06/28/2024
022394.00 | Portland |  | 2239400 |  | 022394.00 | REGIONAL PROGRAM | PORTLAND, INTERSTATE 295 NORTHBOUND MEDIAN | PIKE INDUSTRIES, INC. |  | WAYNE WATSON | Shawn Smith |  | 07/24/2023 | 11/30/2023
026055.01 | Portland |  | 2605501 |  | 026055.01 | HIGHWAY PROGRAM | Portland Building Demolition | DREW CORPORATION |  |  | Ernest Martin |  | 02/01/2024 | 08/08/2027
026242.00 | Portland, Raymond, Westbrook |  | 2624200 |  | 026242.00 | MULTIMODAL PROGRAM | STATEWIDE: INSTALLATION OF SIGNAL BACKPLATES ON ROUTE 302 | ELECTRIC LIGHT CO. INC. |  |  | Gerald Dostie |  | 06/03/2024 | 12/31/2024
022394.00 | Portland, South Portland |  | 2242001 |  | 022420.01 | REGIONAL PROGRAM | SOUTH PORTLAND-PORTLAND INTERSTATE 295 NORTHBOUND MILL & FIL | PIKE INDUSTRIES, INC. |  | WAYNE WATSON | Shawn Smith |  | 05/15/2022 | 10/21/2023
023454.00 | Presque Isle |  | 23454.00 |  | 023454.00 | MULTIMODAL PROGRAM | PRESQUE ISLE, RAILROAD BRIDGE REHABILITATION | CPM CONSTRUCTORS |  | LEWIS BENNER | Nathaniel Benoit |  | 02/09/2022 | 12/27/2023
026440.00 | Prospect |  | 2644000 |  | 026440.00 | BRIDGE PROGRAM | MARSH BRIDGE (#2510) OVER CARLEY BROOK. LOCATED 0.40 OF A MI | DEVOE CONSTRUCTION |  |  | Jason Stetson |  | 12/20/2023 | 11/29/2024
024595.00 | Prospect, Verona Island |  |  |  | 024595.00 | BRIDGE PROGRAM | PROSPECT - VERONA ISLAND, PENOBSCOT NARROWS BR & OBS LTG | TOM HEDSTROM ELECTRIC PC |  |  | Denver Small |  | 11/15/2023 | 09/11/2024
022862.00 | Randolph, Washington |  | 022862.00 |  | 022862.00 | MAINTENANCE | JEFFERSON, FORESTRY & CANOPY CLEARING | INTEGRITY FOREST MANAGEMENT |  | MATT WHITCOMB | John Skelley |  | 08/03/2020 | 09/25/2020
028569.00 | Rangeley Plt |  | 028569.00 |  | 028569.00 | MAINTENANCE | RANGLEY PLT, FORESTRY & CANOPY CLEARING | M & H LOGGING, LLC |  |  | ?
025919.00 | Raymond |  | 2591900 |  | 025919.00 | MULTIMODAL PROGRAM | FRYE ISLAND: RE-WIRING OF FRYE ISLAND FERRY TERMINAL | MOULISON ELECTRIC, INC. |  |  | Brian Keezer |  | 10/18/2023 | 01/31/2025
025921.00 | Raymond |  | 2592100 |  | 025921.00 | MULTIMODAL PROGRAM | RAYMOND: FRYE ISLAND FERRY LANDING DECK REPLACEMENT | CHESTERFIELD ASSOCIATES, INC. |  |  | Brian Keezer |  | 02/09/2024 | 05/01/2024
022194.00 | Rockland |  | ROCKLAND - STATE FERRY VESSEL |  | 022194.00 | MULTIMODAL PROGRAM | ROCKLAND - STATE FERRY VESSEL REPLACEMENT | SENESCO MARINE |  | ALEX ANDERSON | Nathaniel Benoit |  | 10/01/2021 | 10/09/2024
024153.00 | Rockland, Rockport, Warren |  | 2415300 |  | 024153.00 | REGIONAL PROGRAM | WARREN-ROCKLAND-ROCKPORT, ROUTE 90 MILL & FILL | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  | DEAN ROWLANDS | Robert K Betz |  | 06/26/2022 | 06/30/2024
025955.01 | Rockport |  | 025955.03 |  | 025955.03 | MULTIMODAL PROGRAM | ROCKPORT: MODIFY TRAFFIC SIGNAL AT RT. 17 AND RT. 90 | DAGLE ELECTRICAL CONSTRUCTION CORP. |  | KAREN LIBBY | Mackenzie Kersbergen |  | 01/22/2024 | 11/06/2024
023027.00 | Rumford |  | 023027.00 |  | 023027.00 | MAINTENANCE | RUMFORD BRIDGE LIGHTING | A. D. ELECTRIC, INC. |  | DOUG COOMBS 215-4051 | Douglas Coombs
025293.00 | Rumford |  | 2529300 |  | 025293.00 | BRIDGE PROGRAM | MORSE BRIDGE (#2585) OVER THE ANDROSCOGGIN RIVER. LOCATED 0. | CPM CONSTRUCTORS |  |  | Jason Stetson |  | 04/16/2024 | 11/01/2024
025955.01 | Sabattus |  | 025955.01 |  | 025955.01 | MULTIMODAL PROGRAM | SABATTUS: MODIFY TRAFFIC SIGNAL AT RT. 126 AND RT. 9 | DAGLE ELECTRICAL CONSTRUCTION CORP. |  | KAREN LIBBY | Mackenzie Kersbergen |  | 01/22/2024 | 11/06/2024
025955.01 | Sabattus |  | 025955.02 |  | 025955.02 | MULTIMODAL PROGRAM | SABATTUS: MODIFY TRAFFIC SIGNAL AT RT.126 AND RT.132 | DAGLE ELECTRICAL CONSTRUCTION CORP. |  | KAREN LIBBY | Mackenzie Kersbergen |  | 01/22/2024 | 11/06/2024
024163.00 | Saco |  | 024163.00 |  | 024163.00 | REGIONAL PROGRAM | SACO, US ROUTE 1 MILL AND FILL | PIKE INDUSTRIES, INC. |  | MATTHEW GALLAGHER | Laray Hamilton |  | 09/05/2023 | 10/04/2023
023274.00 | Saco |  | 2327400 |  | 023274.00 | MULTIMODAL PROGRAM | SACO: PARK-AND-RIDE IMPROVEMENTS | SHAW BROTHERS CONSTRUCTION, INC. |  |  | Daniel Loring |  | 11/27/2023 | 10/11/2024
023759.10 | Saint George, South Thomaston |  | 023759.10 |  | 023759.10 | REGIONAL PROGRAM | THOMASTON & ST GEORGE RTE 73 CHIP | HAGAR ENTERPRISES, INC. |  | QUINN WARREN | Robert K Betz |  | 08/14/2023 | 05/11/2024
019001.00 | Sanford |  | AC-STP-1900(100)X |  | 019001.00 | HIGHWAY PROGRAM | SANFORD INTERSECTION IMPROVEMENTS | R. J. GRONDIN & SONS |  | MATTHEW GUESS | Ernest Martin |  | 09/06/2023 | 08/17/2024
022498.00 | Sanford, Wells |  | 2249800 |  | 022498.00 | REGIONAL PROGRAM | WELLS-SANFORD, ROUTE 109 4" COLD IN PLACE RECYCLE | PIKE INDUSTRIES, INC. |  | MATTHEW GUESS | Laray Hamilton |  | 08/08/2021 | 06/30/2023
025961.00 | Scarborough |  | 2596900 |  | 025969.00 | REGIONAL PROGRAM | SCARBOROUGH EAST GRAND AVENUE MILL AND FILL | SHAW BROTHERS CONSTRUCTION, INC. |  | NOAH FRENCH | Laray Hamilton |  | 09/06/2023 | 05/15/2024
026957.00 | Searsmont |  | 026957.00 |  | 026957.00 | MAINTENANCE | SEARSMONT, INSTREAM CULVERT REPLACEMENTS | F C WORK & SONS, INC. |  | MATT WHITCOMB | Jamie Andrews |  | 09/01/2021 | 10/01/2021
017281.00 | Searsport |  | NH-1728(100)E |  | 017281.00 | HIGHWAY PROGRAM | WIN 17281.00 SEARSPORT ROUTE 1 | GORDON CONTRACTING INC. |  | BEECHER WHITCOMB | Ernest Martin |  | 04/02/2023 | 03/28/2025
025240.00 | Sherman |  | 025240.00 |  | 025240.00 | MAINTENANCE | SHERMAN TRUCK STORAGE GARAGE | NICKERSON & O'DAY, INC. |  | RICKY GRADIE | Robert Watson
028025.00 | Sherman |  | 028025.00 |  | 028025.00 | MAINTENANCE | SHERMAN INSTALLATION OF SEWER SYSTEM | IMPACT AUTO INC. |  | KEVIN BUTLER | ?
027709.00 | Sidney |  | 027709.00 |  | 027709.00 | MAINTENANCE | SIDNEY, INSTREAM CULVERT REPLACEMENTS MIDDLE ROAD | LITTLEFIELD’S CONSTRUCTION |  | MATT WHITCOMB | Brian Reeves |  | 05/17/2022 | 09/30/2022
026115.00 | Skowhegan |  | 2611500 |  | 026115.00 | BRIDGE PROGRAM | SKOWHEGAN, SMITH POND BR DECK REPL | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  |  | Mark Parlin |  | 05/13/2024 | 10/14/2024
023697.00 | Smyrna |  | 2375500 |  | 023755.00 | REGIONAL PROGRAM | LARGE CULVERT REPLACEMENT | J. MCLAUGHLIN CONSTRUCTION, LLC |  |  | Roger Soucy |  | 06/05/2024 | 10/29/2024
022260.01 | Solon |  | 021894.01 |  | 022260.01 | BRIDGE PROGRAM | SOLON, MAIN STREET BRIDGE REPL | T BUCK CONSTRUCTION, INC. |  | DAVID DOUCETTE | Andrew Lathe |  | 03/13/2023 | 06/27/2024
026690.00 | South Portland |  | 026690.00 |  | 026690.00 | PLANNING | SOUTH PORTLAND, SHIM & OVERLAY | COASTAL ROAD REPAIR LLC. |  | SUZZANE NORTON | John Skelley |  | 08/07/2023 | 11/30/2023
020535.00 | South Portland |  | 020535.00 |  | 020535.00 | BRIDGE PROGRAM | RESTORE AQUATIC ORGANISM PASSAGE IN RED BROOK AT I-295 RAMP | CULVERT REHABILITATION SERVICES (DIV. OF CLH & SON) |  | NICHOLAS BOYD | Devan Eaton |  | 04/01/2024 | 07/08/2024
020535.00 | South Portland |  | 023601.00 |  | 023601.00 | BRIDGE PROGRAM | CULVERT REHABILITATION TO I-295 NB/ RED BROOK BRIDGE # 6295 | CULVERT REHABILITATION SERVICES (DIV. OF CLH & SON) |  | NICHOLAS BOYD | Devan Eaton |  | 04/01/2024 | 07/08/2024
022630.00 | Stonington |  | STP-2263(000) |  | 022630.00 | BRIDGE PROGRAM | OCEANVILLE BRIDGE (#3696) OVER OCEANVILLE THOROUGHFARE. LOCA | REED & REED, INC. |  |  | Andrew Lathe |  | 02/21/2024 | 10/30/2024
023476.00 | Swans Island |  | 2348000 |  | 023480.00 | MULTIMODAL PROGRAM | SWANS ISLAND, FENDER SYSTEM MODIFICATIONS | PROCK MARINE COMPANY |  | TYLER CAMICK | Aurele Gorneau Ii |  | 07/01/2021 | 05/31/2024
023454.00 | T11 R4 Wels |  | 23460.00 |  | 023460.00 | MULTIMODAL PROGRAM | T11 R4, RAILROAD BRIDGE REPLACEMENT | CPM CONSTRUCTORS |  | LEWIS BENNER | Nathaniel Benoit |  | 02/09/2022 | 12/27/2023
023454.00 | T11 R4 Wels |  | 23458.00 |  | 023458.00 | MULTIMODAL PROGRAM | T11 R4, RAILROAD BRIDGE REHABILITATION | CPM CONSTRUCTORS |  | LEWIS BENNER | Nathaniel Benoit |  | 02/09/2022 | 12/27/2023
018984.00 | The Forks Plt, West Forks Plt |  | 022362.00 |  | 022362.00 | BRIDGE PROGRAM | THE FORKS BRIDGE (#2841) OVER THE UPPER KENNEBEC RIVER. LOCA | BMB CONSTRUCTION LLC |  | RESIDENT? | Mark Parlin |  | 05/20/2024 | 11/25/2024
026700.00 | Thomaston |  | 026700.00 |  | 026700.00 | REGIONAL PROGRAM | THOMASTON, US ROUTE 1 ULTRA-THIN BONDED WEARING COURSE | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  | MATHIEU CUTLER | Robert K Betz |  | 09/25/2023 | 06/28/2024
023476.00 | Tremont |  | 2347600 |  | 023476.00 | MULTIMODAL PROGRAM | BASS HARBOR, FENDER SYSTEM MODIFICATIONS | PROCK MARINE COMPANY |  | TYLER CAMICK | Aurele Gorneau Ii |  | 07/01/2021 | 05/31/2024
023020.00 | Tremont |  | 2302000 |  | 023020.00 | HIGHWAY PROGRAM | TREMONT ROUTE 102A - SLOPE STABILIZATION | R F JORDAN & SONS CONSTRUCTION, INC. |  |  | Rhobe Moulton |  | 01/15/2024 | 07/02/2024
025143.00 | Trenton |  | 2601300 |  | 026013.00 | REGIONAL PROGRAM | TRENTON, ROUTE 3 STATEWIDE WEIGH AREAS | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | CARMEN FORZETTING | Randall Barrows |  | 06/11/2023 | 12/31/2023
017163.03 | Trenton |  | 1716303 |  | 017163.03 | MULTIMODAL PROGRAM | TRENTON, ACADIA GATEWAY CENTER | NICKERSON & O'DAY, INC. |  | EDWARD KARPINSKI | Brian Keezer |  | 05/03/2023 | 05/03/2025
017163.03 | Trenton |  | 1716303 |  | 017163.04 | MULTIMODAL PROGRAM | TRENTON, ACADIA GATEWAY CENTER | NICKERSON & O'DAY, INC. |  | EDWARD KARPINSKI | Brian Keezer |  | 05/03/2023 | 05/03/2025
025417.10 | Turner |  | 025417.10 |  | 025417.10 | REGIONAL PROGRAM | TURNER ROUTE 219 PUGMILL | PRATT & SONS, INC. |  | HEATHER GROVES | Guy Whittington |  | 07/13/2023 | 10/13/2023
020421.00 | Van Buren |  | NHPP-2042(100) |  | 020421.00 | REGIONAL PROGRAM | RT.1 RECONSTRUCTION & REHABILITATION | SODERBERG COMPANY, INC. |  | ANTHONY HUSTON | Roger Soucy |  | 06/30/2023 | 12/20/2024
026700.00 | Waldoboro, Warren |  | 026704.00 |  | 026704.00 | REGIONAL PROGRAM | WALDOBORO-WARREN ROUTE 1 - UTBWC | ALL STATES ASPHALT DBA ALL STATES CONSTRUCTION INC |  | MATHIEU CUTLER | Robert K Betz |  | 09/25/2023 | 06/28/2024
026396.00 | Warren |  | 2639600 |  | 026396.00 | HIGHWAY PROGRAM | WARREN, RT 90, RPLACEMENT OF LARGE CULVERT #46641 | PRATT & SONS, INC. |  |  | Douglas Coombs |  | 05/15/2024 | 09/24/2024
026154.00 | Warren |  | 2615400 |  | 026154.00 | BRIDGE PROGRAM | WARREN, ST, GEORGE RIVER BR DECK REPL | T BUCK CONSTRUCTION, INC. |  | RESIDENT? | Devan Eaton |  | 04/29/2024 | 12/13/2024
022022.00 | Washburn |  | 022022.00 |  | 022022.00 | MULTIMODAL PROGRAM | WASHBURN: NEW SIDEWALKS ON MAIN, HINES AND SCHOOL ST. | SODERBERG COMPANY, INC. |  | RESIDENT? | Aurele Gorneau Ii |  | 04/29/2024 | 09/27/2024
022022.00 | Washburn |  | 025167.00 |  | 025167.00 | REGIONAL PROGRAM | WASHBURN: DRAINAGE IMPROVEMENTS ON RT. 164 AND RT. 228 | SODERBERG COMPANY, INC. |  | RESIDENT? | Roger Soucy |  | 05/27/2024 | 10/10/2025
021894.01 | Waterville |  | 021894.01 |  | 021894.01 | BRIDGE PROGRAM | WATERVILLE, I-95 SB/WEBB RD BR REPL | WYMAN & SIMPSON, INC. |  | CANDACE THOMPSON | Devan Eaton |  | 08/31/2022 | 09/30/2024
023138.00 | Waterville |  | 2313800 |  | 023138.00 | BRIDGE PROGRAM | WATERVILLE-WINSLOW, TICONIC BR REPL | CIANBRO CORPORATION |  | TRAVIS HAMEL | Mark Parlin |  | 07/25/2023 | 12/22/2026
028845.00 | Waterville |  | 028845.00 |  | 028845.00 | MAINTENANCE | WATERVILLE, INSTREAM CULVERT REPLACEMENT WEBB ROAD | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | MATT WHITCOMB | Peter Newkirk |  | 04/01/2023 | 05/01/2023
023505.00 | Waterville |  | 2350500 |  | 023505.00 | BRIDGE PROGRAM | OAKLAND - WATERVILLE, ARMSTRONG RD. BR REPL | CPM CONSTRUCTORS |  | CANDACE THOMPSON | Devan Eaton |  | 08/21/2023 | 11/29/2024
021894.01 | Waterville |  | 021900.01 |  | 021900.01 | BRIDGE PROGRAM | WATERVILLE, I-95 NB/WEBB RD BR REPL | WYMAN & SIMPSON, INC. |  | CANDACE THOMPSON | Devan Eaton |  | 08/31/2022 | 09/30/2024
022266.00 | Webster Plt |  | 2226600 |  | 022266.00 | BRIDGE PROGRAM | WEBSTER PLANTATION, MATTAGODUS BR REPL. | EUROVIA ATLANTIC COAST LLC DBA NORTHEAST PAVING |  | STEVE MOORE | Mark Parlin |  | 06/07/2023 | 01/03/2024
023188.00 | Wells |  | 2353500 |  | 023535.00 | BRIDGE PROGRAM | BUFFAM BRIDGE (#2107) OVER WEBHANNET RIVER. | SCOTT CONSTRUCTION CORPORATION |  |  | Brian Nichols |  | 04/03/2024 | 10/30/2024
029489.00 | Wells |  |  |  | 029491.00 | MAINTENANCE | MILL & FILL REGION 1 WELLS | GLIDDEN EXCAVATING & PAVING, INC. |  |  | ?
027051.00 | Whitefield |  | 027051.00 |  | 027051.00 | MAINTENANCE | WHITEFIELD & ALNA, FORESTRY & CANOPY CLEARING | COMPREHENSIVE LAND TECHNOLOGIES |  | MATT WHITCOMB | Brian Reeves |  | 09/14/2021 | 11/24/2021
023803.00 | Winslow |  | 2380300 |  | 023803.00 | REGIONAL PROGRAM | WINSLOW, ROUTE 100A LARGE CULVERT REHABILITATION | CULVERT REHABILITATION SERVICES (DIV. OF CLH & SON) |  |  | Robert K Betz |  | 06/03/2024 | 08/21/2024
025305.00 | Wiscasset, Woolwich |  | 025305.00 |  | 025305.00 | BRIDGE PROGRAM | WOOLWICH-WISCASSET, NEW BR SUPERSTR REPL | T BUCK CONSTRUCTION, INC. |  | GLENN PHILBROOK | Devan Eaton |  | 04/22/2024 | 12/27/2024
018767.01 | Woodstock |  | 1728001 |  | 018767.01 | HIGHWAY PROGRAM | WOODSTOCK, HIGHWAY RECONSTRUCTION, | GORDON CONTRACTING INC. |  | SHANE AMOROSO | Rhobe Moulton |  | 11/12/2020 | 07/31/2024
025129.00 | Woodstock |  | 2513100 |  | 025131.00 | REGIONAL PROGRAM | WOODSTOCK, ROUTE 26 1-1/4" OVERLAY | PIKE INDUSTRIES, INC. |  | WYATT JOHNSON | Guy Whittington |  | 06/27/2022 | 11/15/2023
025288.00 | Woolwich |  | 025288.00 |  | 025288.00 | MAINTENANCE | WOOLWICH & WISCASSET FORESTRY CLEARING | COMPREHENSIVE LAND TECHNOLOGIES |  | MATT WHITCOMB | David Allen |  | 10/05/2020 | 12/18/2020
023929.00 | Woolwich |  | 2392900 |  | 023929.00 | BRIDGE PROGRAM | WOOLWICH, STATION 46 BRIDGE REPLACEMENT. | REED & REED, INC. |  | GLENN PHILLBROOK | Devan Eaton |  | 01/03/2022 | 07/15/2026
023929.00 | Woolwich |  | 2392900 |  | 023929.01 | BRIDGE PROGRAM | WOOLWICH, PLEASANT COVE BRIDGE CONSTRUCTION. | REED & REED, INC. |  | GLENN PHILLBROOK | Devan Eaton |  | 01/10/2022 | 07/15/2026
027174.00 | Woolwich |  | 027174.00 |  | 027174.00 | HIGHWAY PROGRAM | WOOLWICH ROUTE 127 LARGE CULVERT REPLACEMENT LC#228491 | PRATT & SONS, INC. |  |  | Douglas Coombs |  | 04/15/2024 | 05/31/2024
023106.01 | Yarmouth |  | 023825.00 |  | 023825.00 | MULTIMODAL PROGRAM | YARMOUTH, SHARED USE PATH | CPM CONSTRUCTORS |  | KAYLA STICKNEY | Brian Keezer |  | 11/17/2021 | 11/15/2024
023106.01 | Yarmouth |  | 023106.01 |  | 023106.01 | BRIDGE PROGRAM | YARMOUTH, I295 NB BR 5833 & I295 SB BR 1509 REPL | CPM CONSTRUCTORS |  | KAYLA STICKNEY | Devan Eaton |  | 11/17/2021 | 11/14/2024
029489.00 | York |  |  |  | 029489.00 | MAINTENANCE | MILL & FILL REGION 1 YORK | GLIDDEN EXCAVATING & PAVING, INC. |  |  | ?
018995.57 |  |  |  |  | 018995.57 | REGIONAL PROGRAM | REGION 5 CRACKSEAL | SEALCOATING, INC. DBA INDUS |  |  | Roger Soucy |  | 06/03/2024 | 09/27/2024
026598.00 |  |  | 26598.00 |  | 026598.00 | REGIONAL PROGRAM | WIN 26598.00, REGION 4 ADA IMPROVEMENTS | BMB CONSTRUCTION LLC |  | BILL LUCAS | Randall Barrows |  | 09/18/2023 | 12/01/2023
027199.00 |  |  | 027205.00 |  | 027205.00 | MAINTENANCE | YORK, WEARING SURFACE REPLACEMENT #3202 | GLIDDEN EXCAVATING & PAVING, INC. |  | ROB BETZ | ?
029481.00 |  |  |  |  | 029481.00 | MAINTENANCE | WINSLOW & ALBION, CULVERT REPLACEMENTS | N F LUCE, INC. |  |  | ? |  | 10/02/2023 | 11/30/2023
029479.00 |  |  |  |  | 029479.00 | MAINTENANCE | SIDNEY & OAKLAND, CULVERT REPLACEMENTS | ST. LAURENT & SON, INC |  |  | ? |  | 10/02/2023 | 11/30/2023
027199.00 |  |  | 027199.00 |  | 027199.00 | MAINTENANCE | KENNEBUNK, WEARING SURFACE REPLACEMENT #5883 | GLIDDEN EXCAVATING & PAVING, INC. |  | ROB BETZ | ?
025944.00 |  |  | 025944.00 |  | 025944.00 | MAINTENANCE | BROOKS, INSTREAM CULVERT REPLACEMENT | MAINE EARTH |  | MATTHEW WHITCOMB | Jamie Andrews |  | 09/28/2020 | 10/01/2020
027199.00 |  |  | 027201.00 |  | 027201.00 | MAINTENANCE | NORTH YARMOUTH, WEARING SURFACE REPLACEMENT #6156 | GLIDDEN EXCAVATING & PAVING, INC. |  | ROB BETZ | ?
028039.00 |  |  | 028039.00 |  | 028039.00 | MAINTENANCE | BENEDICTA & SILVER RIDGE TOWNSHIPS GRAVEL SURFACE REPAIR | M O HARRIS, INC. |  | KEVIN BUTLER | ?
027199.00 |  |  | 027249.00 |  | 027249.00 | MAINTENANCE | SANFORD/ALFRED, WEARING SURFACE REPLACEMENT #1265 | GLIDDEN EXCAVATING & PAVING, INC. |  | ROB BETZ | ?
027091.00 |  |  |  |  | 027091.00 | MAINTENANCE | BOOTHBAY SLOPE STABILIZATION | ST. LAURENT & SON, INC |  |  | Brian Reeves
027199.00 |  |  | 027203.00 |  | 027203.00 | MAINTENANCE | GORHAM, WEARING SURFACE REPLACEMENT #6445 | GLIDDEN EXCAVATING & PAVING, INC. |  | ROB BETZ | ?
BRIDGE PROGRAM
Name |  |  |  | Title |  |  |  |  | Phone |  |  | Location
Wayne Frankhauser |  |  |  | Program Manager |  |  |  |  | 207-624-3421 |  |  | Central
Eric Shepherd |  |  |  | Assistant Program Manager/Construction |  |  |  |  | 207-592-7825 |  |  | Central
Richard Myers |  |  |  | Assistant Program Manager/Design |  |  |  |  | 207-557-5985 |  |  | Central
Scott Rollins |  |  |  | Sr. Project Manager |  |  |  |  | 207-592-3499 |  |  | Central
Mike Wight |  |  |  | Sr. Project Manager |  |  |  |  | 207-624-3435 |  |  | Central
Devin Eaton |  |  |  | Sr. Project Manager |  |  |  |  | 207-624-3458 |  |  | Central
Devin Anderson |  |  |  | Area Construction Manager |  |  |  |  | 207-624-3402 |  |  | Central
Andrew Lathe |  |  |  | Sr. Project Manager |  |  |  |  | 207-441-7362 |  |  | Central
Travis Hamel |  |  |  | Area Construction Manager |  |  |  |  | 207-215-7312 |  |  | Central
Joseph Stilwell |  |  |  | Fabrication Engineer |  |  |  |  | 207-624-3336 |  |  | Central
CONTRACTS
Name |  |  |  | Title |  |  |  |  | Phone |  |  | Location
George Macdougall |  |  |  | Contracts Engineer |  |  |  |  | 207-624-3353 |  |  | Central
Kevin Hanlon |  |  |  | Document Review Manager |  |  |  |  | 207-624-3343 |  |  | Central
Leonard Lidback |  |  |  | Document Review/Project Closeout |  |  |  |  | 207-624-3502 |  |  | Central
Roxane Cleaves |  |  |  | Document Review/Project Closeout |  |  |  |  | 207-624-3533 |  |  | Central
Stephen Cain |  |  |  | Document Review/Project Closeout |  |  |  |  | 207-446-0521 |  |  | Central
Guy Berthiaume |  |  |  | Field Manager |  |  |  |  | 207-624-3534 |  |  | Central
Rebecca Snowden |  |  |  | Contractor payments |  |  |  |  | 207-624-3515 |  |  | Central
VACANT |  |  |  | Electronic Bidding/Web Page/Bid Tabs | [7 empty] | Central
Angela Latno |  |  |  | Elations/Prequal |  |  |  |  | 207-624-3519 |  |  | Central
Joseph Caraglia |  |  |  | Bid Openings/Amendments |  |  |  |  | 207-624-3472 |  |  | Central
HIGHWAY PROGRAM
Name |  |  |  | Title |  |  |  |  | Phone |  |  | Location
Bradford Foley |  |  |  | Program Manager |  |  |  |  | 207-624-3539 |  |  | Central
Stephen Bodge II |  |  |  | Assistant Program Manager /Design |  |  |  |  | 207-441-6850 |  |  | Central
Scott Bickford |  |  |  | Assistant Program Manager/Construction |  |  |  |  | 207-215-3857 |  |  | Central
Doug Coombs |  |  |  | Sr. Project Manager |  |  |  |  | 207-215-4051 |  |  | Central
Ernest Martin Jr. |  |  |  | Sr. Project Manager |  |  |  |  | 207-624-3381 |  |  | Central
Rhobe Moulton |  |  |  | Sr. Project Manager |  |  |  |  | 207-624-3391 |  |  | Central
Construction Support – see Regional Program
REGIONAL PROGRAM
Name |  |  |  | Title |  |  |  |  | Phone |  |  | Location
David Bernhardt |  |  |  | Program Manager |  |  |  |  | 207-446-1816 |  |  | Central
Scott Bickford |  |  |  | Assistant Program Manager/Construction |  |  |  |  | 207-215-3857 |  |  | Central
Denis lovely |  |  |  | Assistant Program Manager/Construction |  |  |  |  | 207-446-1976 |  |  | Central
Brian Luce |  |  |  | Paving/Pavement Mixes/Construction Support |  |  |  |  | 207-446-0360 |  |  | Central
Shawn Smith |  |  |  | Sr. Project Manager/Construction Support |  |  |  |  | 207-557-1663 |  |  | Central
LaRay Hamilton |  |  |  | Sr. Project Manager |  |  |  |  | 207-592-1367 |  |  | Region 1
Robert Betz |  |  |  | Sr. Project Manager |  |  |  |  | 207-624-8247 |  |  | Region 2
Guy Whittington |  |  |  | Sr. Project Manager |  |  |  |  | 207-562-4228 |  |  | Region 3
Randy Barrows |  |  |  | Sr. Project Manager |  |  |  |  | 207-592-2800 |  |  | Region 4
Roger Soucy |  |  |  | Sr. Project Manager |  |  |  |  | 207-215-8739 |  |  | Region 5
Tim Kelly |  |  |  | Paving/Construction Support |  |  |  |  | 207-215-2043 |  |  | Central
John McDonough |  |  |  | Construction Support |  |  |  |  | 207-215-2043 |  |  | Region 1
Ryan Hodgman |  |  |  | Construction Support |  |  |  |  | 207-592-7382 |  |  | Region 1
Tom Stevens |  |  |  | Construction Support |  |  |  |  | 207-592-4508 |  |  | Region 2
Mark Shibles |  |  |  | Construction Support |  |  |  |  | 207-592-6295 |  |  | Region 3
Jeramy Parker |  |  |  | Construction Support |  |  |  |  | 207-592-6141 |  |  | Region 4
Ryan Sullivan |  |  |  | Construction Support |  |  |  |  | 207-446-0118 |  |  | Region 5
MULTIMODAL PROGRAM
Name |  |  |  | Title |  |  |  |  | Phone |  |  | Location
Jeff Tweedie |  |  |  | Program Manager |  |  |  |  | 207-624-3427 |  |  | Central
Nathanial Benoit |  |  |  | Assistant Program Manager |  |  |  |  | 207-215-1590 |  |  | Central
Aurele Gorneau II |  |  |  | Sr. Project Manager |  |  |  |  | 207-624-3550 |  |  | Central
Brian Keezer |  |  |  | Sr. Project Manager |  |  |  |  | 207-624-3612 |  |  | Central
Mackenzie Kersbergen |  |  |  | Sr. Project Manager |  |  |  |  | 207-215-3820 |  |  | Central
Gerald Dostie |  |  |  | Project Manager I |  |  |  |  | 207-530-6257 |  |  | Central
Dan Loring |  |  |  | Project Manager I |  |  |  |  | 207-624-3451 |  |  | Central
VACANT |  |  |  | Construction Manager | [7 empty] | Central
Kent Cooper |  |  |  | Landscape Architect |  |  |  |  | 207-624-3085 |  |  | Central
Larry Johannesman |  |  |  | Landscape Architect |  |  |  |  | 207-624-3404 |  |  | Central
REGIONAL ENGINEERS
Name |  |  |  | Title |  |  |  |  | Phone |  |  | Location
VACANT |  |  |  | Regional Engineer |  |  |  |  | 207-885-7000 |  |  | Region 1
Brian Reeves |  |  |  | Regional Engineer |  |  |  |  | 207-592-1402 |  |  | Region 2
Tony Beaulieu |  |  |  | Regional Engineer |  |  |  |  | 207-562-4228 |  |  | Region 3
John Devin |  |  |  | Regional Engineer |  |  |  |  | 207-592-5943 |  |  | Region 4
Brent Bubar |  |  |  | Regional Engineer |  |  |  |  | 207-557-3886 |  |  | Region 5
Mark Hume |  |  |  | M&O Contracts Manager |  |  |  |  | 207-778-8480 |  |  | Central
REGIONAL MANAGERS
Name |  |  |  | Title |  |  |  |  | Phone |  |  | Location
Travis Moore |  |  |  | Regional Manager |  |  |  |  | 207-885-7000 |  |  | Region 1
Jamie Andrews |  |  |  | Regional Manager |  |  |  |  | 207-624-8200 |  |  | Region 2
Thomas Roberts |  |  |  | Regional Manager |  |  |  |  | 207-562-4228 |  |  | Region 3
Steven Thebarge |  |  |  | Regional Manager |  |  |  |  | 207-941-4500 |  |  | Region 4
Robert Watson |  |  |  | Regional Manager |  |  |  |  | 207-764-2200 |  |  | Region 5
SAFETY
Name |  |  |  | Title |  |  |  |  | Phone |  |  | Location
Eula DeRocle |  |  |  | Safety |  |  |  |  | 207-446-6527 |  |  | Central
TESTING & LABS
Name |  |  |  | Title |  |  |  |  | Phone |  |  | Location
Rick Bradbury |  |  |  | Testing Engineer |  |  |  |  | 207-624-3482 |  |  | Central
Kevin Cummings |  |  |  | Quality Assurance Engineer |  |  |  |  | 207-624-3429 |  |  | Central
Nancy Bradbury |  |  |  | TIMS Manager |  |  |  |  | 207-215-7217 |  |  | Region 4
Mark Alley |  |  |  | Central Lab Engineer |  |  |  |  | 207-941-4526 |  |  | Region 4
James R. Robinson |  |  |  | Freeport Lab Supervisor |  |  |  |  | 207-707-2501 |  |  | Freeport
TRAFFIC SERVICES
Name |  |  |  | Title |  |  |  |  | Phone |  |  | Location
Stephen Landry |  |  |  | State Traffic Engineer |  |  |  |  | 207-624-3632 |  |  | Central
Region Main Office |  |  |  | Phone
Region 1 |  |  |  | 207-885-7000
Region 2 |  |  |  | 207-624-8200
Region 3 |  |  |  | 207-562-4228
Region 4 |  |  |  | 207-941-4500
Region 5 |  |  |  | 207-764-2060
*Note: Construction Begin date is based on forecast or actual dates. If there is no actual date, the forecast date is used.
List is filtered on contracts with an Advertise actual date entered, Project status = 'Active' and projects have no Final Records Submitted date entered.
Contact: Phone numbers for project residents listed or offices listed
Source: Departmental contract and project management systems
Refresh Cycle: Weekly
Last Refresh: |  |  |  |  | 04/15/2024
1