## Sheet1
FEMA DIGITAL FLOOD INSURANCE RATE MAP SCHEDULE
County/Watershed | Project Manager | County EMA Director | Regional Planning Commission | Notes from the State Coordinator | Discovery Meeting | Flood Risk Review Meetings | Preliminary Map Issued | Revised Preliminary Maps Issued | Federal Register Publication | Newspaper Notice (2nd) | Appeals period Started | Appeals Period Close | Projected LFD Date | Final Effective Date
DIGITAL FLOOD INSURANCE RATE MAPPING IN PROGRESS
Aroostook: Model Zone A for the Fish, Aroostook, St. Francis River-St. John River, Becaguimec Stream-St. John River, and Meduxnekeag watersheds. Re-delineation 2' topo. | Pam Lombard USGS | Darren Woods | Jay Kamm | 11/23: The field work is close to completion. | 10/4/2022 | Work maps projected for the 3rd quarter 2026.
Androscoggin County | Pam Lombard USGS | Angela Molino | Erica Bufkins |  | 2023-12-12 | Work maps projected for the 1st quarter of 2027.
Oxford: Model Zone A/re-delineation 2' topo |  | Allyson Hill | Erica Bufkins | 11/23: This data will kept in FEMA's database for future FIS.
Upper Androscoggin Watershed: No new studies. Re-delineation to the 2' contours & modelled Zone As. | Greg Stewart USGS | Angela Molino | Erica Bufkins | The Upper Androscoggin River Watershed includes portions of Oxford and Franklin Counites. | 2020-11-17 | Work maps issued 1st quarter 2026
Lower Androscoggin Watershed | Aron Langly, ARC |  |  | Oxford County includes some of Presumpscot River Watershed. Franklin County | 2026-06-10 | Flood Risk Review meetings and work maps issued September 9, 10, 2026.
Dead River Watershed | Diana Rodriguez/COMPASS (AECOM & CDM Smith) |  |  | 11/23:Field surveys began in Jul 2023 | June 15,16, 2022 | Flood Risk Review work maps issued 3rd Quarter 2025. | Projected Franklin 4th quarter 2026, Somerset 1st quarter 2027
Hancock: 7 mi. stretch of Union River/Model Zone A/re-delineation 2' topo | Erik Danielson AECOM | Andrew Sankey | Averi Varney | 11/23: FEMA expected to initiate the LOMR process to update the map panels, rather than through the traditional process.
Lower Kennebec River Watershed | Erik Danielson AECOM |  |  |  | 11/9 & 11/10/2022 | Projected 3rd quarter 2026
Mattawamkeag River Watershed | Caroline Jones ARC |  |  | Penobscot County only | 10/20221 | Flood Risk Review meeting and work maps August 25, 2026
Piscataquis River Watershed: 28 miles of new study | COMPASS (AECOM & CDM Smith) |  |  |  | 6/29 & 6/30/2022 | Flood Risk Review meeting and work maps June 30, 2026
St. George/Sheepscot River Watershed | Pam Lombard USGS |  |  |  | 2023-11-29 | Projected 1st quarter 2027
Saco River Watershed (Oxford County only) | COMPASS (AECOM & CDM Smith) |  |  |  | 5/10 & 5/11/2022 | Projected 2nd quarter 2026
Waldo County | Greg Stewart USGS |  |  |  | 2023-11-28 | Projected 1st quarter 2027
DIGITAL FLOOD INSURANCE RATE MAPS
County | Effective Date |  | Community | Effective Date |  | Watershed | Effective Date
Androscoggin | 2013-07-08 |  | Allagash | 2003-04-02 |  | Lower Penobscot River | 2023-07-19
Cumberland | 2024-06-20
Hancock | 2016-07-20 |  | Bangor | 2002-03-04
Kennebec | 2011-06-16 |  | Eagle Lake | 2006-08-02
Knox | 2016-07-06 |  | Fort Kent | 2016-07-06
Lincoln | 2015-07-16 |  | Mapleton | 2007-12-18
Oxford | 2009-07-07 |  | Orrington | 2002-07-17
Sagadahoc | 2015-07-16 |  | Saco | 2006-01-05
Waldo | 2015-07-06 |  | Van Buren | 2008-01-16
Washington | 2017-07-18
York | 2024-07-17
Prepared by: | Maine Floodplain Management Program |  |  |  |  | Last updated: September 16, 2026
Maine Office of Community Affairs
Noah Bezanson | Noah.Bezanson@maine.gov
(207) 287-8063
Janet Parker | janet.parker@maine.gov
(207) 287-9981

## Schedule
FLOODPLAIN MAPPING SCHEDULE
County | Scoping Discovery | Mapping Task Order | Final Effective Date | Project Length Including Scoping | Project Length for Mapping | Status
Androscoggin | 2006 | 2009 | 2013-07-08 | 7 | 4 | complete
Kennebec * | 2005 | 2006 | 2011-06-16 | 6 | 5 | complete
Oxford * | 2004 | 2006 | 2009-07-07 | 5 | 3 | complete
Cumberland | 2005 | 2006 | tbd | 9 | 7 | incomplete
York * | 2004 | 2005 | tbd | 9 | 8 | incomplete
Fort Kent | 2009 | 2009 | tbd | 4 | 4 | incomplete
Hancock | 2011 | 2011 | tbd | 2 | 2 | incomplete
Knox | 2011 | 2011 | tbd | 2 | 2 | incomplete
Lincoln | 2011 | 2011 | tbd | 2 | 2 | incomplete
Sagadahoc | 2011 | 2011 | tbd | 2 | 2 | incomplete
Waldo | 2011 | 2011 | tbd | 2 | 2 | incomplete
Washington | 2011 | 2012 | tbd | 2 | 1 | incomplete
Aroostook | unknown | unknown | unknown | unknown | unknown | unknown
Franklin | unknown | unknown | unknown | unknown | unknown | unknown
Penobscot | unknown | unknown | unknown | unknown | unknown | unknown
Piscataquis | unknown | unknown | unknown | unknown | unknown | unknown
Somerset | unknown | unknown | unknown | unknown | unknown | unknown

## Quality
FLOODPLAIN MAPPING SCHEDULE
Miles of Floodplain
County | Riverine | Coastal | Valid | unknown or Unveriefied
Androscoggin
Kennebec
Oxford
Cumberland
York
Fort Kent
Hancock
Knox
Lincoln
Sagadahoc
Waldo
Washington
Aroostook
Franklin
Penobscot
Piscataquis
Somerset